## PBE Build List-OLD (hidden)
Build Title | Model Year | Vehicle Family | Build Type | Build Phase | Build Status | Vehicle Quantity | TCF MRD | Weeks to MRD | TCF Build Start | Weeks to Build Start | X-Flag Due Date | Final BOM Due Date | Process Sheet Due Date | BOM Review Date | Build Lead | Build Location | Build Strategy | WBS Code | Tree FC# | Build Total # of Parts | Build % REQ | Build % PO | Build % Received | Build Cost | Build Tracker URL | Date Created | Last Modified
2024 XX Mule 2 | 2024 | XX | Mule | 2 | Active | 44 | 2021-08-02 | -3.1429 | 2021-08-16 | -1.1429 |  |  |  |  | Anurag Bansal | North Truck Garage | [8 empty] | https://docs.google.com/spreadsheets/d/18QOmQ2iddsRq7RasWzdtjeDlM_yyibF07-xJSNklfxY/ | 2021-06-14 | 2021-06-14
2028 XX Mule 1 | 2028 | XX | Mule | 1 | Active | 36 | 2021-10-04 | 5.8571 | 2021-10-18 | 7.8571 |  |  |  |  | Anurag Bansal | CTC |  | VD00222_EPBS_MU01 | [6 empty] | https://docs.google.com/spreadsheets/d/1GQfBNDlylWvJJdEG3MzocyckzDWQKnED9SSNJ6NShUE/ | 2021-07-29 | 2021-07-29
2030 XX Mule 2 | 2030 | XX | Mule | 2 | Active | 12 | 2021-09-06 | 1.8571 | 2021-09-20 | 3.8571 |  |  |  |  | Anurag Bansal | CTC |  | VD00987_EBPS_MU02 | [6 empty] | https://docs.google.com/spreadsheets/d/1EwQaGN9AkGR0D_L16ByevVy3QJaFSfD18lCEvHWf3aY/ | 2021-07-29 | 2021-07-29

## Add New Build-OLD (hidden)
Add New Build
Model Year | 2030
Vehicle Family | XX
Build Type | Mule
Build Phase | 2
Vehicle Quantity | 12
TCF MRD | 2021-09-06
TCF Build Start | 2021-09-20
Build Location | CTC
Build Strategy
Work Scope - 32wk (Plan)
WBS Code | VD00987_EBPS_MU02

## Edit Build Info-OLD (hidden)
Edit Build Info
Build Title
| Current Info | New Info
Model Year
Vehicle Family
Build Type
Build Phase
Vehicle Quantity
TCF MRD
TCF Build Start
Build Location
Build Strategy
Tree FC#
WBS Code
X-Flag Due Date
Final BOM Due Date
Process Sheet Due Date
BOM Review Date

## PBE Build List
Build Title | Model Year | Vehicle Family | Build Type | Build Phase | Build Status | Vehicle Quantity | TCF MRD | Weeks to MRD | TCF Build Start | Weeks to Build Start | X-Flag Due Date | Final BOM Due Date | Process Sheet Due Date | BOM Review Date | Build Lead | Build Location | Build Strategy | WBS Code | Work Scope - 32wk (Plan) | Work Scope - 32wk (Actual) | Work Scope - 32wk (Pulse) | Noun Name Delivered - 30wk (Plan) | Noun Name Delivered - 30wk (Actual) | Noun Name Delivered - 30wk (Pulse) | Build Phase Funding Approved - 19wk (Plan) | Build Phase Funding Approved - 19wk (Actual) | Build Phase Funding Approved - 19wk (Pulse) | Vehicle QTY Published - 26wk (Plan) | Vehicle QTY Published - 26wk (Actual) | Vehicle QTY Published - 26wk (Pulse) | Carrier Specs Published - 18wk (Plan) | Carrier Specs Published - 18wk (Actual) | Carrier Specs Published - 18wk (Pulse) | Build Plan Complete - 16wk (Plan) | Build Plan Complete - 16wk (Actual) | Build Plan Complete - 16wk (Pulse) | Donor Order Pulse - 14wk (Plan) | Donor Order Pulse - 14wk (Actual) | Donor Order Pulse - 14wk (Pulse) | Bridge Design Complete - 12wk (Plan) | Bridge Design Complete - 12wk (Actual) | Bridge Design Complete - 12wk (Pulse) | Overall Build Pulse | Build Status Comments | Build Shop Readiness | Part Delivery Pulse | Program Scope | Carrier | Tree FC# | Build Total # of Parts | Build % REQ | Build % PO | Build % Received | Build Cost | Build Tracker URL | Date Created | Last Modified
2026 XX Mule 4 | 2026 | XX | Mule | 4 | Active | 55 | 2021-07-05 | -7.1429 | 2021-07-19 | -5.1429 | 2021-06-21 | 2021-06-25 | 2021-07-05 | 2021-07-14 | Anurag Bansal | Truck Garage |  | VD00111_EBPS_MU04 | 2020-12-07 | 2020-12-07 | Green | 2020-12-21 | 2020-12-21 | Green | 2021-03-08 | 2021-03-08 | Yellow | 2021-01-18 | 2021-01-18 | Red | 2021-03-15 | 2021-03-15 | Yellow | 2021-03-29 | 2021-03-29 | Green | 2021-04-12 | 2021-04-12 | Green | 2021-04-26 | 2021-04-26 | Green | Yellow | test | Green | Red |  |  | FC00ABC98876/0.001 |  |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/ | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/ | 2021-08-03 | 2021-07-28
2025 HD Mule 2 Diesel | 2025 | HD | Mule | 2 Diesel | Active | 6 | 2022-01-03 | 18.8571 | 2022-01-17 | 20.8571 |  |  |  |  | Joe Fallert | Truck | Hoist | VD00243_EBPS_MU02 | 2021-06-07 |  |  | 2021-06-21 |  |  | 2021-09-06 |  |  | 2021-07-19 |  |  | 2021-09-13 |  |  | 2021-09-27 |  |  | 2021-10-11 |  |  | 2021-10-25 | [14 empty] | https://docs.google.com/spreadsheets/d/1tzfGtKXNDlo-snT1hfs3xMez_fsv7BOsXLLWoY5BxXA/ | 2021-07-06 | 2021-07-06
2025 LB Mule 2 | 2025 | LB | Mule | 2 | Active | 16 | 2022-01-03 | 18.8571 | 2022-01-17 | 20.8571 | 2021-11-08 | 2021-11-22 | 2021-12-13 | 2021-12-20 | Ryan Sheen | PVO | Hoist/Carrier | VD00322_EBPS_MU02 | 2021-06-07 |  |  | 2021-06-21 |  |  | 2021-09-06 |  |  | 2021-07-19 |  |  | 2021-09-13 |  |  | 2021-09-27 |  |  | 2021-10-11 |  |  | 2021-10-25 | [14 empty] | https://docs.google.com/spreadsheets/d/1X5IGZe0si7HazoXD8FaO7BQY-nIOUN0csRzH1hwU8g0/ | 2021-07-06 | 2021-07-07
2025 LB Mule 1 | 2025 | LB | Mule | 1 | Active | 3 | 2021-10-18 | 7.8571 | 2021-11-01 | 9.8571 | 2021-08-23 | 2021-09-06 | 2021-09-27 | 2021-10-04 | Ryan Sheen | PVO | Hoist | Hoist/Carrier | 2021-03-22 |  |  | 2021-04-05 |  |  | 2021-06-21 |  |  | 2021-05-03 |  |  | 2021-06-28 |  |  | 2021-07-12 |  |  | 2021-07-26 |  |  | 2021-08-09 | [8 empty] | FC00ABY75203/001 | [5 empty] | https://docs.google.com/spreadsheets/d/1i8J0eSKbe6sgLXIHnha8xdEhCExoA0oPKbw6eZ93PMY/ | 2021-07-08 | 2021-07-14
2023 VF BEV Mule 2 | 2023 | VF BEV | Mule | 2 | Active | 26 | 2021-04-26 | -17.1429 | 2021-05-17 | -14.1429 | 2021-03-01 | 2021-03-15 | 2021-04-05 | 2021-04-12 | Mollie Stafford | PVO/ Truck |  | VD00583 | 2020-10-05 |  |  | 2020-10-19 |  |  | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-25 |  |  | 2021-02-08 |  |  | 2021-02-22 | [8 empty] | FA00ADV39660 & FA00ADV39701 | [5 empty] | https://docs.google.com/spreadsheets/d/1WfsgfBPvWlWIsajfbpaMw-LZ-hOZAORh_h4CIm9j3b0/ | 2021-07-28 | 2021-07-28
2024 JL Mule 1 | 2024 | JL | Mule | 1 | Active | 153v+2b | 2021-11-15 | 11.8571 | 2021-11-29 | 13.8571 | 2021-09-20 | 2021-10-04 | 2021-10-25 | 2021-11-01 | Mollie Stafford |  | Hoist/Carrier | VD00713_EBPS_MU01 | 2021-04-19 |  |  | 2021-05-03 |  |  | 2021-07-19 |  |  | 2021-05-31 |  |  | 2021-07-26 |  |  | 2021-08-09 |  |  | 2021-08-23 |  |  | 2021-09-06 | [8 empty] | N/A | [5 empty] | https://docs.google.com/spreadsheets/d/1I06FDo2lu1Xb4hyqvSW9JyOj7bKYvd1fr-cIk_d4ppo/ | 2021-07-28 | 2021-07-30
2024 JT Mule 1 | 2024 | JT | Mule | 1 | Active | 21 | 2022-01-31 | 22.8571 | 2022-02-14 | 24.8571 |  |  |  |  | Mollie Stafford |  | Hoist/ Carrier |  | 2021-07-05 |  |  | 2021-07-19 |  |  | 2021-10-04 |  |  | 2021-08-16 |  |  | 2021-10-11 |  |  | 2021-10-25 |  |  | 2021-11-08 |  |  | 2021-11-22 | [8 empty] | N/A | [5 empty] | https://docs.google.com/spreadsheets/d/1EvmtR1L3y_OWxvrti3jNwUo6IjzykEWEGhEIr5q7kcc/ | 2021-07-28 | 2021-07-30
2026 XY Mule 3A | 2026 | XY | Mule | 3A | Active | 23 | 2021-08-23 | -0.14286 | 2021-09-06 | 1.8571 |  |  |  |  | Anurag Bansal | PVO |  | VD00111_EBPS_MU03 | 2021-01-25 |  |  | 2021-02-08 |  |  | 2021-04-26 |  |  | 2021-03-08 |  |  | 2021-05-03 |  |  | 2021-05-17 |  |  | 2021-05-31 |  |  | 2021-06-14 | [7 empty] | XY Mule 2 | FC00AAA11111/0.001.00001 | [5 empty] | https://docs.google.com/spreadsheets/d/1-SH6h794oCdHHqg-nTJsU2Rh4CxN361yHj9tb_fK1JA/ | 2021-08-05 | 2021-08-05
2026 XX Mule 9 | 2026 | XX | Mule | 9 | Active | 25 | 2021-10-15 | 7.4286 | 2021-10-29 | 9.4286 |  |  |  |  | Anurag Bansal | Pilot |  |  | 2021-03-19 |  |  | 2021-04-02 |  |  | 2021-06-18 |  |  | 2021-04-30 |  |  | 2021-06-25 |  |  | 2021-07-09 |  |  | 2021-07-23 |  |  | 2021-08-06 | [14 empty] | https://docs.google.com/spreadsheets/d/18iQwymYo5FXN0K3vqDlu_ns_p76J_vhQJGkGVPNWfhA/ | 2021-08-09 | 2021-08-09
2027 XX Mule 9A | 2027 | XX | Mule | 9A | Active | 12 | 2021-08-16 | -1.1429 | 2021-08-30 | 0.85714 |  |  |  |  | Anurag Bansal | PVO |  |  | 2021-01-18 |  |  | 2021-02-01 |  |  | 2021-04-19 |  |  | 2021-03-01 |  |  | 2021-04-26 |  |  | 2021-05-10 |  |  | 2021-05-24 |  |  | 2021-06-07 | [14 empty] | https://docs.google.com/spreadsheets/d/1iTJpbRfqMI7KW-e9pXaWrVHqpl12J9ZztjxqXUrXzeI/ | 2021-08-10 | 2021-08-10
Formulas:
Work Scope - 32wk (Plan) = [TCF Build Start]-7*32
Noun Name Delivered - 30wk (Plan) = [TCF Build Start]-7*30
Vehicle QTY Published - 26wk (Plan) = [TCF Build Start]-7*26
Carrier Specs Published - 18wk (Plan) = [TCF Build Start]-7*18
Build Plan Complete - 16wk (Plan) = [TCF Build Start]-7*16
Donor Order Pulse - 14wk (Plan) = [TCF Build Start]-7*14
Bridge Design Complete - 12wk (Plan) = [TCF Build Start]-7*12

## Add New Build
Add New Build
Model Year
Vehicle Family
Build Type
Build Phase
Vehicle Quantity
TCF MRD
TCF Build Start
Build Location
Build Strategy
WBS Code
Tree FC#
Program Scope
Carrier

## Edit Build Info
Edit Build Info
Build Title
| Current Info | New Info
Model Year
Vehicle Family
Build Type
Build Phase
Vehicle Quantity
TCF MRD
TCF Build Start
Build Location
Build Strategy
WBS Code
Tree FC#
X-Flag Due Date
Final BOM Due Date
Process Sheet Due Date
BOM Review Date
Program Scope
Carrier

## Build Detail Status
[14 empty] | Designs | [5 empty] | Ordering | [5 empty] | Delivery | [5 empty] | BOM | [5 empty] | Designs | [5 empty] | Ordering | [5 empty] | Delivery | [5 empty] | BOM
Build Title | Vehicle Family | Build Status | Vehicle Quantity | TCF MRD | Weeks to MRD | TCF Build Start | Weeks to Build Start | Build Lead | Build Location | BICEEP | System | PBE Engineer | Total # of Parts | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | Build Tracker URL
Build Title | Vehicle Family | Build Status | Vehicle Quantity | TCF MRD | Weeks to MRD | TCF Build Start | Weeks to Build Start | Build Lead | Build Location | BICEEP | System | PBE Engineer | Total # of Parts | Designs-G-% | Designs-Y-% | Designs-R-% | Designs-B-% | Designs-N-% | Designs-0-% | Ordering-G-% | Ordering-Y-% | Ordering-R-% | Ordering-B-% | Ordering-N-% | Ordering-0-% | Delivery-G-% | Delivery-Y-% | Delivery-R-% | Delivery-B-% | Delivery-N-% | Delivery-0-% | BOM-G-% | BOM-Y-% | BOM-R-% | BOM-B-% | BOM-N-% | BOM-0-% | Designs-G-# | Designs-Y-# | Designs-R-# | Designs-B-# | Designs-N-# | Designs-0-# | Ordering-G-# | Ordering-Y-# | Ordering-R-# | Ordering-B-# | Ordering-N-# | Ordering-0-# | Delivery-G-# | Delivery-Y-# | Delivery-R-# | Delivery-B-# | Delivery-N-# | Delivery-0-# | BOM-G-# | BOM-Y-# | BOM-R-# | BOM-B-# | BOM-N-# | BOM-0-# | Build Tracker URL
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Body | Underbody | Anurag Bansal | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Body | Battery Tray | Anurag Bansal | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Int/Ext | Fascias | Anurag Bansal | 1 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Engine Systems | Fuels | Anurag Bansal | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Chassis | Structures | Muhammad J Khan | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Chassis | Brakes | Anurag Bansal | 1 | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Powertrain | Powertrain | Chris Engles | 1 | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Int/Ext | Doors | Shrey Arodia | 20 | 60% | 30% | 10% | 0% | 0% | 0% | 30% | 40% | 30% | 0% | 0% | 0% | 10% | 60% | 30% | 0% | 0% | 0% | 10% | 30% | 60% | 0% | 0% | 0% | 12 | 6 | 2 | 0 | 0 | 0 | 6 | 8 | 6 | 0 | 0 | 0 | 2 | 12 | 6 | 0 | 0 | 0 | 2 | 6 | 12 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Electrical | Wiring | Ashar Khan | 16 | 0% | 100% | 0% | 0% | 0% | 0% | 38% | 25% | 38% | 0% | 0% | 0% | 31% | 25% | 44% | 0% | 0% | 0% | 50% | 38% | 13% | 0% | 0% | 0% | 0 | 16 | 0 | 0 | 0 | 0 | 6 | 4 | 6 | 0 | 0 | 0 | 5 | 4 | 7 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Body | End Items | Wesley Cialek | 2 | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 0% | 0% | 0% | 0% | 50% | 50% | 0% | 0% | 0% | 50% | 50% | 0% | 0% | 0% | 0% | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Engine Systems | Exhaust | Susan Burhan | 21 | 43% | 0% | 57% | 0% | 0% | 0% | 71% | 10% | 19% | 0% | 0% | 0% | 67% | 19% | 14% | 0% | 0% | 0% | 81% | 14% | 5% | 0% | 0% | 0% | 9 | 0 | 12 | 0 | 0 | 0 | 15 | 2 | 4 | 0 | 0 | 0 | 14 | 4 | 3 | 0 | 0 | 0 | 17 | 3 | 1 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Chassis | Knuckles | Zunaid Khan | 22 | 86% | 0% | 14% | 0% | 0% | 0% | 82% | 0% | 18% | 0% | 0% | 0% | 82% | 0% | 18% | 0% | 0% | 0% | 91% | 0% | 9% | 0% | 0% | 0% | 19 | 0 | 3 | 0 | 0 | 0 | 18 | 0 | 4 | 0 | 0 | 0 | 18 | 0 | 4 | 0 | 0 | 0 | 20 | 0 | 2 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2024 XX Mule 2 | XX | Active | 44 | 2021-08-02 | 6.7143 | 2021-08-16 | 8.7143 | Anurag Bansal | North Truck Garage | Chassis | Fuels | Michael Kaslly | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/18QOmQ2iddsRq7RasWzdtjeDlM_yyibF07-xJSNklfxY/

## Red Item Details
Build Title | Vehicle Family | Build Status | Vehicle Quantity | TCF MRD | Weeks to MRD | TCF Build Start | Weeks to Build Start | Build Lead | Build Location | Issue Category | BICEEP | System | PBE Engineer | Part Description | Part Number | Total Quantity | Comments to Report | REQ # | PO # | Supplier Name | Build Tracker URL
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Chassis | Knuckles | Zunaid Khan | Diesel Line Bracket | 1670H07448 |  | Design revision pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Chassis | Knuckles | Zunaid Khan | FUEL BUNDLE - CHASSIS DSL - DP 173WB/52GAL | 1670D77194 |  | Design not available in TeamCenter |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Chassis | Knuckles | Zunaid Khan | Fuel Delivery Module | 57008982AA | 2 | Need to confirm PN |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Engine Systems | Exhaust | Susan Burhan | FILLER PATCH PIECE - UREA TANK CROSSMEMBER | 1670H91792 |  | Design not released, long lead item |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Engine Systems | Exhaust | Susan Burhan | FUEL LINE TRANS BRKT | 1670H52564 |  | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Engine Systems | Exhaust | Susan Burhan | Diesel Line Bracket | 1670H07448 |  | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Engine Systems | Exhaust | Susan Burhan | TUBE ASSY - CHASSIS RETURN | 1670D72093 |  | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Engine Systems | Exhaust | Susan Burhan | FUEL TUBE - CHASSIS SUPPLY | 1670D72094 | 10 | Design not released | 4500720 |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Engine Systems | Exhaust | Susan Burhan | FSOV LINE | 1670D74120 | 10 | Design not released, can't send for RFQ, long lead item | 4500720 |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Engine Systems | Exhaust | Susan Burhan | FSOC TO HC DOSER LINE | 1670D72096 | 10 | Design not released | 4500720 |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Engine Systems | Exhaust | Susan Burhan | FUEL BUNDLE - CHASSIS DSL - DP 197WB/52GAL | 1670D76972 |  | Design not released | 4500720 |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Engine Systems | Exhaust | Susan Burhan | Fuel Delivery Module | 57008984AA | 3 | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Engine Systems | Exhaust | Susan Burhan | Fuel Delivery Module | 57008983AA | 1 | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Engine Systems | Exhaust | Susan Burhan | Fuel Delivery Module | 57008982AA | 2 | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Engine Systems | Exhaust | Susan Burhan | Fuel Delivery Module | 57008981AA | 7 | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Int/Ext | Doors | Shrey Arodia | APPLIQUE - RR QTR LT | 6UN17TRMAA | 45 |  |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - A-PILLAR RT | 6LF10TRMAA | 45 | Design Issues |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Design Issues | Int/Ext | Fascias | Anurag Bansal | [7 empty] | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Chassis | Knuckles | Zunaid Khan | FSOV LINE | 1670D74120 | 10 | Req in approval for 3 weeks |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Chassis | Knuckles | Zunaid Khan | FUEL BUNDLE - CHASSIS DSL HO - DJ 160WB/31GAL | 1670D75635 | 2 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Chassis | Knuckles | Zunaid Khan | FUEL BUNDLE - CHASSIS DSL HO - DJ 149WB/31GAL | 1670D68770 | 3 | Req in approval for 3 weeks |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Chassis | Knuckles | Zunaid Khan | Fuel Delivery Module | 57008982AA | 2 | Need to confirm PN |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Engine Systems | Exhaust | Susan Burhan | FSOV LINE | 1670D74120 | 10 | Design not released, can't send for RFQ, long lead item | 4500720 |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Engine Systems | Exhaust | Susan Burhan | FUEL BUNDLE - CHASSIS DSL HO - DJ 160WB/31GAL | 1670D75635 | 2 | Design not released, long lead item |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Engine Systems | Exhaust | Susan Burhan | FUEL BUNDLE - CHASSIS DSL HO - DJ 149WB/31GAL | 1670D68770 | 3 | Design not released, potential delay ordering |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Engine Systems | Exhaust | Susan Burhan | Fuel Delivery Module | 57008981AA | 7 | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Body | End Items | Wesley Cialek | BRACKET ASSY - FENDER TO HOOD HINGE RT | 68444808AA | 2 | Quote Pending |  |  | RCO | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Electrical | Wiring | Ashar Khan | WIRING ASSY - FRONT END MODULE | 68343527AB |  | Design Revision pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Electrical | Wiring | Ashar Khan | CHARGER - WIRELESS DEVICE | 68487354AA |  | REQ Submitted |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Electrical | Wiring | Ashar Khan | USB CHARGING PORT - DUAL | 68487349AB |  | Quote Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Electrical | Wiring | Ashar Khan | TOUCH DISPLAY - HVAC CONTROLS COMFORT & CONVENIENCE | 68438397AA |  | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Electrical | Wiring | Ashar Khan | SWITCH ASSY - DOOR MOUNTED 24 WAY DRIVER | 68341963AB |  | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Electrical | Wiring | Ashar Khan | MICROPHONE ASSY - MODULE & BEZEL | 6UA07TRMAA |  | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Int/Ext | Doors | Shrey Arodia | ARM - SIDE RT | 6UN92TRMAA | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Int/Ext | Doors | Shrey Arodia | BEZEL - UPR SEAT BELT QTR LWR TRIM PANEL LT | 6TL03TRMAA | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - D-PILLAR W/POWER LIFTGATE LT | 6TK98TRMAB | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - C-D PILLAR UPR BRIDGE RT | 6RS02TRMAA | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - C-PILLAR UPR LT | 6LF51TRMAA | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - A-PILLAR LT | 6LF11TRMAA | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Order Issues | Chassis | Brakes | Anurag Bansal | Random | 68525697AA | 1 | Waiting on Supplier Info |  |  | Magna | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Chassis | Knuckles | Zunaid Khan | FILLER PATCH PIECE - UREA TANK CROSSMEMBER | 1670H91792 |  | PO Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Chassis | Knuckles | Zunaid Khan | FUEL BUNDLE - CHASSIS DSL - DP 197WB/52GAL | 1670D76970 | [5 empty] | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Chassis | Knuckles | Zunaid Khan | FUEL BUNDLE - CHASSIS DSL HO - DJ 169WB/32GAL | 1670D77196 | 2 |  |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Chassis | Knuckles | Zunaid Khan | Fuel Delivery Module | 57008982AA | 2 | Need to confirm PN |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Engine Systems | Exhaust | Susan Burhan | FILLER PATCH PIECE - UREA TANK CROSSMEMBER | 1670H91792 |  | Design not released, long lead item |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Engine Systems | Exhaust | Susan Burhan | FUEL BUNDLE - CHASSIS DSL - DP 197WB/52GAL | 1670D76970 |  | Design not released, long lead item |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Engine Systems | Exhaust | Susan Burhan | FUEL BUNDLE - CHASSIS DSL HO - DJ 169WB/32GAL | 1670D77196 | 2 | Mfg issue, supplier needs design revised |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Body | End Items | Wesley Cialek | BRACKET ASSY - FENDER TO HOOD HINGE LT | 68444809AA | 2 | REQ pending approval for 3 weeks |  |  | RCO | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Electrical | Wiring | Ashar Khan | BEZEL ASSY - OVERHEAD | 6WC60TRMAA |  | Part will be available after MRD |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Electrical | Wiring | Ashar Khan | WIRING ASSY - FRONT END MODULE | 68343527AB |  | Design Revision pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Electrical | Wiring | Ashar Khan | SC/HEX.FLG.HD - PILOT.PT | 06506188AA |  | Part will be available after MRD but before TCF |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Electrical | Wiring | Ashar Khan | CHARGER - WIRELESS DEVICE | 68487354AA |  | REQ Submitted |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Electrical | Wiring | Ashar Khan | USB CHARGING PORT - DUAL | 68487349AB |  | Quote Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Electrical | Wiring | Ashar Khan | TOUCH DISPLAY - HVAC CONTROLS COMFORT & CONVENIENCE | 68438397AA |  | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Electrical | Wiring | Ashar Khan | MICROPHONE ASSY - MODULE & BEZEL | 6UA07TRMAA |  | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Int/Ext | Doors | Shrey Arodia | ARM - SIDE LT | 6UN93TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Int/Ext | Doors | Shrey Arodia | TRIM PANEL ASSY - RR QTR LWR RT | 6LF66TRMAB | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Int/Ext | Doors | Shrey Arodia | BEZEL - C-PILLAR BELT OPENING RT | 6TL00TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - C-D PILLAR UPR BRIDGE LT | 6RS03TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - D-PILLAR UPR RT | 6LF52TRMAC | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - B-PILLAR RT | 6LF26TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Chassis | Brakes | Anurag Bansal | Random | 68525697AA | 1 | Waiting on Supplier Info |  |  | Magna | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | Delivery Issues | Int/Ext | Fascias | Anurag Bansal | [7 empty] | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Chassis | Knuckles | Zunaid Khan | Fuel Delivery Module | 57008982AA | 2 | Need to confirm PN |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Chassis | Knuckles | Zunaid Khan | Fuel Delivery Module | 57008981AA | 7 | Need to confirm C/L |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Engine Systems | Exhaust | Susan Burhan | Fuel Delivery Module | 57008981AA | 7 | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Electrical | Wiring | Ashar Khan | WIRING ASSY - FRONT END MODULE | 68343527AB |  | Design Revision pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Electrical | Wiring | Ashar Khan | SENSOR MODULE - RAIN | 68384226AA |  | Part Number Confirmation reqd |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM PANEL ASSY - RR QTR LWR LT | 6YS96TRMAB | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Int/Ext | Doors | Shrey Arodia | ARM - SIDE LT | 6UN93TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Int/Ext | Doors | Shrey Arodia | APPLIQUE - RR QTR RT | 6UN16TRMAA | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM PANEL ASSY - RR QTR LWR RT | 6LF66TRMAB | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Int/Ext | Doors | Shrey Arodia | BEZEL - C-PILLAR BELT OPENING LT | 6TL01TRMAA | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Int/Ext | Doors | Shrey Arodia | BEZEL - C-PILLAR BELT OPENING RT | 6TL00TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Int/Ext | Doors | Shrey Arodia | HANDLE - ASSIST RT | 6TE92TRMAA | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - C-D PILLAR UPR BRIDGE LT | 6RS03TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - D-PILLAR UPR LT | 6LF52TRMAC | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - D-PILLAR UPR RT | 6LF52TRMAC | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - B-PILLAR LT | 6LF27TRMAA | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - B-PILLAR RT | 6LF26TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 55 | 2021-07-05 | -4.4286 | 2021-07-19 | -2.4286 | Anurag Bansal | Truck Garage | BOM Issues | Powertrain | Powertrain | Chris Engles | SENSOR - AMBIENT TEMPERATURE | 05149265AB | 45 | Part number to be revised |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2022 XX Proto 1 |  | Active | 35 | 2021-07-19 | 5.4 | 2021-08-02 | 7.4 | Anurag Bansal | North Truck Garage | Design Issues | Int/Ext | Front End Module | Anurag Bansal | FUEL BUNDLE - ENGINE | 68571544AA |  |  | 4509844 |  |  | https://docs.google.com/spreadsheets/d/1wWjW5v7pBU44EANIEk8klfRuDmPw401CzTDKGmo6vGo/

## Build KPI Assessment
Edit Build Info
Build Title | 2026 XX Mule 4
| Current Info | New Info
Work Scope - 32wk (Plan) | 2020-12-07 |  | Work Scope - 32wk
Work Scope - 32wk (Actual) | 2020-12-07
Work Scope - 32wk (Pulse) | Green
Noun Name Delivered - 30wk (Plan) | 2020-12-21 |  | Noun Name Delivered - 30wk
Noun Name Delivered - 30wk (Actual) | 2020-12-21
Noun Name Delivered - 30wk (Pulse) | Green
Build Phase Funding Approved - 19wk (Plan) | 2021-03-08 |  | Build Phase Funding Approved - 19wk
Build Phase Funding Approved - 19wk (Actual) | 2021-03-08
Build Phase Funding Approved - 19wk (Pulse) | Yellow
Vehicle QTY Published - 26wk (Plan) | 2021-01-18 |  | Vehicle QTY Published - 26wk
Vehicle QTY Published - 26wk (Actual) | 2021-01-18
Vehicle QTY Published - 26wk (Pulse) | Red
Carrier Specs Published - 18wk (Plan) | 2021-03-15 |  | Carrier Specs Published - 18wk
Carrier Specs Published - 18wk (Actual) | 2021-03-15
Carrier Specs Published - 18wk (Pulse) | Yellow
Build Plan Complete - 16wk (Plan) | 2021-03-29 |  | Build Plan Complete - 16wk
Build Plan Complete - 16wk (Actual) | 2021-03-29
Build Plan Complete - 16wk (Pulse) | Green
Donor Order Pulse - 14wk (Plan) | 2021-04-12 |  | Donor Order Pulse - 14wk
Donor Order Pulse - 14wk (Actual) | 2021-04-12
Donor Order Pulse - 14wk (Pulse) | Green
Bridge Design Complete - 12wk (Plan) | 2021-04-26 |  | Bridge Design Complete - 12wk
Bridge Design Complete - 12wk (Actual) | 2021-04-26
Bridge Design Complete - 12wk (Pulse) | Green
Overall Build Pulse | Yellow |  | Overall Pulse & Comments
Build Shop Readiness | Green
Part Delivery Pulse | Red
Build Status Comments | test

## Build KPI Data
Build Title | SEQ | Build # | Plan MRD | Plan TCF Start | Plan Build Complete | Plan Delivery | Projected Delivery | Actual TCF Start | Actual Build Complete | Actual Delivery | Delivery Delta (Weeks) | Early Delivery | On-Time Delivery | 1 - 2 Week Late Delivery | More Than 2 Week Late Delivery | Chassis Shortages @ MRD | Electrical Shortages @ MRD | Engine Systems Shortages @ MRD | Exterior Shortages @ MRD | Interior Shortages @ MRD | Powertrain Shortages @ MRD | % Available @ MRD | Chassis Shortages @ Build Start | Electrical Shortages @ Build Start | Engine Systems Shortages @ Build Start | Exterior Shortages @ Build Start | Interior Shortages @ Build Start | Powertrain Shortages @ Build Start | % Available @ Build Start | Plan Build | Plan Validation | Week-of Effect | In Process Build | In Process Validation | Actual Build | Actual Validation | Plan Build + Plan Validation | Build Tracker URL
| 1 | R3MP-54178 | 2021-05-03 | 2021-05-17 | 2021-06-07 | 2021-06-21 |  | 2021-05-06 | 2021-06-11 | 2021-07-01 | 1.4 | 0 | 0 | 1 | 0 | 8 | 3 | 33 | 9 | 3 | 1 | 70% | 2 | 1 | 13 | 1 | 0 | 1 | 90% | 16 | 11 | 5 | #N/A | #N/A | 27 | 15 | 27
| 2 | R3MP-54181 | 2021-05-10 | 2021-05-24 | 2021-06-07 | 2021-06-21 |  | 2021-05-20 | 2021-06-15 | 2021-07-01 | 1.4 | 0 | 0 | 1 | 0 | 7 | 3 | 32 | 7 | 2 | 1 | 74% | 1 | 0 | 7 | 1 | 0 | 1 | 95% | 11 | 11 | 5 | #N/A | #N/A | 19 | 13 | 22
| 3 | R3MP-54183 | 2021-05-10 | 2021-05-24 | 2021-06-07 | 2021-06-21 |  | 2021-05-20 | 2021-06-18 | 2021-07-02 | 1.6 | 0 | 0 | 1 | 0 | 7 | 3 | 32 | 7 | 2 | 1 | 74% | 1 | 0 | 8 | 1 | 0 | 1 | 94% | 11 | 11 | 5 | #N/A | #N/A | 22 | 11 | 22
| 4 | R3MP-54186 | 2021-05-10 | 2021-05-24 | 2021-06-07 | 2021-06-21 |  | 2021-05-20 | 2021-06-15 | 2021-07-01 | 1.4 | 0 | 0 | 1 | 0 | 7 | 3 | 32 | 7 | 2 | 1 | 74% | 1 | 0 | 8 | 1 | 0 | 1 | 94% | 11 | 11 | 5 | #N/A | #N/A | 19 | 13 | 22
| 5 | R3MP-54187 | 2021-05-17 | 2021-05-31 | 2021-06-14 | 2021-06-28 |  | 2021-06-01 | 2021-06-21 | 2021-07-02 | 0.6 | 0 | 1 | 0 | 0 | 3 | 2 | 16 | 1 | 0 | 1 | 88% | 1 | 0 | 4 | 0 | 0 | 1 | 97% | 11 | 11 | 5 | #N/A | #N/A | 15 | 10 | 22
| 6 | R3MP-54199 | 2021-05-17 | 2021-05-31 | 2021-06-14 | 2021-06-28 |  | 2021-06-04 | 2021-06-23 | 2021-07-02 | 0.6 | 0 | 1 | 0 | 0 | 9 | 2 | 21 | 1 | 0 | 1 | 84% | 7 | 0 | 8 | 0 | 0 | 1 | 92% | 11 | 11 | 5 | #N/A | #N/A | 14 | 8 | 22
| 7 | R3MP-54192 | 2021-05-17 | 2021-05-31 | 2021-06-14 | 2021-06-28 |  | 2021-06-03 | 2021-06-22 | 2021-07-02 | 0.6 | 0 | 1 | 0 | 0 | 7 | 2 | 23 | 1 | 0 | 2 | 83% | 5 | 0 | 8 | 0 | 0 | 1 | 93% | 11 | 11 | 5 | #N/A | #N/A | 14 | 9 | 22
| 8 | R3MP-54205 | 2021-05-24 | 2021-06-07 | 2021-06-21 | 2021-07-05 |  | 2021-06-10 |  |  | -6340.3 | 0 | 0 | 0 | 0 | 6 | 0 | 20 | 2 | 0 | 1 | 85% | 4 | 0 | 6 | 0 | 0 | 0 | 95% | 11 | 11 | 5 | 38 | #N/A | #N/A | #N/A | 22
| 9 | R3MP-54198 | 2021-05-24 | 2021-06-07 | 2021-06-21 | 2021-07-05 |  | 2021-06-09 |  |  | -6340.3 | 0 | 0 | 0 | 0 | 9 | 0 | 20 | 2 | 0 | 1 | 85% | 6 | 0 | 6 | 0 | 0 | 1 | 94% | 11 | 11 | 5 | 39 | #N/A | #N/A | #N/A | 22
| 10 | R3MP-54200 | 2021-05-24 | 2021-06-07 | 2021-06-21 | 2021-07-05 |  | 2021-06-10 |  |  | -6340.3 | 0 | 0 | 0 | 0 | 9 | 0 | 20 | 2 | 0 | 1 | 85% | 7 | 0 | 8 | 0 | 0 | 1 | 92% | 11 | 11 | 5 | 38 | #N/A | #N/A | #N/A | 22
| 11 | R3MP-54201 | 2021-05-31 | 2021-06-14 | 2021-06-28 | 2021-07-12 |  | 2021-06-15 |  |  | -6341.3 | 0 | 0 | 0 | 0 | 5 | 0 | 11 | 0 | 0 | 1 | 91% | 4 | 0 | 10 | 0 | 0 | 1 | 92% | 11 | 11 | 5 | 35 | #N/A | #N/A | #N/A | 22
| 12 | R3MP-54202 | 2021-05-31 | 2021-06-14 | 2021-06-28 | 2021-07-12 |  | 2021-06-15 |  |  | -6341.3 | 0 | 0 | 0 | 0 | 8 | 1 | 12 | 0 | 0 | 1 | 89% | 6 | 0 | 11 | 0 | 0 | 1 | 91% | 11 | 11 | 5 | 35 | #N/A | #N/A | #N/A | 22
| 13 | R3MP-54203 | 2021-05-31 | 2021-06-14 | 2021-06-28 | 2021-07-12 |  | 2021-06-15 |  |  | -6341.3 | 0 | 0 | 0 | 0 | 8 | 1 | 12 | 0 | 0 | 2 | 89% | 6 | 0 | 12 | 0 | 0 | 1 | 91% | 11 | 11 | 5 | 35 | #N/A | #N/A | #N/A | 22
| 14 | R3MP-54204 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-07-19 |  | 2021-06-22 |  |  | -6342.3 | 0 | 0 | 0 | 0 | 7 | 1 | 10 | 0 | 0 | 1 | 91% | 0 | 1 | 6 | 0 | 0 | 1 | 96% | 11 | 11 | 5 | 30 | #N/A | #N/A | #N/A | 22
| 15 | R3MP-54182 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-07-19 |  | 2021-06-17 |  |  | -6342.3 | 0 | 0 | 0 | 0 | 4 | 3 | 10 | 0 | 0 | 1 | 91% | 0 | 0 | 6 | 0 | 0 | 1 | 96% | 11 | 11 | 5 | 33 | #N/A | #N/A | #N/A | 22
| 16 | R3MP-54185 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-07-19 |  | 2021-06-21 |  |  | -6342.3 | 0 | 0 | 0 | 0 | 4 | 5 | 10 | 0 | 0 | 1 | 90% | 0 | 3 | 6 | 0 | 0 | 1 | 95% | 11 | 11 | 5 | 31 | #N/A | #N/A | #N/A | 22
| 17 | R3MP-54196 | 2021-06-14 | 2021-06-28 | 2021-07-12 | 2021-07-26 |  | 2021-06-29 |  |  | -6343.3 | 0 | 0 | 0 | 0 | 6 | 5 | 12 | 0 | 0 | 2 | 88% | 0 | 3 | 4 | 0 | 0 | 0 | 96% | 11 | 11 | 5 | 25 | #N/A | #N/A | #N/A | 22
| 18 | R3MP-54197 | 2021-06-14 | 2021-06-28 | 2021-07-12 | 2021-07-26 |  | 2021-06-23 |  |  | -6343.3 | 0 | 0 | 0 | 0 | 4 | 5 | 12 | 0 | 0 | 2 | 89% | 0 | 3 | 4 | 0 | 0 | 0 | 96% | 11 | 11 | 5 | 29 | #N/A | #N/A | #N/A | 22
| 19 | R3MP-54195 | 2021-07-26 | 2021-08-09 | 2021-08-23 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 20 | R3MP-54194 | 2021-07-26 | 2021-08-09 | 2021-08-23 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 1 | R4DT-55621 | 2021-04-12 | 2021-04-26 | 2021-07-26 | 2021-08-09 |  | 2021-04-20 |  |  | -6345.3 | 0 | 0 | 0 | 0 | 42 | 6 | 10 | 3 | 1 | 1 | 70% | 2 | 1 | 1 | 0 | 0 | 0 | 98% | 66 | 11 | 5 | 75 | #N/A | #N/A | #N/A | 77
| 2 | R4DT-55622 | 2021-04-26 | 2021-05-10 | 2021-06-07 | 2021-06-28 |  | 2021-05-07 | 2021-06-18 | 2021-07-02 | 0.6 | 0 | 1 | 0 | 0 | 8 | 1 | 5 | 0 | 1 | 0 | 92% | 5 | 1 | 3 | 0 | 0 | 0 | 95% | 21 | 16 | 5 | #N/A | #N/A | 31 | 11 | 37
| 1 | K3VF-54405 | 2021-05-03 | 2021-05-17 | 2021-06-14 | 2021-08-09 |  | 2021-05-24 |  |  | -6345.3 | 0 | 0 | 0 | 0 | 46 | 49 | 35 | 0 | 3 | 9 | 28% | 13 | 46 | 17 | 80 | 16 | 4 | 42% | 21 | 41 | 5 | 51 | #N/A | #N/A | #N/A | 62
| 2 | K3VF-54404 | 2021-05-10 | 2021-05-24 | 2021-06-21 | 2021-08-16 |  | 2021-06-16 |  |  | -6346.3 | 0 | 0 | 0 | 0 | 31 | 49 | 35 | 0 | 3 | 7 | 36% | 12 | 25 | 13 | 78 | 7 | 4 | 55% | 21 | 41 | 5 | 34 | #N/A | #N/A | #N/A | 62
| 3 | K3VF-54406 | 2021-05-10 | 2021-05-24 | 2021-06-21 | 2021-08-16 |  | 2021-06-25 |  |  | -6346.3 | 0 | 0 | 0 | 0 | 31 | 49 | 35 | 0 | 3 | 7 | 36% | 12 | 25 | 13 | 78 | 7 | 4 | 55% | 21 | 41 | 5 | 27 | #N/A | #N/A | #N/A | 62
| 4 | K3VF-54416 | 2021-05-17 | 2021-05-31 | 2021-06-28 | 2021-08-23 |  | 2021-06-23 |  |  | -6347.3 | 0 | 0 | 0 | 0 | 13 | 46 | 17 | 80 | 16 | 4 | 42% | 12 | 25 | 9 | 72 | 6 | 3 | 59% | 21 | 41 | 5 | 29 | #N/A | #N/A | #N/A | 62
| 5 | K3VF-54418 | 2021-05-17 | 2021-05-31 | 2021-06-28 | 2021-08-23 |  |  |  |  | -6347.3 | 0 | 0 | 0 | 0 | 13 | 46 | 18 | 80 | 16 | 5 | 41% | 12 | 25 | 10 | 72 | 6 | 4 | 58% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 6 | K3VF-54397 | 2021-05-24 | 2021-06-07 | 2021-07-05 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | 15 | 25 | 14 | 78 | 7 | 4 | 53% | 12 | 21 | 5 | 64 | 9 | 4 | 65% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 7 | K3VF-54398 | 2021-05-24 | 2021-06-07 | 2021-07-05 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | 16 | 25 | 14 | 78 | 7 | 6 | 52% | 12 | 21 | 5 | 64 | 9 | 5 | 64% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 8 | K3VF-54394 | 2021-05-31 | 2021-06-14 | 2021-07-12 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | 16 | 25 | 10 | 73 | 6 | 5 | 56% | 8 | 20 | 2 | 55 | 7 | 2 | 71% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 9 | K3VF-54395 | 2021-05-31 | 2021-06-14 | 2021-07-12 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | 16 | 25 | 10 | 73 | 6 | 5 | 56% | 8 | 20 | 2 | 55 | 7 | 1 | 72% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 10 | K3VF-54396 | 2021-06-07 | 2021-06-21 | 2021-07-19 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | 12 | 21 | 5 | 65 | 9 | 4 | 64% | 8 | 20 | 2 | 22 | 7 | 1 | 82% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 11 | K3VF-54402 | 2021-06-07 | 2021-06-21 | 2021-07-19 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | 12 | 21 | 5 | 65 | 9 | 4 | 64% | 8 | 20 | 2 | 25 | 7 | 3 | 80% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 12 | K3VF-54403 | 2021-06-14 | 2021-06-28 | 2021-07-26 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | 12 | 20 | 2 | 57 | 8 | 4 | 69% | 6 | 20 | 4 | 18 | 8 | 3 | 81% | 21 | 36 | 5 | #N/A | #N/A | #N/A | #N/A | 57
| 13 | K3VF-54399 | 2021-06-14 | 2021-06-28 | 2021-07-26 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | 10 | 20 | 2 | 57 | 8 | 3 | 70% | 6 | 20 | 4 | 18 | 8 | 4 | 81% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 14 | K3VF-54400 | 2021-06-21 | 2021-07-05 | 2021-08-02 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | 9 | 20 | 3 | 25 | 7 | 4 | 79% | 5 | 18 | 4 | 9 | 3 | 3 | 87% | 21 | 36 | 5 | #N/A | #N/A | #N/A | #N/A | 57
| 15 | K3VF-54401 | 2021-06-21 | 2021-07-05 | 2021-08-02 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | 9 | 20 | 3 | 25 | 7 | 5 | 79% | 5 | 18 | 4 | 9 | 3 | 5 | 87% | 21 | 36 | 5 | #N/A | #N/A | #N/A | #N/A | 57
| 16 | K3VF-54411 | 2021-06-28 | 2021-07-12 | 2021-08-09 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | 7 | 20 | 4 | 21 | 8 | 7 | 80% | 5 | 16 | 2 | 7 | 3 | 5 | 88% | 21 | 36 | 5 | #N/A | #N/A | #N/A | #N/A | 57
| 17 | K3VF-54412 | 2021-06-28 | 2021-07-12 | 2021-08-09 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | 8 | 20 | 4 | 21 | 8 | 7 | 80% | 6 | 17 | 2 | 7 | 3 | 5 | 88% | 21 | 36 | 5 | #N/A | #N/A | #N/A | #N/A | 57
| 18 | K3VF-54417 | 2021-07-05 | 2021-07-19 | 2021-08-16 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | 7 | 19 | 4 | 10 | 3 | 7 | 85% | [7 empty] | 21 | 31 | 5 | #N/A | #N/A | #N/A | #N/A | 52
| 19 | K3VF-54419 | 2021-07-05 | 2021-07-19 | 2021-08-16 | 2021-10-04 |  |  |  |  | -6353.3 | 0 | 0 | 0 | 0 | 8 | 19 | 5 | 11 | 3 | 7 | 84% | [7 empty] | 21 | 36 | 5 | #N/A | #N/A | #N/A | #N/A | 57
| 20 | K3VF-54410 | 2021-07-12 | 2021-07-26 | 2021-08-23 | 2021-10-04 |  |  |  |  | -6353.3 | 0 | 0 | 0 | 0 | 7 | 17 | 4 | 9 | 3 | 6 | 86% | [7 empty] | 21 | 31 | 5 | #N/A | #N/A | #N/A | #N/A | 52
| 21 | K3VF-54413 | 2021-07-12 | 2021-07-26 | 2021-08-23 | 2021-10-04 |  |  |  |  | -6353.3 | 0 | 0 | 0 | 0 | 7 | 17 | 5 | 11 | 3 | 5 | 86% | [7 empty] | 21 | 31 | 5 | #N/A | #N/A | #N/A | #N/A | 52
| 22 | K3VF-54407 | 2021-07-19 | 2021-08-02 | 2021-08-30 | 2021-10-11 |  |  |  |  | -6354.3 | 0 | 0 | 0 | 0 | [14 empty] | 21 | 31 | 5 | #N/A | #N/A | #N/A | #N/A | 52
| 23 | K3VF-54408 | 2021-07-19 | 2021-08-02 | 2021-08-30 | 2021-10-11 |  |  |  |  | -6354.3 | 0 | 0 | 0 | 0 | [14 empty] | 21 | 31 | 5 | #N/A | #N/A | #N/A | #N/A | 52
| 24 | K3VF-54409 | 2021-07-26 | 2021-08-09 | 2021-09-06 | 2021-10-11 |  |  |  |  | -6354.3 | 0 | 0 | 0 | 0 | [14 empty] | 21 | 26 | 5 | #N/A | #N/A | #N/A | #N/A | 47
| 1 | R4DT-55602 | 2021-03-22 | 2021-04-05 | 2021-04-26 | 2021-05-03 |  | 2021-04-06 | 2021-04-30 | 2021-05-26 | 3.3 | 0 | 0 | 0 | 1 | 3 | 4 | 2 | 8 | 6 | 2 | 73% | 0 | 0 | 1 | 7 | 2 | 0 | 89% | 16 | 6 | 5 | #N/A | #N/A | 19 | 19 | 22
| 2 | R4DT-55492 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-05-17 |  | 2021-04-20 | 2021-05-04 | 2021-05-26 | 1.3 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 8 | 8 | 1 | 79% | 0 | 3 | 1 | 2 | 2 | 1 | 91% | 16 | 6 | 5 | #N/A | #N/A | 11 | 17 | 22
| 3 | R4DT-55490 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-05-17 |  | 2021-04-14 | 2021-05-04 | 2021-05-26 | 1.3 | 0 | 0 | 1 | 0 | 0 | 2 | 3 | 8 | 8 | 1 | 79% | 0 | 3 | 1 | 2 | 2 | 1 | 91% | 16 | 6 | 5 | #N/A | #N/A | 15 | 17 | 22
| 4 | R4DT-55493 | 2021-04-12 | 2021-04-26 | 2021-05-17 | 2021-05-24 |  | 2021-04-28 | 2021-05-26 | 2021-05-26 | 0.3 | 0 | 1 | 0 | 0 | 1 | 1 | 2 | 8 | 4 | 2 | 82% | 0 | 3 | 1 | 0 | 2 | 1 | 93% | 16 | 6 | 5 | #N/A | #N/A | 21 | 1 | 22
| 5 | R4DT-55568 | 2021-04-12 | 2021-04-26 | 2021-05-17 | 2021-07-19 |  | 2021-04-28 | 2021-06-10 |  | -6342.3 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 8 | 4 | 6 | 76% | 5 | 6 | 13 | 0 | 0 | 3 | 88% | 16 | 46 | 5 | #N/A | 38 | 32 | #N/A | 62
| 6 | R4DT-55571 | 2021-04-19 | 2021-05-03 | 2021-05-24 | 2021-07-19 |  | 2021-05-04 | 2021-06-15 |  | -6342.3 | 0 | 0 | 0 | 0 | 11 | 7 | 21 | 7 | 5 | 4 | 77% | 0 | 0 | 2 | 3 | 1 | 0 | 97% | 16 | 41 | 5 | #N/A | 35 | 31 | #N/A | 57
| 7 | R4DT-55570 | 2021-04-19 | 2021-05-03 | 2021-05-24 | 2021-07-26 |  | 2021-05-05 | 2021-06-15 |  | -6343.3 | 0 | 0 | 0 | 0 | 11 | 9 | 25 | 7 | 5 | 6 | 73% | 0 | 0 | 2 | 3 | 1 | 0 | 97% | 16 | 46 | 5 | #N/A | 35 | 30 | #N/A | 62
| 8 | R4DT-55494 | 2021-04-19 | 2021-05-03 | 2021-05-24 | 2021-07-26 |  | 2021-05-06 | 2021-06-15 |  | -6343.3 | 0 | 0 | 0 | 0 | 9 | 10 | 25 | 7 | 5 | 6 | 72% | 0 | 0 | 0 | 2 | 0 | 0 | 99% | 16 | 46 | 5 | #N/A | 35 | 29 | #N/A | 62
| 9 | R4DT-55567 | 2021-04-26 | 2021-05-10 | 2021-05-31 | 2021-08-02 |  | 2021-05-11 | 2021-06-25 |  | -6344.3 | 0 | 0 | 0 | 0 | 7 | 8 | 20 | 5 | 4 | 5 | 80% | 0 | 1 | 1 | 3 | 0 | 0 | 97% | 16 | 46 | 5 | #N/A | 27 | 34 | #N/A | 62
| 10 | R4DT-55562 | 2021-04-26 | 2021-05-10 | 2021-05-31 | 2021-08-02 |  | 2021-05-27 | 2021-07-07 |  | -6344.3 | 0 | 0 | 0 | 0 | 11 | 8 | 20 | 5 | 4 | 5 | 77% | 0 | 1 | 1 | 5 | 0 | 0 | 97% | 16 | 46 | 5 | #N/A | 19 | 30 | #N/A | 62
| 11 | R4DT-55488 | 2021-04-26 | 2021-05-10 | 2021-05-31 | 2021-08-09 |  | 2021-06-16 | 2021-07-07 |  | -6345.3 | 0 | 0 | 0 | 0 | 11 | 7 | 20 | 5 | 4 | 5 | 77% | 0 | 1 | 1 | 5 | 0 | 1 | 96% | 16 | 51 | 5 | #N/A | 19 | 16 | #N/A | 67
| 12 | R4DT-55569 | 2021-05-03 | 2021-05-17 | 2021-06-07 | 2021-08-09 |  | 2021-06-11 |  |  | -6345.3 | 0 | 0 | 0 | 0 | 1 | 4 | 5 | 8 | 1 | 1 | 92% | 0 | 1 | 1 | 5 | 0 | 1 | 96% | 16 | 46 | 5 | 37 | #N/A | #N/A | #N/A | 62
| 13 | R4DT-55563 | 2021-05-03 | 2021-05-17 | 2021-06-07 | 2021-08-16 |  | 2021-06-18 |  |  | -6346.3 | 0 | 0 | 0 | 0 | 1 | 6 | 7 | 8 | 1 | 2 | 90% | 0 | 2 | 1 | 5 | 0 | 1 | 96% | 16 | 51 | 5 | 32 | #N/A | #N/A | #N/A | 67
| 14 | R4DT-55566 | 2021-05-03 | 2021-05-17 | 2021-06-07 | 2021-08-16 |  | 2021-06-25 |  |  | -6346.3 | 0 | 0 | 0 | 0 | 1 | 5 | 7 | 8 | 1 | 3 | 89% | 0 | 2 | 1 | 5 | 0 | 1 | 96% | 16 | 51 | 5 | 27 | #N/A | #N/A | #N/A | 67
| 15 | R4DT-55564 | 2021-05-10 | 2021-05-24 | 2021-06-14 | 2021-08-23 |  | 2021-06-29 |  |  | -6347.3 | 0 | 0 | 0 | 0 | 2 | 5 | 8 | 8 | 1 | 3 | 89% | 0 | 2 | 1 | 5 | 0 | 2 | 96% | 16 | 51 | 5 | 25 | #N/A | #N/A | #N/A | 67
| 16 | R4DT-55565 | 2021-05-10 | 2021-05-24 | 2021-06-14 | 2021-08-23 |  | 2021-07-07 |  |  | -6347.3 | 0 | 0 | 0 | 0 | 2 | 6 | 8 | 8 | 1 | 2 | 89% | 0 | 3 | 1 | 5 | 0 | 2 | 95% | 16 | 51 | 5 | 19 | #N/A | #N/A | #N/A | 67
| 1 | R4DT-55581 | 2021-05-31 | 2021-06-14 | 2021-07-05 | 2021-07-12 |  | 2021-06-10 | 2021-06-21 |  | -6341.3 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 5 | 1 | 3 | 79% | 0 | 4 | 0 | 4 | 1 | 1 | 91% | 16 | 6 | 5 | #N/A | 31 | 8 | #N/A | 22
| 2 | R4DT-55580 | 2021-06-14 | 2021-06-28 | 2021-07-19 | 2021-07-26 |  | 2021-06-15 | 2021-06-24 |  | -6343.3 | 0 | 0 | 0 | 0 | 2 | 7 | 14 | 5 | 1 | 1 | 85% | 0 | 0 | 0 | 0 | 0 | 1 | 98% | 16 | 6 | 5 | #N/A | 28 | 8 | #N/A | 22
| 3 | R4DT-55575 | 2021-06-14 | 2021-06-28 | 2021-07-19 | 2021-07-26 |  | 2021-06-21 | 2021-06-27 |  | -6343.3 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 1 | 3 | 77% | 0 | 2 | 1 | 1 | 1 | 1 | 97% | 16 | 6 | 5 | #N/A | 26 | 5 | #N/A | 22
| 4 | R4DT-55593 | 2021-06-21 | 2021-07-05 | 2021-07-26 | 2021-08-02 |  | 2021-06-24 | 2021-06-30 |  | -6344.3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 95% | 2 | 2 | 3 | 0 | 0 | 2 | 96% | 16 | 6 | 5 | #N/A | 24 | 5 | #N/A | 22
| 5 | R4DT-55586 | 2021-06-21 | 2021-07-05 | 2021-07-26 | 2021-08-02 |  | 2021-06-29 |  |  | -6344.3 | 0 | 0 | 0 | 0 | 1 | 3 | 6 | 1 | 0 | 3 | 94% | 0 | 1 | 0 | 0 | 0 | 0 | 99% | 16 | 6 | 5 | 25 | #N/A | #N/A | #N/A | 22
| 6 | R4DT-55573 | 2021-06-28 | 2021-07-12 | 2021-08-02 | 2021-08-09 |  | 2021-07-02 |  |  | -6345.3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 96% | 0 | 1 | 0 | 0 | 0 | 0 | 99% | 16 | 6 | 5 | 22 | #N/A | #N/A | #N/A | 22
| 7 | R4DT-55598 | 2021-06-28 | 2021-07-12 | 2021-08-02 | 2021-08-09 |  | 2021-07-06 |  |  | -6345.3 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 1 | 0 | 2 | 95% | 0 | 2 | 1 | 0 | 0 | 0 | 98% | 16 | 6 | 5 | 20 | #N/A | #N/A | #N/A | 22
| 8 | R4DT-55596 | 2021-07-05 | 2021-07-19 | 2021-08-09 | 2021-08-16 |  | 2021-07-12 |  |  | -6346.3 | 0 | 0 | 0 | 0 | 4 | 4 | 3 | 1 | 1 | 2 | 93% | 0 | 0 | 0 | 0 | 0 | 1 | 99% | 16 | 6 | 5 | 16 | #N/A | #N/A | #N/A | 22
| 9 | R4DT-55594 | 2021-07-05 | 2021-07-19 | 2021-08-09 | 2021-08-16 |  |  |  |  | -6346.3 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 1 | 96% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 10 | R4DT-55595 | 2021-07-12 | 2021-07-26 | 2021-08-16 | 2021-08-23 |  |  |  |  | -6347.3 | 0 | 0 | 0 | 0 | 2 | 3 | 4 | 0 | 0 | 2 | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 11 | R4DT-55601 | 2021-07-12 | 2021-07-26 | 2021-08-16 | 2021-08-23 |  |  |  |  | -6347.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 12 | R4DT-55579 | 2021-07-12 | 2021-07-26 | 2021-08-16 | 2021-08-23 |  |  |  |  | -6347.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 13 | R4DT-55587 | 2021-07-19 | 2021-08-02 | 2021-08-23 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 14 | R4DT-55584 | 2021-07-19 | 2021-08-02 | 2021-08-23 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 15 | R4DT-55592 | 2021-07-19 | 2021-08-02 | 2021-08-23 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 16 | R4DT-55585 | 2021-07-26 | 2021-08-09 | 2021-08-30 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 17 | R4DT-55574 | 2021-07-26 | 2021-08-09 | 2021-08-30 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 18 | R4DT-55578 | 2021-08-02 | 2021-08-16 | 2021-09-06 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 19 | R4DT-55589 | 2021-08-02 | 2021-08-16 | 2021-09-06 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 20 | R4DT-55572 | 2021-08-02 | 2021-08-16 | 2021-09-06 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 21 | R4DT-55588 | 2021-08-09 | 2021-08-23 | 2021-09-13 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 22 | R4DT-55489 | 2021-08-09 | 2021-08-23 | 2021-09-13 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 23 | R4DT-55577 | 2021-08-16 | 2021-08-30 | 2021-09-20 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 24 | R4DT-55590 | 2021-08-16 | 2021-08-30 | 2021-09-20 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 25 | R4DT-55591 | 2021-08-16 | 2021-08-30 | 2021-09-20 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 26 | R4DT-55583 | 2021-08-16 | 2021-08-30 | 2021-09-20 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 1 | R3MP-54314 | 2021-06-21 | 2021-07-05 | 2021-07-19 | 2021-08-02 |  |  |  |  | -6344.3 | 0 | 0 | 0 | 0 | 7 | 3 | 11 | 1 | 2 | 4 | 87% | 8 | 3 | 9 | 0 | 1 | 3 | 89% | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 2 | R3MP-54369 | 2021-06-21 | 2021-07-05 | 2021-07-19 | 2021-08-02 |  |  |  |  | -6344.3 | 0 | 0 | 0 | 0 | 7 | 3 | 11 | 1 | 2 | 4 | 87% | 8 | 3 | 10 | 0 | 1 | 3 | 89% | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 3 | R3MP-54317 | 2021-06-21 | 2021-07-05 | 2021-07-19 | 2021-08-02 |  |  |  |  | -6344.3 | 0 | 0 | 0 | 0 | 7 | 3 | 11 | 1 | 2 | 4 | 87% | 7 | 3 | 11 | 0 | 1 | 3 | 89% | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 4 | R3MP-54372 | 2021-06-21 | 2021-07-05 | 2021-07-19 | 2021-08-02 |  |  |  |  | -6344.3 | 0 | 0 | 0 | 0 | 7 | 3 | 13 | 1 | 2 | 4 | 86% | 8 | 3 | 15 | 0 | 1 | 3 | 87% | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 5 | R3MP-54320 | 2021-06-28 | 2021-07-12 | 2021-07-26 | 2021-08-09 |  |  |  |  | -6345.3 | 0 | 0 | 0 | 0 | 7 | 3 | 16 | 1 | 1 | 3 | 86% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 6 | R3MP-54321 | 2021-06-28 | 2021-07-12 | 2021-07-26 | 2021-08-09 |  |  |  |  | -6345.3 | 0 | 0 | 0 | 0 | 10 | 3 | 17 | 1 | 1 | 3 | 84% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 7 | R3MP-54322 | 2021-06-28 | 2021-07-12 | 2021-07-26 | 2021-08-09 |  |  |  |  | -6345.3 | 0 | 0 | 0 | 0 | 10 | 5 | 17 | 2 | 1 | 4 | 82% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 8 | R3MP-54318 | 2021-06-28 | 2021-07-12 | 2021-07-26 | 2021-08-09 |  |  |  |  | -6345.3 | 0 | 0 | 0 | 0 | 10 | 5 | 17 | 2 | 1 | 4 | 82% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 9 | R3MP-54323 | 2021-07-05 | 2021-07-19 | 2021-08-02 | 2021-08-16 |  |  |  |  | -6346.3 | 0 | 0 | 0 | 0 | 10 | 5 | 16 | 0 | 1 | 5 | 83% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 10 | R3MP-54324 | 2021-07-05 | 2021-07-19 | 2021-08-02 | 2021-08-16 |  |  |  |  | -6346.3 | 0 | 0 | 0 | 0 | 9 | 5 | 16 | 0 | 1 | 6 | 83% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 11 | R3MP-54325 | 2021-07-05 | 2021-07-19 | 2021-08-02 | 2021-08-16 |  |  |  |  | -6346.3 | 0 | 0 | 0 | 0 | 11 | 5 | 17 | 0 | 1 | 8 | 81% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 12 | R3MP-54375 | 2021-07-12 | 2021-07-26 | 2021-08-09 | 2021-08-23 |  |  |  |  | -6347.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 13 | R3MP-54327 | 2021-07-12 | 2021-07-26 | 2021-08-09 | 2021-08-23 |  |  |  |  | -6347.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 14 | R3MP-54368 | 2021-07-19 | 2021-08-02 | 2021-08-16 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 15 | R3MP-54370 | 2021-07-19 | 2021-08-02 | 2021-08-16 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 16 | R3MP-54371 | 2021-08-02 | 2021-08-16 | 2021-08-30 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 17 | R3MP-54373 | 2021-08-02 | 2021-08-16 | 2021-08-30 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 18 | R3MP-54374 | 2021-08-09 | 2021-08-23 | 2021-09-06 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 19 | R3MP-54326 | 2021-08-09 | 2021-08-23 | 2021-09-06 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 20 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 5 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 6 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 7 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 8 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 9 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 10 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 11 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 12 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 13 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 14 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 15 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 16 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 17 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 18 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 19 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 20 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | K3WS-54828 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | K3WS-54809 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | K3WS-54815 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | K3WS-54823 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 5 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 6 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 7 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 8 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 9 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 10 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 11 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 12 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 13 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 14 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 15 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 16 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 17 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 18 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 19 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 20 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | K3WS-54828 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | K3WS-54809 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | K3WS-54815 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | K3WS-54828 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | K3WS-54809 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | K3WS-54815 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | K3WS-54823 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | K3WS-54828 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | K3WS-54809 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | K3WS-54815 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | K3WS-54823 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | K3WS-54828 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | K3WS-54809 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | K3WS-54815 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | K3WS-54823 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | R4DT-P1288 | 2021-10-11 | 2021-10-25 | 2021-11-08 | 2021-11-22 |  |  |  |  | -6360.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 2 | R4DT-P1289 | 2021-10-25 | 2021-11-08 | 2021-11-22 | 2021-12-06 |  |  |  |  | -6362.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 3 | R4DT-P1251 | 2021-10-25 | 2021-11-08 | 2021-11-22 | 2021-12-06 |  |  |  |  | -6362.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 4 | R4DT-P1183 | 2021-11-01 | 2021-11-15 | 2021-11-29 | 2021-12-13 |  |  |  |  | -6363.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 5 | R4DT-P1341 | 2021-11-01 | 2021-11-15 | 2021-11-29 | 2021-12-13 |  |  |  |  | -6363.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 6 | R4DT-P1152 | 2021-11-01 | 2021-11-15 | 2021-11-29 | 2021-12-13 |  |  |  |  | -6363.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 7 | R4DT-P1319 | 2021-11-08 | 2021-11-22 | 2021-12-06 | 2021-12-20 |  |  |  |  | -6364.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 8 | R4DT-P1347 | 2021-11-08 | 2021-11-22 | 2021-12-06 | 2021-12-20 |  |  |  |  | -6364.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 9 | R4DT-P1346 | 2021-11-08 | 2021-11-22 | 2021-12-06 | 2021-12-20 |  |  |  |  | -6364.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 10 | R4DT-P1344 | 2021-11-08 | 2021-11-22 | 2021-12-06 | 2021-12-20 |  |  |  |  | -6364.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 11 | R4DT-P1345 | 2021-11-15 | 2021-11-29 | 2021-12-13 | 2022-01-03 |  |  |  |  | -6366.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 12 | R4DT-P1329 | 2021-11-15 | 2021-11-29 | 2021-12-13 | 2022-01-03 |  |  |  |  | -6366.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 13 | R4DT-P1253 | 2021-11-15 | 2021-11-29 | 2021-12-13 | 2022-01-03 |  |  |  |  | -6366.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 14 | R4DT-P1255 | 2021-11-15 | 2021-11-29 | 2021-12-13 | 2022-01-03 |  |  |  |  | -6366.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 15 | R4DT-P1332 | 2021-11-15 | 2021-11-29 | 2021-12-13 | 2022-01-03 |  |  |  |  | -6366.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 16 | R4DT-P1176 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-10 |  |  |  |  | -6367.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 17 | R4DT-P1354 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-10 |  |  |  |  | -6367.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 18 | R4DT-P1165 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-10 |  |  |  |  | -6367.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 19 | R4DT-P1257 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-10 |  |  |  |  | -6367.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 20 | R4DT-P1258 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-10 |  |  |  |  | -6367.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 21 | R4DT-P1261 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-10 |  |  |  |  | -6367.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 22 | R4DT-P1177 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-17 |  |  |  |  | -6368.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 23 | R4DT-P1184 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-17 |  |  |  |  | -6368.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 24 | R4DT-P1323 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-17 |  |  |  |  | -6368.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 25 | R4DT-P1166 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-17 |  |  |  |  | -6368.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 26 | R4DT-P1153 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-17 |  |  |  |  | -6368.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 27 | R4DT-P1248 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 32
| 28 | R4DT-P1240 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 32
| 29 | R4DT-P1189 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 32
| 30 | R4DT-P1193 | 2021-12-06 | 2021-12-20 | 2022-01-10 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 31 | R4DT-P1196 | 2021-12-06 | 2021-12-20 | 2022-01-10 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 32 | R4DT-P1217 | 2021-12-06 | 2021-12-20 | 2022-01-10 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 33 | R4DT-P1167 | 2021-12-06 | 2021-12-20 | 2022-01-10 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 34 | R4DT-P1172 | 2021-12-06 | 2021-12-20 | 2022-01-10 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 35 | R4DT-P1178 | 2021-12-20 | 2022-01-03 | 2022-01-17 | 2022-01-31 |  |  |  |  | -6370.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 36 | R4DT-P1160 | 2021-12-20 | 2022-01-03 | 2022-01-17 | 2022-01-31 |  |  |  |  | -6370.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 37 | R4DT-P1181 | 2021-12-20 | 2022-01-03 | 2022-01-17 | 2022-01-31 |  |  |  |  | -6370.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 38 | R4DT-P1199 | 2021-12-20 | 2022-01-03 | 2022-01-17 | 2022-01-31 |  |  |  |  | -6370.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 39 | R4DT-P1210 | 2021-12-20 | 2022-01-03 | 2022-01-17 | 2022-01-31 |  |  |  |  | -6370.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 40 | R4DT-P1185 | 2021-12-20 | 2022-01-03 | 2022-01-17 | 2022-01-31 |  |  |  |  | -6370.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 41 | R4DT-P1161 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 42 | R4DT-P1244 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 43 | R4DT-P1343 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 44 | R4DT-P1194 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 45 | R4DT-P1219 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 46 | R4DT-P1168 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 47 | R4DT-P1173 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 48 | R4DT-P1170 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 49 | R4DT-P1162 | 2022-01-03 | 2022-01-17 | 2022-01-31 | 2022-02-14 |  |  |  |  | -6372.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 50 | R4DT-P1182 | 2022-01-03 | 2022-01-17 | 2022-01-31 | 2022-02-14 |  |  |  |  | -6372.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 51 | R4DT-P1245 | 2022-01-03 | 2022-01-17 | 2022-01-31 | 2022-02-14 |  |  |  |  | -6372.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 52 | R4DT-P1327 | 2022-01-03 | 2022-01-17 | 2022-01-31 | 2022-02-14 |  |  |  |  | -6372.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 53 | R4DT-P1211 | 2022-01-03 | 2022-01-17 | 2022-01-31 | 2022-02-14 |  |  |  |  | -6372.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 54 | R4DT-P1233 | 2022-01-03 | 2022-01-17 | 2022-01-31 | 2022-02-14 |  |  |  |  | -6372.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 55 | R4DT-P1254 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 56 | R4DT-P1256 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 57 | R4DT-P1399 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 58 | R4DT-P1212 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 59 | R4DT-P1190 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 60 | R4DT-P1154 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 61 | R4DT-P1175 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 62 | R4DT-P1171 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 63 | R4DT-P1252 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 64 | R4DT-P1259 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 65 | R4DT-P1260 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 66 | R4DT-P1314 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 67 | R4DT-P1223 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 68 | R4DT-P1204 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 69 | R4DT-P1169 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 70 | R4DT-P1186 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 71 | R4DT-P1312 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 72 | R4DT-P1353 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 73 | R4DT-P1317 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 74 | R4DT-P1195 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 75 | R4DT-P1235 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 76 | R4DT-P1191 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 77 | R4DT-P1174 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 78 | R4DT-P1320 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 79 | R4DT-P1316 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 80 | R4DT-P1328 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 81 | R4DT-P1355 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 82 | R4DT-P1352 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 83 | R4DT-P1224 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 84 | R4DT-P1205 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 85 | R4DT-P1203 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 86 | R4DT-P1231 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 87 | R4DT-P1313 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 88 | R4DT-P1334 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 89 | R4DT-P1350 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 90 | R4DT-P1351 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 91 | R4DT-P1192 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 92 | R4DT-P1322 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 93 | R4DT-P1232 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 94 | R4DT-P1216 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 95 | R4DT-P1324 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 96 | R4DT-P1348 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 97 | R4DT-P1349 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 98 | R4DT-P1206 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 99 | R4DT-P1226 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 100 | R4DT-P1227 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 101 | R4DT-P1187 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 102 | R4DT-P1236 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 103 | R4DT-P1228 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 104 | R4DT-P1218 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 105 | R4DT-P1200 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 106 | R4DT-P1225 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 107 | R4DT-P1237 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 108 | R4DT-P1213 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 109 | R4DT-P1208 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 110 | R4DT-P1336 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 111 | R4DT-P1331 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 112 | R4DT-P1221 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 113 | R4DT-P1229 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 114 | R4DT-P1220 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 115 | R4DT-P1214 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 116 | R4DT-P1198 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 117 | R4DT-P1234 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 118 | R4DT-P1238 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 119 | R4DT-P1287 | 2022-03-07 | 2022-03-21 | 2022-04-04 | 2022-04-18 |  |  |  |  | -6381.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 120 | R4DT-P1230 | 2022-03-07 | 2022-03-21 | 2022-04-04 | 2022-04-18 |  |  |  |  | -6381.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 121 | R4DT-P1209 | 2022-03-07 | 2022-03-21 | 2022-04-04 | 2022-04-18 |  |  |  |  | -6381.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 122 | R4DT-P1222 | 2022-03-07 | 2022-03-21 | 2022-04-04 | 2022-04-18 |  |  |  |  | -6381.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 123 | R4DT-P1400 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 124 | R4DT-P1311 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 125 | R4DT-P1318 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 126 | R4DT-P1188 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 127 | R4DT-P1201 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 128 | R4DT-P1202 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 129 | R4DT-P1215 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 1 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 5 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 6 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 7 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 8 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 9 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 10 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 11 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 12 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 13 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 14 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 15 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 16 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 5 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 6 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 7 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 8 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 9 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 5 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 6 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 7 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 8 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 9 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 10 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 11 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 12 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 13 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 14 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 15 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 16 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 17 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 18 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 19 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 20 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 21 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 22 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 23 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 24 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 25 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 26 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 27 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 28 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 29 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 30 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 31 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | R5DJ-91896 | 2021-07-26 | 2021-08-09 | 2021-08-30 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 2 | R5DJ-91897 | 2021-08-09 | 2021-08-23 | 2021-09-13 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 3 | R5DJ-91898 | 2021-08-09 | 2021-08-23 | 2021-09-13 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 4 | R5DJ-91899 | 2021-08-16 | 2021-08-30 | 2021-09-20 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 5 | R5D2-54363 | 2021-08-16 | 2021-08-30 | 2021-09-20 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 6 | R5DD-54174 | 2021-08-23 | 2021-09-06 | 2021-09-27 | 2021-10-04 |  |  |  |  | -6353.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 7 | R5D2-54364 | 2021-08-23 | 2021-09-06 | 2021-09-27 | 2021-10-04 |  |  |  |  | -6353.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 8 | R5D2-54365 | 2021-08-30 | 2021-09-13 | 2021-10-04 | 2021-10-11 |  |  |  |  | -6354.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 9 | R5DP-64502 | 2021-08-30 | 2021-09-13 | 2021-10-04 | 2021-10-11 |  |  |  |  | -6354.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 10 | R5D2-54366 | 2021-09-06 | 2021-09-20 | 2021-10-11 | 2021-10-18 |  |  |  |  | -6355.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 11 | R5DP-64503 | 2021-09-06 | 2021-09-20 | 2021-10-11 | 2021-10-18 |  |  |  |  | -6355.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 12 | R5D2-54367 | 2021-09-13 | 2021-09-27 | 2021-10-18 | 2021-10-25 |  |  |  |  | -6356.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 1 | K3WS-54828 | 2021-01-25 | 2021-02-08 | 2021-03-01 | 2021-03-22 | 2021-03-22 | 2021-02-11 | 2021-03-01 | 2021-03-26 | 0.6 | 0 | 1 | 0 | 0 | 28 | 9 | 31 | 46 | 96 | 9 | 79% | 14 | 2 | 7 | 21 | 38 | 1 | 92% | 16 | 16 | 5 | #N/A | #N/A | 13 | 20 | 32
| 2 | K3WS-54809 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-03-29 | 2021-02-23 | 2021-03-09 | 2021-04-09 | 1.6 | 0 | 0 | 1 | 0 | 15 | 4 | 7 | 22 | 41 | 1 | 91% | 1 | 4 | 4 | 17 | 20 | 2 | 95% | 11 | 16 | 5 | #N/A | #N/A | 11 | 24 | 27
| 3 | K3WS-54815 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-03-29 | 2021-02-25 | 2021-03-10 | 2021-04-14 | 2.3 | 0 | 0 | 0 | 1 | 13 | 8 | 8 | 28 | 39 | 2 | 90% | 2 | 4 | 2 | 16 | 9 | 1 | 96% | 11 | 16 | 5 | #N/A | #N/A | 10 | 26 | 27
| 4 | K3WS-54823 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-03-29 | 2021-02-26 | 2021-03-11 | 2021-04-16 | 2.6 | 0 | 0 | 0 | 1 | 18 | 2 | 13 | 30 | 44 | 2 | 89% | 2 | 6 | 3 | 16 | 11 | 5 | 95% | 11 | 16 | 5 | #N/A | #N/A | 10 | 27 | 27
| 5 | K3WS-54825 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-03-29 | 2021-03-03 | 2021-03-15 | 2021-04-09 | 1.6 | 0 | 0 | 1 | 0 | 14 | 10 | 10 | 30 | 48 | 4 | 88% | 3 | 7 | 3 | 18 | 12 | 7 | 95% | 11 | 16 | 5 | #N/A | #N/A | 9 | 20 | 27
| 6 | K3WS-54806 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-03-29 | 2021-03-04 | 2021-03-16 | 2021-04-16 | 2.6 | 0 | 0 | 0 | 1 | 19 | 3 | 14 | 34 | 57 | 4 | 87% | 4 | 2 | 6 | 14 | 17 | 3 | 95% | 11 | 16 | 5 | #N/A | #N/A | 9 | 24 | 27
| 7 | K3WS-54820 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-04-05 | 2021-04-05 | 2021-03-05 | 2021-03-29 | 2021-04-20 | 2.1 | 0 | 0 | 0 | 1 | 6 | 7 | 9 | 25 | 22 | 4 | 92% | 2 | 1 | 0 | 3 | 2 | 1 | 99% | 11 | 16 | 5 | #N/A | #N/A | 17 | 17 | 27
| 8 | K3WS-54805 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-04-05 | 2021-04-05 | 2021-03-08 | 2021-03-18 | 2021-04-26 | 3 | 0 | 0 | 0 | 1 | 11 | 2 | 9 | 24 | 27 | 2 | 92% | 2 | 1 | 1 | 0 | 5 | 0 | 99% | 11 | 16 | 5 | #N/A | #N/A | 9 | 28 | 27
| 9 | K3WS-54797 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-04-05 | 2021-04-05 | 2021-03-09 | 2021-03-19 | 2021-04-21 | 2.3 | 0 | 0 | 0 | 1 | 12 | 4 | 9 | 27 | 28 | 2 | 92% | 2 | 1 | 1 | 0 | 8 | 0 | 98% | 11 | 16 | 5 | #N/A | #N/A | 9 | 24 | 27
| 10 | K3WS-54804 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-04-05 | 2021-04-05 | 2021-03-11 | 2021-03-22 | 2021-04-22 | 2.4 | 0 | 0 | 0 | 1 | 13 | 4 | 11 | 27 | 28 | 2 | 91% | 2 | 1 | 0 | 0 | 8 | 0 | 98% | 11 | 16 | 5 | #N/A | #N/A | 8 | 24 | 27
| 11 | K3WS-54803 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-04-05 | 2021-04-12 | 2021-03-12 | 2021-03-23 | 2021-04-21 | 2.3 | 0 | 0 | 0 | 1 | 13 | 4 | 12 | 28 | 29 | 2 | 91% | 2 | 1 | 0 | 0 | 6 | 0 | 99% | 11 | 16 | 5 | #N/A | #N/A | 8 | 22 | 27
| 12 | K3WS-54830 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-04-12 | 2021-04-12 | 2021-03-16 | 2021-03-26 | 2021-04-22 | 1.4 | 0 | 0 | 1 | 0 | 10 | 8 | 10 | 25 | 24 | 3 | 92% | 2 | 1 | 0 | 3 | 6 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 9 | 20 | 27
| 13 | K3WS-54798 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-04-12 | 2021-04-19 | 2021-03-17 | 2021-04-07 | 2021-04-22 | 1.4 | 0 | 0 | 1 | 0 | 10 | 6 | 12 | 22 | 26 | 4 | 92% | 2 | 1 | 0 | 0 | 8 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 16 | 12 | 27
| 14 | K3WS-54799 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-04-12 | 2021-04-19 | 2021-03-17 | 2021-04-09 | 2021-04-28 | 2.3 | 0 | 0 | 0 | 1 | 10 | 6 | 13 | 25 | 27 | 5 | 91% | 2 | 2 | 1 | 0 | 11 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 18 | 14 | 27
| 15 | K3WS-54818 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-04-12 | 2021-04-19 | 2021-03-19 | 2021-04-06 | 2021-04-28 | 2.3 | 0 | 0 | 0 | 1 | 10 | 10 | 13 | 29 | 21 | 3 | 91% | 2 | 1 | 0 | 4 | 8 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 13 | 17 | 27
| 16 | K3WS-54821 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-04-19 | 2021-04-19 | 2021-03-22 | 2021-04-13 | 2021-04-28 | 1.3 | 0 | 0 | 1 | 0 | 2 | 1 | 5 | 5 | 13 | 1 | 97% | 2 | 0 | 0 | 0 | 1 | 0 | 99% | 11 | 16 | 5 | #N/A | #N/A | 17 | 12 | 27
| 17 | K3WS-54813 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-04-19 | 2021-04-19 | 2021-03-23 | 2021-04-14 | 2021-04-29 | 1.4 | 0 | 0 | 1 | 0 | 2 | 1 | 5 | 5 | 9 | 1 | 97% | 2 | 1 | 0 | 0 | 2 | 1 | 99% | 11 | 16 | 5 | #N/A | #N/A | 17 | 12 | 27
| 18 | K3WS-54827 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-04-19 | 2021-05-10 | 2021-03-24 | 2021-04-26 | 2021-05-03 | 2 | 0 | 0 | 1 | 0 | 4 | 2 | 5 | 3 | 15 | 2 | 97% | 3 | 1 | 2 | 0 | 7 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 24 | 6 | 27
| 19 | K3WS-54800 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-04-19 | 2021-04-26 | 2021-03-29 | 2021-04-19 | 2021-04-29 | 1.4 | 0 | 0 | 1 | 0 | 2 | 2 | 2 | 4 | 16 | 2 | 97% | 2 | 1 | 0 | 0 | 6 | 1 | 99% | 11 | 16 | 5 | #N/A | #N/A | 16 | 9 | 27
| 20 | K3WS-54816 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-26 | 2021-04-26 | 2021-03-31 | 2021-04-16 | 2021-04-28 | 0.3 | 0 | 1 | 0 | 0 | 2 | 2 | 5 | 7 | 11 | 2 | 97% | 2 | 1 | 0 | 0 | 2 | 2 | 99% | 11 | 16 | 5 | #N/A | #N/A | 13 | 9 | 27
| 21 | K3WS-54826 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-26 | 2021-04-26 | 2021-04-01 | 2021-04-20 | 2021-04-30 | 0.6 | 0 | 1 | 0 | 0 | 2 | 2 | 7 | 7 | 13 | 3 | 96% | 2 | 1 | 1 | 0 | 4 | 1 | 99% | 11 | 16 | 5 | #N/A | #N/A | 14 | 9 | 27
| 22 | K3WS-54819 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-26 | 2021-05-17 | 2021-04-07 | 2021-04-30 | 2021-05-07 | 1.6 | 0 | 0 | 1 | 0 | 2 | 3 | 7 | 7 | 13 | 2 | 96% | 2 | 2 | 1 | 0 | 3 | 1 | 99% | 11 | 16 | 5 | #N/A | #N/A | 18 | 6 | 27
| 23 | K3WS-54817 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-26 | 2021-05-31 | 2021-04-08 | 2021-04-21 | 2021-05-11 | 2.1 | 0 | 0 | 0 | 1 | 2 | 3 | 8 | 10 | 13 | 3 | 96% | 2 | 2 | 1 | 0 | 6 | 2 | 98% | 11 | 16 | 5 | #N/A | #N/A | 10 | 15 | 27
| 24 | K3WS-54810 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-05-03 | 2021-04-26 | 2021-04-09 | 2021-04-22 | 2021-04-30 | -0.4 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 8 | 1 | 98% | 2 | 2 | 2 | 1 | 8 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 10 | 7 | 27
| 25 | K3WS-54814 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-05-03 | 2021-05-31 | 2021-04-12 | 2021-04-23 | 2021-05-04 | 0.1 | 0 | 1 | 0 | 0 | 2 | 2 | 2 | 1 | 8 | 1 | 98% | 2 | 2 | 2 | 1 | 8 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 10 | 8 | 27
| 26 | K3WS-54808 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-05-03 | 2021-05-31 | 2021-04-14 | 2021-05-04 | 2021-05-11 | 1.1 | 0 | 0 | 1 | 0 | 2 | 2 | 1 | 1 | 11 | 1 | 98% | 2 | 2 | 1 | 1 | 11 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 15 | 6 | 27
| 27 | K3WS-54807 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-05-03 | 2021-06-07 | 2021-04-15 | 2021-04-28 | 2021-05-10 | 1 | 0 | 1 | 0 | 0 | 2 | 2 | 1 | 2 | 12 | 1 | 98% | 2 | 2 | 1 | 2 | 12 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 10 | 9 | 27
| 28 | K3WS-54811 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-06-07 | 2021-04-19 | 2021-04-29 | 2021-05-06 | -0.6 | 1 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 11 | 1 | 97% | 3 | 2 | 3 | 2 | 11 | 1 | 97% | 11 | 16 | 5 | #N/A | #N/A | 9 | 6 | 27
| 29 | K3WS-54812 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-06-07 | 2021-04-20 | 2021-05-04 | 2021-05-07 | -0.4 | 1 | 0 | 0 | 0 | 3 | 3 | 3 | 2 | 12 | 1 | 97% | 3 | 3 | 3 | 2 | 12 | 1 | 97% | 11 | 16 | 5 | #N/A | #N/A | 11 | 4 | 27
| 30 | K3WS-54822 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-06-07 | 2021-04-21 | 2021-05-05 | 2021-05-24 | 2 | 0 | 0 | 1 | 0 | 2 | 2 | 4 | 2 | 16 | 2 | 97% | 2 | 2 | 4 | 2 | 16 | 2 | 97% | 11 | 16 | 5 | #N/A | #N/A | 11 | 14 | 27
| 31 | K3WS-54824 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-06-14 | 2021-04-23 | 2021-05-06 | 2021-05-26 | 2.3 | 0 | 0 | 0 | 1 | 3 | 2 | 3 | 6 | 16 | 2 | 96% | 3 | 2 | 3 | 6 | 16 | 2 | 96% | 11 | 16 | 5 | #N/A | #N/A | 10 | 15 | 27
| 32 | K3WS-54801 | 2021-03-29 | 2021-04-12 | 2021-04-26 | 2021-05-17 | 2021-06-14 | 2021-04-26 | 2021-05-11 | 2021-05-27 | 1.4 | 0 | 0 | 1 | 0 | 2 | 4 | 1 | 3 | 16 | 3 | 97% | 1 | 1 | 0 | 1 | 5 | 0 | 99% | 11 | 16 | 5 | #N/A | #N/A | 12 | 13 | 27
| 33 | K3WS-54802 | 2021-03-29 | 2021-04-12 | 2021-04-26 | 2021-05-17 | 2021-06-14 | 2021-04-27 | 2021-05-12 | 2021-06-03 | 2.4 | 0 | 0 | 0 | 1 | 2 | 4 | 1 | 7 | 17 | 3 | 96% | 1 | 1 | 0 | 3 | 6 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 12 | 17 | 27
| 34 | K3WS-54835 | 2021-03-29 | 2021-04-12 | 2021-04-26 | 2021-05-17 | 2021-06-21 | 2021-04-29 | 2021-05-07 | 2021-05-07 | -1.4 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 6 | 14 | 0 | 95% | 0 | 0 | 0 | 1 | 4 | 0 | 98% | 11 | 16 | 5 | #N/A | #N/A | 7 | 1 | 27
| 35 | K3WS-54836 | 2021-04-05 | 2021-04-19 | 2021-05-03 | 2021-05-24 | 2021-06-21 | 2021-04-30 | 2021-05-12 | 2021-05-12 | -1.7 | 1 | 0 | 0 | 0 | 1 | 3 | 0 | 8 | 10 | 0 | 95% | 0 | 1 | 0 | 2 | 5 | 0 | 98% | 11 | 16 | 5 | #N/A | #N/A | 9 | 1 | 27
| 36 | K3WS-54829 | 2021-04-05 | 2021-04-19 | 2021-05-03 | 2021-05-24 | 2021-06-21 | 2021-05-04 | 2021-05-14 | 2021-05-26 | 0.3 | 0 | 1 | 0 | 0 | 8 | 5 | 4 | 7 | 19 | 3 | 95% | 1 | 1 | 0 | 1 | 7 | 0 | 99% | 11 | 16 | 5 | #N/A | #N/A | 9 | 9 | 27
| 37 | K3WS-55312 | 2021-05-10 | 2021-05-24 | 2021-06-07 | 2021-06-28 | 2021-06-28 | 2021-05-13 | 2021-06-04 | 2021-06-14 | -2 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 4 | 2 | 98% | 0 | 1 | 1 | 2 | 4 | 2 | 99% | 11 | 16 | 5 | #N/A | #N/A | 17 | 7 | 27
| 38 | K3WS-55313 | 2021-05-10 | 2021-05-24 | 2021-06-07 | 2021-06-28 | 2021-06-28 | 2021-05-14 | 2021-06-08 | 2021-06-15 | -1.9 | 1 | 0 | 0 | 0 | 2 | 1 | 3 | 2 | 4 | 3 | 98% | 0 | 1 | 3 | 2 | 4 | 2 | 98% | 11 | 16 | 5 | #N/A | #N/A | 18 | 6 | 27
| 39 | K3WS-55314 | 2021-05-10 | 2021-05-24 | 2021-06-07 | 2021-06-28 | 2021-06-28 | 2021-05-18 | 2021-06-09 | 2021-06-18 | -1.4 | 1 | 0 | 0 | 0 | 2 | 1 | 4 | 6 | 5 | 2 | 98% | 0 | 1 | 4 | 6 | 5 | 2 | 98% | 11 | 16 | 5 | #N/A | #N/A | 17 | 8 | 27
| 1 | 22JL-ML101 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-10 | 2021-03-16 | 2021-03-16 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 80% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 5 | 1 | 7
| 2 | 22JL-ML102 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-18 | 2021-03-23 | 2021-03-26 | 0.6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 4 | 7
| 3 | 22JL-ML103 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-10 | 2021-03-16 | 2021-03-16 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 80% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 5 | 1 | 7
| 4 | 22JL-ML104 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-10 | 2021-03-15 | 2021-03-16 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 80% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 4 | 2 | 7
| 5 | 22JL-ML105 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-10 | 2021-03-16 | 2021-03-24 | -0.7 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 5 | 7 | 7
| 6 | 22JL-ML106 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-10 | 2021-03-17 | 2021-03-17 | -1.7 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 7 | 22JL-ML107 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-10 | 2021-03-17 | 2021-03-18 | -1.6 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 6 | 2 | 7
| 8 | 22JL-ML108 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-11 | 2021-03-16 | 2021-03-19 | -1.4 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 4 | 4 | 7
| 9 | 22JL-ML109 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-18 | 2021-03-23 | 2021-03-24 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 2 | 7
| 10 | 22JL-ML110 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-11 | 2021-03-17 | 2021-03-17 | -1.7 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 5 | 1 | 7
| 11 | 22JL-ML111 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-12 | 2021-03-18 | 2021-03-18 | -1.6 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 5 | 1 | 7
| 12 | 22JL-ML112 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-12 | 2021-03-17 | 2021-03-17 | -1.7 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 4 | 1 | 7
| 13 | 22JL-ML113 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-15 | 2021-03-19 | 2021-03-19 | -2.4 | 1 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 82% | 7 | 0 | 0 | 0 | 0 | 0 | 82% | 6 | 1 | 5 | #N/A | #N/A | 5 | 1 | 7
| 14 | 22JL-ML114 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-16 | 2021-03-19 | 2021-03-24 | -1.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 4 | 4 | 7
| 15 | 22JL-ML115 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-24 | 2021-03-26 | 2021-03-26 | -1.4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 16 | 22JL-ML116 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-24 | 2021-03-30 | 2021-03-31 | -0.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 6 | 1 | 5 | #N/A | #N/A | 5 | 2 | 7
| 17 | 22JL-ML117 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-24 | 2021-03-30 | 2021-03-31 | -0.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 85% | 5 | 0 | 0 | 0 | 0 | 1 | 85% | 6 | 1 | 5 | #N/A | #N/A | 5 | 2 | 7
| 18 | 22JL-ML118 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-16 | 2021-03-23 | 2021-03-29 | -1 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 6 | 5 | 7
| 19 | 22JL-ML119 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-16 | 2021-03-23 | 2021-03-24 | -1.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 6 | 2 | 7
| 20 | 22JL-ML120 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-17 | 2021-03-18 | 2021-03-19 | -2.4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 2 | 2 | 7
| 21 | 22JL-ML121 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-19 | 2021-03-23 | 2021-03-24 | -2.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 3 | 2 | 7
| 22 | 22JL-ML122 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-19 | 2021-03-26 | 2021-03-26 | -2.4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 23 | 22JL-ML123 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-19 | 2021-03-23 | 2021-03-24 | -2.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 3 | 2 | 7
| 24 | 22JL-ML124 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-19 | 2021-03-24 | 2021-03-25 | -2.6 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 4 | 2 | 7
| 25 | 22JL-ML125 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-22 | 2021-03-25 | 2021-03-26 | -2.4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 4 | 2 | 7
| 26 | 22JL-ML126 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-22 | 2021-03-24 | 2021-03-25 | -2.6 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 3 | 2 | 7
| 27 | 22JL-ML127 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-22 | 2021-03-24 | 2021-03-25 | -2.6 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 6 | 1 | 5 | #N/A | #N/A | 3 | 2 | 7
| 28 | 22JL-ML128 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-22 | 2021-03-30 | 2021-03-31 | -1.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 6 | 1 | 5 | #N/A | #N/A | 7 | 2 | 7
| 29 | 22JL-ML130 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-19 |  | 2021-03-23 | 2021-03-31 | 2021-03-31 | -2.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 6 | 1 | 5 | #N/A | #N/A | 7 | 1 | 7
| 30 | 22JL-ML131 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-19 |  | 2021-03-24 | 2021-03-25 | 2021-03-26 | -3.4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 85% | 5 | 0 | 0 | 0 | 0 | 1 | 85% | 6 | 1 | 5 | #N/A | #N/A | 2 | 2 | 7
| 31 | 22JL-ML132 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-19 |  | 2021-03-24 | 2021-03-26 | 2021-03-26 | -3.4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 32 | 22JL-ML153 | 2021-04-12 | 2021-04-26 | 2021-05-03 | 2021-05-10 |  | 2021-04-22 | 2021-05-05 | 2021-05-06 | -0.6 | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 2 | 81% | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 6 | 6 | 5 | #N/A | #N/A | 10 | 2 | 12
| 33 | 22JL-ML151 | 2021-04-12 | 2021-04-26 | 2021-05-03 | 2021-05-10 |  | 2021-04-22 | 2021-05-05 | 2021-05-06 | -0.6 | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 2 | 82% | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 6 | 6 | 5 | #N/A | #N/A | 10 | 2 | 12
| 34 | 22JL-ML152 | 2021-04-12 | 2021-04-26 | 2021-05-03 | 2021-05-10 |  | 2021-04-22 | 2021-05-05 | 2021-05-06 | -0.6 | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 2 | 82% | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 6 | 6 | 5 | #N/A | #N/A | 10 | 2 | 12
| 35 | 22JL-ML154 | 2021-04-12 | 2021-04-26 | 2021-05-03 | 2021-05-10 |  | 2021-04-22 | 2021-05-05 | 2021-05-06 | -0.6 | 1 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 2 | 79% | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 6 | 6 | 5 | #N/A | #N/A | 10 | 2 | 12
| 36 | 22JL-ML138 | 2021-04-19 | 2021-05-03 | 2021-05-10 | 2021-05-17 |  | 2021-04-23 | 2021-05-06 | 2021-05-11 | -0.9 | 1 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 6 | 6 | 5 | #N/A | #N/A | 10 | 4 | 12
| 37 | 22JL-ML136 | 2021-04-19 | 2021-05-03 | 2021-05-10 | 2021-05-17 |  | 2021-04-26 | 2021-05-10 | 2021-05-10 | -1 | 1 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 6 | 6 | 5 | #N/A | #N/A | 11 | 1 | 12
| 38 | 22JL-ML133 | 2021-04-19 | 2021-05-03 | 2021-05-10 | 2021-05-17 |  | 2021-04-26 | 2021-05-06 | 2021-05-07 | -1.4 | 1 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 6 | 6 | 5 | #N/A | #N/A | 9 | 2 | 12
| 39 | 22JL-ML141 | 2021-04-19 | 2021-05-03 | 2021-05-10 | 2021-05-17 |  | 2021-05-12 | 2021-05-24 | 2021-05-28 | 1.6 | 0 | 0 | 1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 9 | 5 | 12
| 40 | 22JL-ML139 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  | 2021-04-26 | 2021-05-11 | 2021-05-12 | -1.7 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 6 | 6 | 5 | #N/A | #N/A | 12 | 2 | 12
| 41 | 22JL-ML142 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  | 2021-05-04 | 2021-05-12 | 2021-05-13 | -1.6 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 2 | 12
| 42 | 22JL-ML160 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  | 2021-05-06 | 2021-05-17 | 2021-05-19 | -0.7 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 8 | 3 | 12
| 43 | 22JL-ML137 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  | 2021-05-04 | 2021-05-17 | 2021-05-25 | 0.1 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 10 | 7 | 12
| 44 | 22JL-ML149 | 2021-05-03 | 2021-05-17 | 2021-05-24 | 2021-05-31 |  | 2021-05-04 | 2021-05-18 | 2021-05-19 | -1.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 11 | 2 | 12
| 45 | 22JL-ML146 | 2021-05-03 | 2021-05-17 | 2021-05-24 | 2021-05-31 |  | 2021-05-04 | 2021-05-17 | 2021-05-19 | -1.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 10 | 3 | 12
| 46 | 22JL-ML157 | 2021-05-03 | 2021-05-17 | 2021-05-24 | 2021-05-31 |  | 2021-05-07 | 2021-05-19 | 2021-05-20 | -1.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 9 | 2 | 12
| 47 | 22JL-ML135 | 2021-05-03 | 2021-05-17 | 2021-05-24 | 2021-05-31 |  | 2021-05-11 | 2021-05-25 | 2021-06-01 | 0.1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 97% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 11 | 6 | 12
| 48 | 22JL-ML140 | 2021-05-10 | 2021-05-24 | 2021-05-31 | 2021-06-07 |  | 2021-05-12 | 2021-05-25 | 2021-06-01 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 10 | 6 | 12
| 49 | 22JL-ML158 | 2021-05-10 | 2021-05-24 | 2021-05-31 | 2021-06-07 |  | 2021-05-12 | 2021-05-25 | 2021-05-28 | -1.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 10 | 4 | 12
| 50 | 22JL-ML159 | 2021-05-10 | 2021-05-24 | 2021-05-31 | 2021-06-07 |  | 2021-05-06 | 2021-05-17 | 2021-05-19 | -2.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 8 | 3 | 12
| 51 | 22JL-ML134 | 2021-05-10 | 2021-05-24 | 2021-05-31 | 2021-06-07 |  | 2021-05-13 | 2021-05-26 | 2021-05-28 | -1.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 10 | 3 | 12
| 52 | 22JL-ML148 | 2021-05-17 | 2021-05-31 | 2021-06-07 | 2021-06-14 |  | 2021-05-14 | 2021-05-20 | 2021-05-20 | -3.6 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 97% | 1 | 0 | 0 | 1 | 0 | 0 | 97% | 6 | 6 | 5 | #N/A | #N/A | 5 | 1 | 12
| 53 | 22JL-ML156 | 2021-05-17 | 2021-05-31 | 2021-06-07 | 2021-06-14 |  | 2021-05-17 | 2021-05-26 | 2021-06-01 | -1.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 8 | 5 | 12
| 54 | 22JL-ML143 | 2021-05-17 | 2021-05-31 | 2021-06-07 | 2021-06-14 |  | 2021-05-18 | 2021-05-28 | 2021-06-01 | -1.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 9 | 3 | 12
| 55 | 22JL-ML155 | 2021-05-17 | 2021-05-31 | 2021-06-07 | 2021-06-14 |  | 2021-05-17 | 2021-05-20 | 2021-06-01 | -1.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 4 | 9 | 12
| 56 | 22JL-ML144 | 2021-05-24 | 2021-06-07 | 2021-06-14 | 2021-06-21 |  | 2021-05-18 | 2021-05-26 | 2021-06-01 | -2.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 5 | 12
| 57 | 22JL-ML145 | 2021-05-24 | 2021-06-07 | 2021-06-14 | 2021-06-21 |  | 2021-05-20 | 2021-05-28 | 2021-06-01 | -2.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 3 | 12
| 58 | 22JL-ML147 | 2021-05-24 | 2021-06-07 | 2021-06-14 | 2021-06-21 |  | 2021-05-20 | 2021-06-11 | 2021-06-15 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 98% | 0 | 0 | 0 | 0 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 17 | 3 | 12
| 59 | 22JL-ML161 | 2021-05-24 | 2021-06-07 | 2021-06-14 | 2021-06-21 |  | 2021-05-25 | 2021-06-09 | 2021-06-15 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 12 | 5 | 12
| 60 | 22JL-ML162 | 2021-05-31 | 2021-06-14 | 2021-06-21 | 2021-06-28 |  | 2021-06-01 | 2021-06-09 | 2021-06-11 | -2.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 3 | 12
| 61 | 22JL-ML163 | 2021-05-31 | 2021-06-14 | 2021-06-21 | 2021-06-28 |  | 2021-06-01 | 2021-06-09 | 2021-06-11 | -2.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 3 | 12
| 62 | 22JL-ML164 | 2021-05-31 | 2021-06-14 | 2021-06-21 | 2021-06-28 |  | 2021-06-01 | 2021-06-09 | 2021-06-11 | -2.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 3 | 12
| 63 | 22JL-ML165 | 2021-05-31 | 2021-06-14 | 2021-06-21 | 2021-06-28 |  | 2021-06-01 | 2021-06-09 | 2021-06-11 | -2.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 3 | 12
| 1 | L2WS-54764 | 2020-10-26 | 2020-11-16 | 2020-11-30 | 2020-12-07 |  | 2020-11-18 | 2020-12-01 | 2020-12-07 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 6 | 5 | #N/A | #N/A | 10 | 5 | 17
| 2 | L2WS-54765 | 2020-10-26 | 2020-11-16 | 2020-11-30 | 2020-12-07 |  | 2020-11-19 | 2020-12-03 | 2020-12-07 | 0 | 0 | 1 | 0 | 0 | 3 |  |  | 0 | 0 |  | 94% | 3 | - |  | 0 | 0 |  | 94% | 11 | 6 | 5 | #N/A | #N/A | 11 | 3 | 17
| 3 | L2WS-54713 | 2020-11-02 | 2020-11-23 | 2020-12-07 | 2020-12-14 |  | 2020-11-20 | 2020-12-09 | 2020-12-10 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 |  | 6 | 2 |  | 96% | 0 | 0 |  | 6 | 2 |  | 96% | 11 | 6 | 5 | #N/A | #N/A | 14 | 2 | 17
| 4 | L2WS-54761 | 2020-11-02 | 2020-11-23 | 2020-12-07 | 2020-12-14 |  | 2020-12-03 | 2020-12-11 | 2020-12-15 | 0.1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 6 | 2 |  | 96% | 0 | 0 |  | 2 | 1 |  | 99% | 11 | 6 | 5 | #N/A | #N/A | 7 | 3 | 17
| 5 | L2WS-54714 | 2020-11-02 | 2020-11-23 | 2020-12-07 | 2020-12-14 |  | 2020-11-30 | 2020-12-11 | 2020-12-14 | 0 | 0 | 1 | 0 | 0 | 0 |  |  | 5 | 1 |  | 93% | 0 |  |  | 2 |  |  | 97% | 11 | 6 | 5 | #N/A | #N/A | 10 | 2 | 17
| 6 | L2WS-54717 | 2020-11-02 | 2020-11-23 | 2020-12-07 | 2020-12-14 |  | 2020-11-23 | 2020-12-07 | 2020-12-11 | -0.4 | 1 | 0 | 0 | 0 |  |  |  | 2 | 0 |  | 97% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 11 | 5 | 17
| 7 | L2WS-54766 | 2020-11-02 | 2020-11-23 | 2020-12-07 | 2020-12-14 |  | 2020-12-01 | 2020-12-09 | 2020-12-11 | -0.4 | 1 | 0 | 0 | 0 |  | 0 |  | 1 | 1 |  | 95% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 7 | 3 | 17
| 8 | L2WS-54767 | 2020-11-02 | 2020-11-23 | 2020-12-07 | 2020-12-14 |  | 2020-12-01 | 2020-12-09 | 2020-12-11 | -0.4 | 1 | 0 | 0 | 0 |  | 0 |  | 1 | 1 |  | 95% |  |  |  |  | 1 |  | 97% | 11 | 6 | 5 | #N/A | #N/A | 7 | 3 | 17
| 9 | L2WS-54737 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-04 | 2021-01-11 | 2021-01-15 | 1.6 | 0 | 0 | 1 | 0 |  | 0 |  | 8 | 0 |  | 91% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 27 | 5 | 27
| 10 | L2WS-54718 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-11 | 2020-12-11 | 2020-12-17 | -2.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 0 |  | 97% |  |  |  | 1 |  |  | 99% | 11 | 16 | 5 | #N/A | #N/A | 1 | 5 | 27
| 11 | L2WS-54719 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-11 | 2020-12-11 | 2020-12-17 | -2.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 4 |  | 91% |  |  |  | 1 | 3 |  | 93% | 11 | 16 | 5 | #N/A | #N/A | 1 | 5 | 27
| 12 | L2WS-54750 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-08 | 2020-12-17 | 2021-01-06 | 0.3 | 0 | 1 | 0 | 0 | 0 | 0 |  | 9 | 3 |  | 94% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 8 | 15 | 27
| 13 | L2WS-54738 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-04 | 2020-12-04 | 2020-12-11 | -3.4 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 6 | 27
| 14 | L2WS-54739 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-03 | 2020-12-04 | 2020-12-11 | -3.4 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 2 | 6 | 27
| 15 | L2WS-54770 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-11-25 | 2020-11-25 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 10 | 27
| 16 | L2WS-54776 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-04 | 2020-12-04 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 3 | 27
| 17 | L2WS-54771 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-03 | 2020-12-03 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 4 | 27
| 18 | L2WS-54772 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-02 | 2020-12-02 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 5 | 27
| 19 | L2WS-54773 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-02 | 2020-12-02 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 5 | 27
| 20 | L2WS-54774 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-02 | 2020-12-02 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 5 | 27
| 21 | L2WS-54775 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-04 | 2020-12-04 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 3 | 27
| 22 | L2WS-54711 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-07 | 2021-01-06 | 2021-01-06 | 0.3 | 0 | 1 | 0 | 0 |  | 3 |  | 6 | 1 |  | 90% |  |  |  |  | 12 |  | 91% | 11 | 16 | 5 | #N/A | #N/A | 23 | 1 | 27
| 23 | L2WS-54745 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-07 | 2021-01-06 | 2021-01-06 | 0.3 | 0 | 1 | 0 | 0 |  | 3 |  | 7 | 1 |  | 89% |  |  |  |  | 15 |  | 92% | 11 | 16 | 5 | #N/A | #N/A | 23 | 1 | 27
| 24 | L2WS-54795 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-11 | 2021-01-06 | 2021-01-06 | 0.3 | 0 | 1 | 0 | 0 |  | 3 |  | 7 | 2 |  | 89% |  |  |  | 1 | 17 |  | 89% | 11 | 16 | 5 | #N/A | #N/A | 19 | 1 | 27
| 25 | L2WS-54796 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-11 | 2021-01-06 | 2021-01-06 | 0.3 | 0 | 1 | 0 | 0 |  | 3 |  | 7 | 1 |  | 90% |  |  |  | 1 | 17 |  | 89% | 11 | 16 | 5 | #N/A | #N/A | 19 | 1 | 27
| 26 | L2WS-54712 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-10 | 2021-01-07 | 2021-01-15 | 0.6 | 0 | 1 | 0 | 0 | 0 | 0 |  | 7 | 2 |  | 95% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 21 | 7 | 27
| 27 | L2WS-54715 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-15 | 2020-12-22 | 2021-01-06 | -0.7 | 1 | 0 | 0 | 0 | 0 |  |  | 6 | 1 |  | 92% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 6 | 12 | 27
| 28 | L2WS-54716 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-16 | 2021-01-06 | 2021-01-12 | 0.1 | 0 | 1 | 0 | 0 | 0 |  |  | 6 | 1 |  | 92% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 16 | 5 | 27
| 29 | L2WS-54720 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-16 | 2020-12-16 | 2021-01-07 | -0.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 4 |  | 91% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 17 | 27
| 30 | L2WS-54721 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-17 | 2020-12-17 | 2021-01-07 | -0.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 4 |  | 91% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 16 | 27
| 31 | L2WS-54722 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-17 | 2020-12-21 | 2021-01-07 | -0.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 4 |  | 91% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 3 | 14 | 27
| 32 | L2WS-54762 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-17 | 2020-12-18 | 2021-01-07 | -0.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 0 |  | 85% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 2 | 15 | 27
| 33 | L2WS-54763 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-17 | 2020-12-18 | 2021-01-07 | -0.6 | 1 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 2 | 15 | 27
| 34 | L2WS-54740 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-04 | 2020-12-04 | 2020-12-11 | -4.4 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 6 | 27
| 35 | L2WS-54741 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-04 | 2020-12-04 | 2020-12-11 | -4.4 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 6 | 27
| 36 | L2WS-54743 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-02 | 2020-12-02 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 5 | 27
| 37 | L2WS-54744 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-03 | 2020-12-03 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 4 | 27
| 38 | L2WS-54706 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-04 | 2020-12-04 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 3 | 27
| 39 | L2WS-54707 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-04 | 2020-12-04 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 3 | 27
| 40 | L2WS-54708 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-11-25 | 2020-11-25 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 10 | 27
| 41 | L2WS-54709 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-11-25 | 2020-11-25 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 10 | 27
| 42 | L2WS-54710 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-02 | 2020-12-02 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 5 | 27
| 43 | L2WS-55019 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-04 | 2020-12-04 | 2020-12-11 | -4.4 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 6 | 27
| 44 | L2WS-55020 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-14 | 2020-12-14 | 2020-12-14 | -4 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 1 | 27
| 45 | L2WS-54723 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2020-12-10 | 2020-12-21 | 2021-01-07 | -1.6 | 1 | 0 | 0 | 0 |  |  |  |  | 4 |  | 95% |  |  |  |  | 4 |  | 95% | 21 | 6 | 5 | #N/A | #N/A | 8 | 14 | 27
| 46 | L2WS-54724 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2020-12-10 | 2020-12-21 | 2021-01-07 | -1.6 | 1 | 0 | 0 | 0 |  |  |  |  | 4 |  | 95% |  |  |  |  | 4 |  | 95% | 21 | 6 | 5 | #N/A | #N/A | 8 | 14 | 27
| 47 | L2WS-54725 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2020-12-10 | 2020-12-22 | 2021-01-07 | -1.6 | 1 | 0 | 0 | 0 |  |  |  |  | 4 |  | 95% |  |  |  |  | 4 |  | 95% | 21 | 6 | 5 | #N/A | #N/A | 9 | 13 | 27
| 48 | L2WS-54726 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2020-12-10 | 2021-01-04 | 2021-01-07 | -1.6 | 1 | 0 | 0 | 0 |  |  |  |  | 4 |  | 95% |  |  |  |  | 4 |  | 95% | 21 | 6 | 5 | #N/A | #N/A | 18 | 4 | 27
| 49 | L2WS-54748 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2021-01-11 | 2021-01-15 | 2021-01-22 | 0.6 | 0 | 1 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 5 | 6 | 27
| 50 | L2WS-54749 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2021-01-12 | 2021-01-15 | 2021-01-22 | 0.6 | 0 | 1 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 4 | 6 | 27
| 51 | L2WS-54768 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2021-01-07 | 2021-01-14 | 2021-01-15 | -0.4 | 1 | 0 | 0 | 0 |  |  |  |  | 1 |  | 97% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 6 | 2 | 27
| 52 | L2WS-54769 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2021-01-07 | 2021-01-08 | 2021-01-12 | -0.9 | 1 | 0 | 0 | 0 |  |  |  |  | 1 |  | 97% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 2 | 3 | 27
| 53 | L2WS-54742 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2020-12-04 | 2020-12-04 | 2020-12-17 | -4.6 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 10 | 27
| 54 | L2WS-54727 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-08 | 2021-01-11 | 2021-01-14 | -1.6 | 1 | 0 | 0 | 0 |  |  |  | 0 | 4 |  | 95% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 2 | 4 | 17
| 55 | L2WS-54728 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-12 | 2021-01-13 | 2021-01-14 | -1.6 | 1 | 0 | 0 | 0 |  |  |  | 0 | 4 |  | 95% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 2 | 2 | 17
| 56 | L2WS-54729 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-13 | 2021-01-14 | 2021-01-14 | -1.6 | 1 | 0 | 0 | 0 |  |  |  | 0 | 4 |  | 95% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 2 | 1 | 17
| 57 | L2WS-54699 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-13 | 2021-02-10 | 2021-02-11 | 2.4 | 0 | 0 | 0 | 1 |  |  |  | 0 | 0 |  | 100% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 21 | 2 | 17
| 58 | L2WS-54700 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-13 | 2021-02-10 | 2021-02-11 | 2.4 | 0 | 0 | 0 | 1 |  |  |  | 0 | 0 |  | 100% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 21 | 2 | 17
| 59 | L2WS-54701 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-13 | 2021-02-10 | 2021-02-11 | 2.4 | 0 | 0 | 0 | 1 |  |  |  | 1 | 0 |  | 97% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 21 | 2 | 17
| 60 | L2WS-54703 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-11 | 2021-02-12 | 2021-02-12 | 2.6 | 0 | 0 | 0 | 1 |  |  |  | 1 | 0 |  | 97% |  |  |  |  | 5 |  | 97% | 11 | 6 | 5 | #N/A | #N/A | 25 | 1 | 17
| 61 | L2WS-54730 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-01-29 | 2021-01-29 | 2021-02-04 | 0.4 | 0 | 1 | 0 | 0 |  |  |  | 2 | 2 |  | 98% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 1 | 5 | 17
| 62 | L2WS-54731 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-01 | 2021-02-02 | 2021-02-04 | 0.4 | 0 | 1 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 3 | 17
| 63 | L2WS-54732 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-03 | 2021-02-04 | 2021-02-08 | 1 | 0 | 1 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 3 | 17
| 64 | L2WS-54733 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-04 | 2021-02-05 | 2021-02-08 | 1 | 0 | 1 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 2 | 17
| 65 | L2WS-54734 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-05 | 2021-02-05 | 2021-02-11 | 1.4 | 0 | 0 | 1 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 1 | 5 | 17
| 66 | L2WS-54752 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-02 | 2021-02-02 | 2021-02-03 | 0.3 | 0 | 1 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 1 | 2 | 17
| 67 | L2WS-54753 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-06 | 2021-02-06 | 2021-02-08 | 1 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 0 | 1 | 17
| 68 | L2WS-54754 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-06 | 2021-02-06 | 2021-02-08 | 1 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 0 | 1 | 17
| 69 | L2WS-54735 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-09 | 2021-02-10 | 2021-02-11 | 0.4 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 2 | 17
| 70 | L2WS-54736 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-10 | 2021-02-11 | 2021-02-11 | 0.4 | 0 | 1 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 1 | 17
| 71 | L2WS-55013 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-01-15 | 2021-01-25 | 2021-01-28 | -1.6 | 1 | 0 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 7 | 4 | 17
| 72 | L2WS-55014 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-01-15 | 2021-01-25 | 2021-01-28 | -1.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 4 |  | 92% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 7 | 4 | 17
| 73 | L2WS-54755 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-09 | 2021-02-12 | 2021-02-12 | 0.6 | 0 | 1 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 4 | 1 | 17
| 74 | L2WS-54756 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-09 | 2021-02-12 | 2021-02-12 | 0.6 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 4 | 1 | 17
| 75 | L2WS-54757 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-10 | 2021-02-12 | 2021-02-12 | 0.6 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 3 | 1 | 17
| 76 | L2WS-54758 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-10 | 2021-02-12 | 2021-02-12 | 0.6 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 3 | 1 | 17
| 77 | L2WS-54759 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-11 | 2021-02-12 | 2021-02-12 | 0.6 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 1 | 17
| 78 | L2WS-54760 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-11 | 2021-02-12 | 2021-02-12 | 0.6 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 1 | 17
| 1 | L2WL-54548 | 2020-12-07 | 2021-01-04 | 2021-01-18 | 2021-01-18 |  | 2021-01-04 | 2021-01-22 | 2021-01-22 | 0.6 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 5 | 14 | 0 | 94% | 0 | 2 | 0 | 5 | 9 | 0 | 96% | 11 | 1 | 5 | #N/A | #N/A | 15 | 1 | 12
| 2 | L2WL-54603 | 2020-12-07 | 2021-01-04 | 2021-01-18 | 2021-01-18 |  | 2021-01-06 | 2021-01-22 | 2021-01-22 | 0.6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 93% | 0 | 0 | 0 | 0 | 2 | 0 | 96% | 11 | 1 | 5 | #N/A | #N/A | 13 | 1 | 12
| 3 | L2WL-54552 | 2020-12-14 | 2021-01-11 | 2021-01-25 | 2021-01-25 |  | 2021-01-11 | 2021-01-28 | 2021-01-28 | 0.4 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 5 | 13 | 0 | 95% | 0 | 1 | 0 | 6 | 10 | 0 | 95% | 11 | 1 | 5 | #N/A | #N/A | 14 | 1 | 12
| 4 | L2WL-54579 | 2020-12-24 | 2021-01-11 | 2021-01-25 | 2021-01-25 |  | 2021-01-11 | 2021-01-29 | 2021-01-29 | 0.6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 0 | 93% | 0 | 0 | 0 | 4 | 4 | 0 | 95% | 11 | 1 | 5 | #N/A | #N/A | 15 | 1 | 12
| 5 | L2WL-54573 | 2021-01-04 | 2021-01-18 | 2021-02-01 | 2021-02-01 |  | 2021-01-18 | 2021-02-01 | 2021-02-01 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 11 | 1 | 12
| 6 | L2WL-54551 | 2021-01-04 | 2021-01-18 | 2021-02-01 | 2021-02-01 |  | 2021-01-18 | 2021-02-08 | 2021-02-08 | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 5 | 11 | 0 | 95% | 0 | 3 | 0 | 6 | 10 | 0 | 95% | 11 | 1 | 5 | #N/A | #N/A | 16 | 1 | 12
| 7 | L2WL-54532 | 2021-01-11 | 2021-01-25 | 2021-02-08 | 2021-02-08 |  | 2021-01-25 | 2021-01-26 | 2021-01-26 | -1.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 97% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 2 | 1 | 12
| 8 | L2WL-54510 | 2021-01-11 | 2021-01-25 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-04 | 2021-02-04 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98% | 0 | 0 | 0 | 4 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 4 | 1 | 12
| 9 | L2WL-54511 | 2021-01-18 | 2021-02-01 | 2021-02-15 | 2021-02-15 |  | 2021-01-26 | 2021-02-05 | 2021-02-05 | -1.4 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 9 | 0 | 94% | 0 | 0 | 0 | 0 | 0 | 0 | 98% | 11 | 1 | 5 | #N/A | #N/A | 9 | 1 | 12
| 10 | L2WL-54601 | 2021-01-18 | 2021-02-01 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-04 | 2021-02-04 | -1.6 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 98% | 0 | 0 | 0 | 2 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 4 | 1 | 12
| 11 | L2WL-54581 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-01-28 | 2021-01-29 | 2021-01-29 | -1.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 12 | L2WL-54586 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-02 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 0 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 5 | 1 | 7
| 13 | L2WL-54514 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 14 | L2WL-54557 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 15 | L2WL-54571 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 16 | L2WL-54555 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 17 | L2WL-54545 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 18 | L2WL-54550 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 19 | L2WL-54602 | 2021-01-25 | 2021-02-08 | 2021-02-22 | 2021-02-22 |  | 2021-02-08 | 2021-02-10 | 2021-02-10 | -1.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 20 | L2WL-54575 | 2021-01-25 | 2021-02-08 | 2021-02-22 | 2021-02-22 |  | 2021-02-08 | 2021-02-10 | 2021-02-10 | -1.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 21 | L2WL-54604 | 2021-01-25 | 2021-02-08 | 2021-02-22 | 2021-02-22 |  | 2021-02-02 | 2021-02-03 | 2021-02-03 | -2.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 2 | 1 | 12
| 22 | L2WL-54587 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-08 | 2021-02-10 | 2021-02-10 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 23 | L2WL-55145 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-08 | 2021-02-10 | 2021-02-10 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 24 | L2WL-54556 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 25 | L2WL-54553 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 26 | L2WL-54566 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 27 | L2WL-54543 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 28 | L2WL-54561 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 29 | L2WL-54576 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 30 | L2WL-54580 | 2021-02-01 | 2021-02-15 | 2021-03-01 | 2021-03-01 |  | 2021-02-08 | 2021-02-15 | 2021-02-15 | -2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 6 | 1 | 12
| 31 | L2WL-54599 | 2021-02-01 | 2021-02-15 | 2021-03-01 | 2021-03-01 |  | 2021-02-09 | 2021-02-18 | 2021-02-18 | -1.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 97% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 8 | 1 | 12
| 32 | L2WL-54590 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-02-18 | 2021-02-18 | 2021-02-18 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 33 | L2WL-54589 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-02-15 | 2021-02-18 | 2021-02-18 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 1 | 7
| 34 | L2WL-54523 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 35 | L2WL-54522 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 36 | L2WL-54546 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 37 | L2WL-54547 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 38 | L2WL-54558 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 39 | L2WL-54544 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 40 | L2WL-54533 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-08 |  | 2021-02-11 | 2021-02-18 | 2021-02-18 | -2.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 6 | 1 | 12
| 41 | L2WL-54535 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-08 |  | 2021-02-11 | 2021-02-18 | 2021-02-18 | -2.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 6 | 1 | 12
| 42 | L2WL-54591 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-02-22 | 2021-02-25 | 2021-02-25 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 1 | 7
| 43 | L2WL-54596 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-02-22 | 2021-02-25 | 2021-02-25 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 97% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 1 | 7
| 44 | L2WL-54528 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-03-22 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 45 | L2WL-54537 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-03-22 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 46 | L2WL-54563 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-03-22 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 47 | L2WL-54564 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-03-22 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 48 | L2WL-54540 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-03-22 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 49 | L2WL-54541 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-03-22 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 50 | L2WL-54505 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-03-15 |  | 2021-02-22 | 2021-02-24 | 2021-02-24 | -2.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 97% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 51 | L2WL-54598 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-03-15 |  | 2021-02-22 | 2021-02-24 | 2021-02-24 | -2.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 99% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 52 | L2WL-54592 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-02-25 | 2021-02-01 | 2021-02-01 | -5 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | -19 | 1 | 7
| 53 | L2WL-54593 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 54 | L2WL-54559 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-02-25 | 2021-03-01 | 2021-03-01 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 55 | L2WL-54515 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-03-02 | 2021-03-03 | 2021-03-03 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 56 | L2WL-54516 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-03-03 | 2021-03-04 | 2021-03-04 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 57 | L2WL-54517 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-03-04 | 2021-03-05 | 2021-03-05 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 58 | L2WL-54518 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-03-04 | 2021-03-05 | 2021-03-05 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 59 | L2WL-54531 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-03-22 |  | 2021-02-23 | 2021-03-01 | 2021-03-01 | -3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 5 | 1 | 12
| 60 | L2WL-54534 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-03-22 |  | 2021-02-23 | 2021-03-02 | 2021-03-02 | -2.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 6 | 1 | 12
| 61 | L2WL-54594 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-02-22 | 2021-02-25 | 2021-02-25 | -2.6 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 1 | 7
| 62 | L2WL-54595 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-03-22 | 2021-03-23 | 2021-03-23 | 1.1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 63 | L2WL-54560 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-03-08 | 2021-03-09 | 2021-03-09 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 64 | L2WL-54570 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-03-09 | 2021-03-10 | 2021-03-10 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 65 | L2WL-54520 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-03-09 | 2021-03-10 | 2021-03-10 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 66 | L2WL-54554 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-03-10 | 2021-03-12 | 2021-03-12 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 67 | L2WL-54562 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-03-10 | 2021-03-12 | 2021-03-12 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 68 | L2WL-54529 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-03-29 |  | 2021-02-25 | 2021-03-01 | 2021-03-01 | -4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 97% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 69 | L2WL-54506 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-03-29 |  | 2021-02-26 | 2021-03-02 | 2021-03-02 | -3.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 70 | L2WL-54588 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 0.1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 71 | L2WL-54582 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 0.1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 72 | L2WL-54539 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-02-25 | 2021-03-01 | 2021-03-01 | -3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 73 | L2WL-54538 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-02-25 | 2021-03-01 | 2021-03-01 | -3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 74 | L2WL-54524 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-12 | 2021-03-15 | 2021-03-15 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 75 | L2WL-54525 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-15 | 2021-03-16 | 2021-03-16 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 76 | L2WL-54584 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-16 | 2021-03-18 | 2021-03-18 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 77 | L2WL-54536 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-05 |  | 2021-03-01 | 2021-03-04 | 2021-03-04 | -4.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 4 | 1 | 12
| 78 | L2WL-54503 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-05 |  | 2021-03-01 | 2021-03-03 | 2021-03-03 | -4.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 79 | L2WL-54597 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 80 | L2WL-54567 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-22 | 2021-03-23 | 2021-03-23 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 81 | L2WL-54549 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-23 | 2021-03-24 | 2021-03-24 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 82 | L2WL-54521 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-24 | 2021-03-25 | 2021-03-25 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 83 | L2WL-54577 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-24 | 2021-03-25 | 2021-03-25 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 84 | L2WL-54600 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-25 | 2021-03-26 | 2021-03-26 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 85 | L2WL-54583 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-25 | 2021-03-26 | 2021-03-26 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 86 | L2WL-54530 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-04-12 |  | 2021-03-03 | 2021-03-05 | 2021-03-05 | -5.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 87 | L2WL-54508 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-04-12 |  | 2021-03-05 | 2021-03-06 | 2021-03-06 | -5.3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 1 | 0 | 12
| 88 | L2WL-54568 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-26 | 2021-03-29 | 2021-03-29 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 89 | L2WL-54569 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-29 | 2021-03-30 | 2021-03-30 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 90 | L2WL-54565 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-04-06 | 2021-04-07 | 2021-04-07 | 0.3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 91 | L2WL-54519 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-04-06 | 2021-04-07 | 2021-04-07 | 0.3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 92 | L2WL-54578 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-04-07 | 2021-04-08 | 2021-04-08 | 0.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 93 | L2WL-54585 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-04-07 | 2021-04-08 | 2021-04-08 | 0.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 94 | L2WL-54504 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-04-19 |  | 2021-03-05 | 2021-03-08 | 2021-03-08 | -6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 2 | 1 | 12
| 95 | L2WL-54513 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-04-19 |  | 2021-03-08 | 2021-03-10 | 2021-03-10 | -5.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 96 | L2WL-54572 | 2021-03-22 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-04-08 | 2021-04-09 | 2021-04-09 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 97 | L2WL-54527 | 2021-03-22 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-04-09 | 2021-04-12 | 2021-04-12 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 98 | L2WL-54526 | 2021-03-22 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-04-12 | 2021-04-12 | 2021-04-12 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 99 | L2WL-54509 | 2021-03-29 | 2021-04-12 | 2021-04-26 | 2021-04-26 |  | 2021-03-09 | 2021-03-12 | 2021-03-12 | -6.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 4 | 1 | 12
| 100 | L2WL-54507 | 2021-03-29 | 2021-04-12 | 2021-04-26 | 2021-04-26 |  | 2021-03-10 | 2021-03-15 | 2021-03-15 | -6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 4 | 1 | 12
| 101 | L2WL-54512 | 2021-04-05 | 2021-04-19 | 2021-05-03 | 2021-05-03 |  | 2021-03-10 | 2021-03-16 | 2021-03-16 | -6.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 5 | 1 | 12
| 102 | L2WL-55253 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-05-10 |  | 2021-03-12 | 2021-03-26 | 2021-03-26 | -6.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 1 | 5 | #N/A | #N/A | 11 | 1 | 17
| 103 | L2WL-54574 | 2021-04-05 | 2021-04-19 | 2021-04-26 | 2021-04-26 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | -4.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 1 | R3DS-54315 | 2020-11-30 | 2020-12-14 | 2021-01-04 | 2021-01-11 |  | 2020-12-18 | 2021-01-14 | 2021-01-26 | 2.1 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 80% | 1 | 2 | 0 | 0 | 0 | 0 | 86% | 16 | 6 | 5 | #N/A | #N/A | 20 | 9 | 22
| 2 | R3DS-54310 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-04 | 2021-01-14 | 2021-01-26 | 0.1 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 82% | 0 | 4 | 0 | 0 | 0 | 0 | 82% | 11 | 6 | 5 | #N/A | #N/A | 9 | 9 | 17
| 3 | R3DS-54312 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-04 | 2021-01-14 | 2021-01-29 | 0.6 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 80% | 0 | 2 | 0 | 0 | 0 | 0 | 97% | 11 | 6 | 5 | #N/A | #N/A | 9 | 12 | 17
| 4 | R3DS-54307 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-01-04 | 2021-01-14 | 2021-01-26 | -0.9 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 80% | 0 | 2 | 0 | 0 | 0 | 0 | 85% | 11 | 6 | 5 | #N/A | #N/A | 9 | 9 | 17
| 5 | R3DS-54311 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-01-06 | 2021-01-18 | 2021-01-29 | -0.4 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 82% | 0 | 4 | 0 | 0 | 0 | 0 | 82% | 11 | 6 | 5 | #N/A | #N/A | 9 | 10 | 17
| 6 | R3DS-54313 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-01-14 | 2021-02-01 | 2021-02-04 | -0.6 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 80% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 11 | 6 | 5 | #N/A | #N/A | 13 | 4 | 17
| 7 | R3DS-54308 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-01-25 | 2021-02-01 | 2021-02-04 | -0.6 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 80% | 0 | 2 | 0 | 0 | 0 | 0 | 85% | 11 | 6 | 5 | #N/A | #N/A | 6 | 4 | 17
| 8 | R3DS-54309 | 2021-01-04 | 2021-01-25 | 2021-02-08 | 2021-02-15 |  | 2021-01-28 | 2021-02-05 | 2021-02-10 | -0.7 | 1 | 0 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 1 | 60% | 0 | 4 | 0 | 0 | 0 | 0 | 82% | 11 | 6 | 5 | #N/A | #N/A | 7 | 4 | 17
| 9 | R3DS-54314 | 2021-01-04 | 2021-01-25 | 2021-02-08 | 2021-02-15 |  | 2021-02-08 | 2021-02-15 | 2021-02-18 | 0.4 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 80% | 0 | 2 | 0 | 0 | 0 | 0 | 86% | 11 | 6 | 5 | #N/A | #N/A | 6 | 4 | 17
| 10 | R3DS-54316 | 2021-01-04 | 2021-01-25 | 2021-02-08 | 2021-02-15 |  | 2021-02-25 | 2021-03-04 | 2021-03-05 | 2.6 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 80% | 3 | 2 | 0 | 0 | 0 | 0 | 73% | 11 | 6 | 5 | #N/A | #N/A | 6 | 2 | 17
| 1 | R3D2-54341 | 2020-11-23 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-03 | 2020-12-10 | 2020-12-14 | -4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 35% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 21 | 6 | 5 | #N/A | #N/A | 6 | 3 | 27
| 2 | R3DJ-91846 | 2020-12-07 | 2020-12-21 | 2021-01-18 | 2021-01-25 |  | 2020-12-15 | 2020-12-22 | 2021-01-28 | 0.4 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 85% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 21 | 6 | 5 | #N/A | #N/A | 6 | 28 | 27
| 3 | R3DJ-91848 | 2020-12-07 | 2020-12-21 | 2021-01-18 | 2021-01-25 |  | 2020-12-23 | 2021-01-28 | 2021-02-11 | 2.4 | 0 | 0 | 0 | 1 | 0 | 9 | 0 | 2 | 0 | 0 | 62% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 21 | 6 | 5 | #N/A | #N/A | 27 | 11 | 27
| 4 | R3DJ-91850 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-01 |  | 2021-01-04 | 2021-02-05 | 2021-02-11 | 1.4 | 0 | 0 | 1 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 81% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 25 | 5 | 22
| 5 | R3D2-54348 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-01 |  | 2021-01-04 | 2021-01-20 | 2021-01-28 | -0.6 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 81% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 13 | 7 | 22
| 6 | R3DJ-91852 | 2020-12-28 | 2021-01-11 | 2021-02-01 | 2021-02-08 |  | 2021-01-07 | 2021-01-20 | 2021-02-02 | -0.9 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 64% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 10 | 10 | 22
| 7 | R3DJ-91847 | 2020-12-28 | 2021-01-11 | 2021-02-01 | 2021-02-08 |  | 2021-01-15 | 2021-01-29 | 2021-02-02 | -0.9 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 92% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 11 | 3 | 22
| 8 | R3DP-64495 | 2020-12-28 | 2021-01-11 | 2021-02-01 | 2021-02-08 |  | 2021-01-15 | 2021-01-20 | 2021-01-27 | -1.7 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 92% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | 4 | 6 | 22
| 9 | R3DJ-91849 | 2021-01-04 | 2021-01-18 | 2021-02-08 | 2021-02-15 |  | 2021-01-22 | 2021-02-03 | 2021-02-05 | -1.4 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 0 | 4 | 0 | 0 | 0 | 0 | 90% | 16 | 6 | 5 | #N/A | #N/A | 9 | 3 | 22
| 10 | R3DJ-91851 | 2021-01-04 | 2021-01-18 | 2021-02-08 | 2021-02-15 |  | 2021-01-22 | 2021-02-22 | 2021-02-24 | 1.3 | 0 | 0 | 1 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 70% | 0 | 4 | 0 | 0 | 0 | 0 | 90% | 16 | 6 | 5 | #N/A | #N/A | 22 | 3 | 22
| 11 | R3DP-64497 | 2021-01-04 | 2021-01-18 | 2021-02-08 | 2021-02-15 |  | 2021-01-28 | 2021-02-10 | 2021-02-16 | 0.1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 62% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 10 | 5 | 22
| 12 | R3DJ-91853 | 2021-01-11 | 2021-01-25 | 2021-02-15 | 2021-02-22 |  | 2021-01-28 | 2021-02-12 | 2021-02-16 | -0.9 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 90% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 12 | 3 | 22
| 13 | R3DJ-91854 | 2021-01-11 | 2021-01-25 | 2021-02-15 | 2021-02-22 |  | 2021-01-29 | 2021-02-10 | 2021-02-11 | -1.6 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 81% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | 9 | 2 | 22
| 14 | R3DJ-91855 | 2021-01-11 | 2021-01-25 | 2021-02-15 | 2021-02-22 |  | 2021-01-29 | 2021-02-09 | 2021-02-11 | -1.6 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 81% | 0 | 4 | 0 | 0 | 0 | 0 | 90% | 16 | 6 | 5 | #N/A | #N/A | 8 | 3 | 22
| 15 | R3DJ-91856 | 2021-01-18 | 2021-02-01 | 2021-02-22 | 2021-03-01 |  | 2021-02-10 | 2021-02-17 | 2021-02-22 | -1 | 1 | 0 | 0 | 0 | 1 | 6 | 0 | 2 | 0 | 0 | 92% | 1 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 6 | 4 | 22
| 16 | R3DJ-91859 | 2021-01-18 | 2021-02-01 | 2021-02-22 | 2021-03-01 |  | 2021-02-12 | 2021-02-17 | 2021-02-22 | -1 | 1 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 90% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 4 | 4 | 22
| 17 | R3DF-56426 | 2021-01-18 | 2021-02-01 | 2021-02-22 | 2021-03-01 |  | 2021-02-12 | 2021-02-17 | 2021-02-26 | -0.4 | 1 | 0 | 0 | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 83% | 1 | 6 | 0 | 2 | 0 | 0 | 92% | 16 | 6 | 5 | #N/A | #N/A | 4 | 8 | 22
| 18 | R3DJ-91860 | 2021-01-25 | 2021-02-08 | 2021-03-01 | 2021-03-08 |  | 2021-02-12 | 2021-02-25 | 2021-03-11 | 0.4 | 0 | 1 | 0 | 0 | 1 | 6 | 0 | 1 | 0 | 0 | 90% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | 10 | 11 | 22
| 19 | R3DJ-91861 | 2021-01-25 | 2021-02-08 | 2021-03-01 | 2021-03-08 |  | 2021-02-17 | 2021-02-19 | 2021-02-19 | -2.4 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 66% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 3 | 1 | 22
| 20 | R3D2-54349 | 2021-01-25 | 2021-02-08 | 2021-03-01 | 2021-03-08 |  | 2021-02-17 | 2021-02-19 | 2021-02-19 | -2.4 | 1 | 0 | 0 | 0 | 1 | 6 | 0 | 2 | 0 | 0 | 81% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 3 | 1 | 22
| 21 | R3D2-54342 | 2021-02-01 | 2021-02-15 | 2021-03-08 | 2021-03-15 |  | 2021-03-12 | 2021-04-01 | 2021-04-07 | 3.3 | 0 | 0 | 0 | 1 | 1 | 6 | 0 | 2 | 0 | 0 | 92% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 15 | 5 | 22
| 22 | R3D2-54343 | 2021-02-01 | 2021-02-15 | 2021-03-08 | 2021-03-15 |  | 2021-03-03 | 2021-03-23 | 2021-03-30 | 2.1 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 90% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 15 | 6 | 22
| 23 | R3D2-54344 | 2021-02-01 | 2021-02-15 | 2021-03-08 | 2021-03-15 |  | 2021-02-19 | 2021-02-25 | 2021-03-08 | -1 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 90% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 5 | 8 | 22
| 24 | R3DP-64496 | 2021-02-08 | 2021-02-22 | 2021-03-15 | 2021-03-22 |  | 2021-02-19 | 2021-02-23 | 2021-03-08 | -2 | 1 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 73% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 3 | 10 | 22
| 25 | R3D2-54345 | 2021-02-08 | 2021-02-22 | 2021-03-15 | 2021-03-22 |  | 2021-02-19 | 2021-03-15 | 2021-03-16 | -0.9 | 1 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 73% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 17 | 2 | 22
| 26 | R3D2-54346 | 2021-02-08 | 2021-02-22 | 2021-03-15 | 2021-03-22 |  | 2021-02-23 | 2021-02-25 | 2021-03-09 | -1.9 | 1 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 73% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 3 | 9 | 22
| 27 | R3D2-54347 | 2021-02-15 | 2021-03-01 | 2021-03-22 | 2021-03-29 |  | 2021-03-16 | 2021-03-26 | 2021-03-29 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 81% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 9 | 2 | 22
| 28 | R3DJ-91857 | 2021-02-15 | 2021-03-01 | 2021-03-22 | 2021-03-29 |  | 2021-02-24 | 2021-04-13 | 2021-04-15 | 2.4 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 81% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 35 | 3 | 22
| 29 | R3DD-54167 | 2021-02-15 | 2021-03-01 | 2021-03-22 | 2021-03-29 |  | 2021-02-23 | 2021-02-25 | 2021-03-11 | -2.6 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 81% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 3 | 11 | 22
| 30 | R3DP-64498 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-04-05 |  | 2021-03-04 | 2021-03-12 | 2021-03-17 | -2.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 7 | 4 | 22
| 31 | R3DJ-91858 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-04-05 |  | 2021-02-26 | 2021-03-10 | 2021-03-17 | -2.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 9 | 6 | 22
| 32 | R3DP-64499 | 2021-03-08 | 2021-03-22 | 2021-04-12 | 2021-04-19 |  | 2021-03-03 | 2021-03-12 | 2021-03-17 | -4.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 8 | 4 | 22
| 33 | R3DP-64500 | 2021-03-08 | 2021-03-22 | 2021-04-12 | 2021-04-19 |  | 2021-04-06 | 2021-04-12 | 2021-04-15 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 5 | 4 | 22
| 1 | 23JL-M2B01 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-03-22 |  | 2021-02-25 | 2021-03-08 | 2021-03-25 | 0.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 93% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 6 | 5 | #N/A | #N/A | 8 | 14 | 17
| 2 | 23JL-M2B02 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-03-29 |  | 2021-02-26 | 2021-03-08 | 2021-03-25 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 6 | 5 | #N/A | #N/A | 7 | 14 | 17
| 3 | 23JL-M2B03 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-03-29 |  | 2021-03-03 | 2021-03-12 | 2021-03-25 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 93% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 6 | 5 | #N/A | #N/A | 8 | 10 | 17
| 1 | R1WL-52116 | 2021-01-11 | 2021-01-25 | 2021-02-08 | 2021-02-22 |  | 2021-01-19 | 2021-02-08 | 2021-02-18 | -0.6 | 1 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 2 | 64% | 1 | 2 | 0 | 0 | 0 | 1 | 86% | 11 | 11 | 5 | #N/A | #N/A | 15 | 9 | 22
| 2 | R1WL-52108 | 2021-01-25 | 2021-02-08 | 2021-02-22 | 2021-03-08 |  | 2021-01-20 | 2021-02-09 | 2021-02-15 | -3 | 1 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 1 | 86% | 1 | 1 | 0 | 0 | 0 | 0 | 94% | 11 | 11 | 5 | #N/A | #N/A | 15 | 5 | 22
| 3 | R1WL-52120 | 2021-02-01 | 2021-02-15 | 2021-03-01 | 2021-03-15 |  | 2021-02-05 | 2021-02-19 | 2021-02-25 | -2.6 | 1 | 0 | 0 | 0 | 2 | 3 | 1 | 0 | 0 | 0 | 83% | 1 | 1 | 1 | 0 | 0 | 0 | 91% | 11 | 11 | 5 | #N/A | #N/A | 11 | 5 | 22
| 4 | R1WL-52119 | 2021-02-01 | 2021-02-15 | 2021-03-01 | 2021-03-15 |  | 2021-02-15 | 2021-03-04 | 2021-03-12 | -0.4 | 1 | 0 | 0 | 0 | 2 | 3 | 1 | 0 | 0 | 0 | 83% | 1 | 1 | 1 | 0 | 0 | 0 | 91% | 11 | 11 | 5 | #N/A | #N/A | 14 | 7 | 22
| 5 | R1WL-52115 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-22 |  | 2021-02-15 | 2021-02-25 | 2021-03-12 | -1.4 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 91% | 1 | 1 | 1 | 0 | 0 | 0 | 91% | 11 | 11 | 5 | #N/A | #N/A | 9 | 12 | 22
| 6 | R1WL-52114 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-22 |  | 2021-02-15 | 2021-02-05 | 2021-03-04 | -2.6 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 91% | 1 | 1 | 1 | 0 | 0 | 0 | 91% | 11 | 11 | 5 | #N/A | #N/A | -7 | 20 | 22
| 1 | L2WL-55139 | 2020-12-07 | 2021-01-04 | 2021-01-11 | 2021-01-11 |  | 2021-01-06 | 2021-01-11 | 2021-01-11 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 1 | 7
| 2 | L2WL-55133 | 2020-12-14 | 2021-01-11 | 2021-01-18 | 2021-01-18 |  | 2021-01-26 | 2021-02-17 | 2021-02-17 | 4.3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 44 | 29 | 0 | 71% | 0 | 1 | 0 | 6 | 5 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 17 | 1 | 7
| 3 | L2WL-55134 | 2020-12-14 | 2021-01-11 | 2021-01-18 | 2021-01-18 |  | 2021-02-09 | 2021-02-18 | 2021-02-18 | 4.4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 43 | 28 | 0 | 71% | 0 | 2 | 0 | 8 | 5 | 0 | 93% | 6 | 1 | 5 | #N/A | #N/A | 8 | 1 | 7
| 4 | L2WL-55143 | 2021-01-04 | 2021-01-18 | 2021-02-08 | 2021-02-08 |  | 2021-01-26 | 2021-02-26 | 2021-02-26 | 2.6 | 0 | 0 | 0 | 1 | 42 | 10 | 2 | 16 | 16 | 1 | 83% | 18 | 10 | 1 | 5 | 3 | 2 | 92% | 16 | 1 | 5 | #N/A | #N/A | 24 | 1 | 17
| 5 | L2WL-55144 | 2021-01-04 | 2021-01-18 | 2021-02-08 | 2021-02-08 |  | 2021-02-17 | 2021-03-05 | 2021-03-05 | 3.6 | 0 | 0 | 0 | 1 | 0 | 23 | 0 | 27 | 68 | 0 | 69% | 0 | 19 | 0 | 8 | 7 | 0 | 91% | 16 | 1 | 5 | #N/A | #N/A | 13 | 1 | 17
| 6 | L2WL-55136 | 2021-01-11 | 2021-01-25 | 2021-02-01 | 2021-02-01 |  | 2021-01-13 | 2021-02-05 | 2021-02-05 | 0.6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 18 | 1 | 7
| 7 | L2WL-55137 | 2021-01-11 | 2021-01-25 | 2021-02-01 | 2021-02-01 |  | 2021-01-13 | 2021-02-05 | 2021-02-05 | 0.6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 18 | 1 | 7
| 8 | L2WL-55138 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-01-20 | 2021-02-05 | 2021-02-05 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 13 | 1 | 7
| 9 | L2WL-55141 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-01-20 | 2021-02-05 | 2021-02-05 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 13 | 1 | 7
| 10 | L2WL-55142 | 2021-01-25 | 2021-02-08 | 2021-02-22 | 2021-02-22 |  | 2021-02-10 | 2021-02-19 | 2021-02-19 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 97% | 0 | 0 | 0 | 1 | 0 | 0 | 99% | 11 | 1 | 5 | #N/A | #N/A | 8 | 1 | 12
| 11 | L2WL-55135 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-03-11 | 2021-03-19 | 2021-03-19 | 4.6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 97% | 0 | 0 | 0 | 1 | 0 | 0 | 99% | 6 | 1 | 5 | #N/A | #N/A | 7 | 1 | 7
| 12 | L2WL-55140 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | -1.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 1 | K3WS-54783 | 2020-11-16 | 2020-11-30 | 2020-12-21 | 2021-01-25 |  | 2020-12-03 | 2021-01-25 | 2021-03-09 | 6.1 | 0 | 0 | 0 | 1 | 46 | 10 | 41 | 46 | 141 | 10 | 71% | 7 | 7 | 15 | 14 | 56 | 3 | 89% | 16 | 26 | 5 | #N/A | #N/A | 38 | 32 | 42
| 2 | K3WS-54791 | 2020-11-30 | 2020-12-14 | 2021-01-18 | 2021-02-08 |  | 2020-12-16 | 2021-01-27 | 2021-03-24 | 6.3 | 0 | 0 | 0 | 1 | 11 | 7 | 15 | 15 | 63 | 5 | 88% | 2 | 0 | 1 | 3 | 11 | 0 | 98% | 26 | 16 | 5 | #N/A | #N/A | 31 | 41 | 42
| 3 | K3WS-54784 | 2020-11-30 | 2020-12-14 | 2021-01-18 | 2021-02-08 |  | 2020-12-18 | 2021-01-28 | 2021-03-12 | 4.6 | 0 | 0 | 0 | 1 | 12 | 8 | 16 | 17 | 63 | 6 | 88% | 3 | 0 | 1 | 4 | 19 | 1 | 97% | 26 | 16 | 5 | #N/A | #N/A | 30 | 32 | 42
| 4 | K3WS-54792 | 2020-11-30 | 2020-12-14 | 2021-01-18 | 2021-02-08 |  | 2021-01-11 | 2021-02-01 | 2021-03-16 | 5.1 | 0 | 0 | 0 | 1 | 12 | 7 | 17 | 17 | 68 | 6 | 87% | 4 | 0 | 1 | 3 | 23 | 0 | 97% | 26 | 16 | 5 | #N/A | #N/A | 16 | 32 | 42
| 5 | K3WS-54790 | 2020-11-30 | 2020-12-14 | 2021-01-18 | 2021-02-08 |  | 2021-01-13 | 2021-02-04 | 2021-03-31 | 7.3 | 0 | 0 | 0 | 1 | 12 | 9 | 21 | 19 | 68 | 6 | 86% | 3 | 1 | 1 | 3 | 20 | 0 | 97% | 26 | 16 | 5 | #N/A | #N/A | 17 | 40 | 42
| 6 | K3WS-54788 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-15 |  | 2021-01-15 | 2021-02-05 | 2021-04-06 | 7.1 | 0 | 0 | 0 | 1 | 10 | 4 | 3 | 4 | 28 | 3 | 94% | 3 | 1 | 1 | 7 | 22 | 0 | 96% | 16 | 16 | 5 | #N/A | #N/A | 16 | 43 | 32
| 7 | K3WS-54789 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-15 |  | 2021-01-21 | 2021-02-09 | 2021-04-06 | 7.1 | 0 | 0 | 0 | 1 | 10 | 4 | 3 | 4 | 28 | 3 | 94% | 1 | 2 | 1 | 3 | 7 | 0 | 98% | 16 | 16 | 5 | #N/A | #N/A | 14 | 41 | 32
| 8 | K3WS-54793 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-15 |  | 2021-01-25 | 2021-02-09 | 2021-02-12 | -0.4 | 1 | 0 | 0 | 0 | 1 | 1 | - | 3 | 22 | - | 93% | 0 | 2 | 0 | 2 | 7 | - | 97% | 16 | 16 | 5 | #N/A | #N/A | 12 | 4 | 32
| 9 | K3WS-54787 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-15 |  | 2021-01-27 | 2021-02-10 | 2021-03-30 | 6.1 | 0 | 0 | 0 | 1 | 10 | 6 | 3 | 9 | 31 | 3 | 94% | 0 | 0 | 2 | 4 | 6 | 0 | 98% | 16 | 16 | 5 | #N/A | #N/A | 11 | 35 | 32
| 10 | K3WS-54786 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-15 |  | 2021-01-29 | 2021-02-11 | 2021-03-12 | 3.6 | 0 | 0 | 0 | 1 | 10 | 6 | 3 | 14 | 38 | 4 | 92% | 0 | 0 | 3 | 5 | 7 | 0 | 98% | 16 | 16 | 5 | #N/A | #N/A | 10 | 22 | 32
| 11 | K3WS-54785 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-15 |  | 2021-02-03 | 2021-02-19 | 2021-03-19 | 4.6 | 0 | 0 | 0 | 1 | 10 | 6 | 4 | 16 | 51 | 6 | 91% | 0 | 2 | 6 | 7 | 8 | 1 | 97% | 16 | 16 | 5 | #N/A | #N/A | 13 | 21 | 32

## Email Distribution
This distribution list will be added to all Announcement and Change emails. The emails will be saved to your draft folder. You can add additional (program specific) recipients and attachments to the email before pressing send. You can add to the bottom of this list.
Role | Email
PBE Manager | anthony.schoenherr@stellantis.com
Build Lead Manager | jim.sovis@stellantis.com
Body Supervisor | michael.moulton@stellantis.com
Int/Ext Supervisor | musharraf.nazir@stellantis.com
Chassis Supervisor | shafqat.bhatti@stellantis.com
Electrical Supervisor | john.petrous@stellantis.com
Engine Systems Supervisor | herb.white@stellantis.com
Powertrain Supervisor | david.ashley@stellantis.com
BOM Lead | shelly.frye@external.stellantis.com
Bridge Design Manager | steve.costello@stellantis.com
Global Prototype Specialist | dustin.urbach@stellantis.com