## Copy of PBE Build List (hidden)
Build Title | Model Year | Vehicle Family | Build Type | Build Phase | Build Status | Quantity | TCF MRD | Weeks to MRD | TCF Build Start | Weeks to Build Start | Build Lead | Build Location | Build Strategy | WBS Code | Tree FC# | Build Total # of Parts | Build % REQ | Build % PO | Build % Received | Build Cost | Build Tracker URL | Date Created | Last Modified
2024 DT Mule 3 BEV-REEV | 2024 | DT | Mule | 3 BEV-REEV | Active | 35 | 2021-07-12 | -6.1429 | 2021-07-26 | -4.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2021-01-23 19:17 | 2021-01-23 19:17
2024 WS Proto Mule [Proto] 1 | 2024 | WS | Proto | Mule [Proto] 1 | On Hold | 3 | 2021-04-12 | -19.1429 | 2021-04-26 | -17.1429 | Sheen Ryan (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2021-01-11 11:06 | 2021-01-11 11:06
2023 MP Mule 1 | 2023 | MP | Mule | 1 | Active | 6 | 2021-01-11 | -32.1429 | 2021-01-25 | -30.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2021-01-10 09:34 | 2021-01-10 09:34
2023 VF Mule BEV 2 | 2023 | VF | Mule | BEV 2 | Active | 24 | 2021-04-25 | -17.2857 | 2021-05-09 | -15.2857 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2021-01-04 08:58 | 2021-01-04 08:58
2024 DT Mule 2 BEV | 2024 | DT | Mule | 2 BEV | Active | 9 | 2021-06-14 | -10.1429 | 2021-06-28 | -8.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-12-21 15:16 | 2020-12-21 15:16
2022 JL Mule 1 | 2022 | JL | Mule | 1 | Active | 73 | 2021-02-22 | -26.1429 | 2021-03-08 | -24.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-12-16 12:16 | 2020-12-16 12:16
2024 DT Mule 1 REEV | 2024 | DT | Mule | 1 REEV | Active | 2 | 2021-04-12 | -19.1429 | 2021-04-26 | -17.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-12-03 11:44 | 2020-12-21 15:18
2023 WS Proto 5B | 2023 | WS | Proto | 5B | Active | 36 | 2021-01-25 | -30.1429 | 2021-02-08 | -28.1429 | Sheen Ryan (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-11-06 15:58 | 2020-11-06 16:00
2024 DT Mule 3 GMET6 | 2024 | DT | Mule | 3 GMET6 | Active | 29 | 2021-05-31 | -12.1429 | 2021-06-14 | -10.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-10-27 21:52 | 2020-10-27 21:52
2024 DT Mule 2 GMET6 | 2024 | DT | Mule | 2 GMET6 | Active | 35 | 2021-03-22 | -22.1429 | 2021-04-05 | -20.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-10-27 21:50 | 2020-10-27 21:50
2022 WS Bucks VPA | 2022 | WS | Bucks | VPA | Active | 79 | 2020-10-26 | -43.1429 | 2020-11-02 | -42.1429 | Sheen Ryan (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-10-16 14:31 | 2020-10-16 14:31
2022 WS Proto 3B | 2022 | WS | Proto | 3B | Active | 5 | 2020-08-31 | -51.1429 | 2020-09-14 | -49.1429 | Sheen Ryan (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-09-18 12:31 | 2020-09-18 12:31
2023 HD Mule 1 MCA | 2023 | HD | Mule | 1 MCA | Active | 32 | 2020-11-23 | -39.1429 | 2020-12-07 | -37.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-09-15 11:26 | 2020-09-15 11:26
2023 JT Mule 3A | 2023 | JT | Mule | 3A | Active | 3 | 2021-01-04 | -33.1429 | 2021-01-18 | -31.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-08-20 14:08 | 2020-08-20 14:08
2025 HD Mule 1 Diesel | 2025 | HD | Mule | 1 Diesel | Active | 9 | 2021-02-15 | -27.1429 | 2021-03-01 | -25.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-08-11 17:50 | 2020-08-11 17:50
2023 JL Mule 4B | 2023 | JL | Mule | 4B | Active | 7 | 2020-08-17 | -53.1429 | 2020-08-31 | -51.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-08-04 14:46 | 2020-08-04 14:46
2023 DS Mule 1 AEB | 2023 | DS | Mule | 1 AEB | Active | 10 | 2020-11-30 | -38.1429 | 2020-12-14 | -36.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-07-31 16:08 | 2020-07-31 16:08
2023 WS Proto 5A | 2023 | WS | Proto | 5A | Active | 11 | 2020-11-16 | -40.1429 | 2020-11-30 | -38.1429 | Sheen Ryan (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-07-16 17:17 | 2021-01-13 10:47
2024 DT Mule 1 Dyn Susp | 2024 | DT | Mule | 1 Dyn Susp | Active | 2 | 2020-11-30 | -38.1429 | 2020-12-14 | -36.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-07-11 11:40 | 2020-07-11 11:40
2022 WL Bucks VP-E | 2022 | WL | Bucks | VP-E | Active | 19 | 2020-10-19 | -44.1429 | 2020-11-02 | -42.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-07-01 15:47 | 2020-07-01 15:47
2022 VF Mule 1 | 2022 | VF | Mule | 1 | Active |  |  | No Date |  | No Date | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-06-24 15:37 | 2020-06-24 15:37
2023 DS Mule 1 AEB | 2023 | DS | Mule | 1 AEB | Active | 10 | 2020-11-30 | -38.1429 | 2020-12-14 | -36.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-06-22 12:26 | 2020-06-22 12:26
2022 LA Mule 2 | 2022 | LA | Mule | 2 | Active | 20 | 2020-07-13 | -58.1429 | 2020-07-27 | -56.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-06-19 07:26 | 2020-06-19 07:26
2023 WS Proto 4C | 2023 | WS | Proto | 4C | Active | 33 | 2020-08-31 | -51.1429 | 2020-09-14 | -49.1429 | Sheen Ryan (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-06-03 09:30 | 2020-09-10 14:41
2022 LA Mule 2 | 2022 | LA | Mule | 2 | Active | 20 | 2020-07-13 | -58.1429 | 2020-07-27 | -56.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-05-27 10:20 | 2020-05-27 10:20
2023 JL Mule 3A | 2023 | JL | Mule | 3A | Active | 3 | 2020-11-30 | -38.1429 | 2020-12-14 | -36.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-05-18 09:48 | 2020-05-18 09:48
2023 JL Mule 2A | 2023 | JL | Mule | 2A | Active | 16 | 2020-10-12 | -45.1429 | 2020-10-26 | -43.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-04-30 08:41 | 2020-04-30 08:41
2023 JL Mule 1A | 2023 | JL | Mule | 1A | Active | 3 | 2020-08-17 | -53.1429 | 2020-08-31 | -51.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-04-22 15:14 | 2020-04-22 15:14
2023 WS Proto 4B | 2023 | WS | Proto | 4B | Active | 7 | 2020-06-08 | -63.1429 | 2020-06-22 | -61.1429 | Sheen Ryan (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-04-03 16:06 | 2020-09-10 14:41
2023 DJ Mule 1 MCA | 2023 | DJ | Mule | 1 MCA | Active | 27 | 2020-10-05 | -46.1429 | 2020-10-19 | -44.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-04-02 16:23 | 2020-04-02 16:23
2023 WS Proto 5 Error | 2023 | WS | Proto | 5 Error | Active | 44 | 2020-11-02 | -42.1429 | 2020-11-16 | -40.1429 | Sheen Ryan (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-03-20 09:05 | 2021-01-13 12:45
2022 DT Mule 3 Fuel | 2022 | DT | Mule | 3 Fuel | Active | 20 | 2020-06-01 | -64.1429 | 2020-06-15 | -62.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-03-12 11:19 | 2020-03-12 11:19
2022 WL Bucks VP-C | 2022 | WL | Bucks | VP-C | Active | 50 | 2020-03-09 | -76.1429 | 2020-03-23 | -74.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-03-09 11:42 | 2020-03-09 11:42
2022 VF Mule 1 | 2022 | VF | Mule | 1 | Active | 42 | 2020-04-27 | -69.1429 | 2020-05-11 | -67.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-03-05 10:06 | 2020-03-05 10:06
2022 WS Proto 3A | 2022 | WS | Proto | 3A | Active | 8 | 2020-03-02 | -77.1429 | 2020-03-16 | -75.1429 | Sheen Ryan (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-03-02 08:05 | 2020-09-18 12:26
2022 RU Mule 3 PHEV | 2022 | RU | Mule | 3 PHEV | Active |  |  | No Date |  | No Date | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-02-13 15:01 | 2020-02-13 15:01
2023 RU Mule 2 EVA | 2023 | RU | Mule | 2 EVA | Active | 20 | 2020-06-29 | -60.1429 | 2020-07-13 | -58.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-02-13 14:40 | 2020-02-13 14:40
2022 RU Mule 3 PHEV | 2022 | RU | Mule | 3 PHEV | Active | 3 | 2020-06-22 | -61.1429 | 2020-07-06 | -59.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-02-13 14:29 | 2020-02-13 14:29
2021 WD VP Buck | 2021 | WD | VP | Buck | Active | 2 | 2020-02-24 | -78.1429 | 2020-03-09 | -76.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-01-30 12:05 | 2020-01-30 12:05
2021 DT VP TRX Bucks | 2021 | DT | VP | TRX Bucks | Active | 10 | 2020-01-13 | -84.1429 | 2020-01-27 | -82.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-01-29 10:51 | 2020-01-29 10:51
2022 WL Bucks VP-D | 2022 | WL | Bucks | VP-D | Active |  |  | No Date |  | No Date | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-01-27 11:45 | 2020-01-27 11:45
2022 ZE Proto 3 | 2022 | ZE | Proto | 3 | Active |  |  | No Date |  | No Date | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-01-15 12:50 | 2020-01-15 12:50
2020 ZE Proto mule | 2020 | ZE | Proto | mule | Active |  |  | No Date |  | No Date | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-01-06 15:05 | 2020-01-15 12:50
2022 DT Mule 2 GT | 2022 | DT | Mule | 2 GT | Active | 9 | 2020-04-06 | -72.1429 | 2020-04-20 | -70.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-01-06 14:36 | 2020-03-13 07:55
2020 4C Mule mule | 2020 | 4C | Mule | mule | Active |  |  | No Date |  | No Date | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2020-01-06 14:15 | 2020-01-15 12:50
2021 JL Mule 4 J9 | 2021 | JL | Mule | 4 J9 | Active | 6 | 2020-01-02 | -85.7143 | 2020-01-12 | -84.2857 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-12-16 07:21 | 2020-01-15 12:50
2021 JT Mule 1 | 2021 | JT | Mule | 1 | Active |  |  | No Date |  | No Date | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-12-05 07:50 | 2020-01-15 12:50
2023 WS Proto 4A | 2023 | WS | Proto | 4A | Active | 5 | 2020-05-04 | -68.1429 | 2020-05-18 | -66.1429 | Sheen Ryan (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-12-03 15:29 | 2020-09-10 14:42
2021 WS Mule 5B | 2021 | WS | Mule | 5B | Active | 16 | 2019-09-30 | -99.1429 | 2019-10-14 | -97.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-10-25 11:13 | 2020-09-10 14:42
2021 WS Mule 5A | 2021 | WS | Mule | 5A | Active | 8 | 2019-09-23 | -100.1429 | 2019-10-07 | -98.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-10-25 11:11 | 2020-09-10 14:42
2022 LA Mule 1 | 2022 | LA | Mule | 1 | Active |  |  | No Date |  | No Date | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-10-23 10:01 | 2020-01-15 12:50
2022 WL Proto 2 PHEV | 2022 | WL | Proto | 2 PHEV | Active | 38 | 2020-02-17 | -79.1429 | 2020-03-02 | -77.1429 | Harvey Gavin (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-09-30 16:31 | 2020-09-10 14:42
2021 WS Proto 6 | 2021 | WS | Proto | 6 | Active | 2 | 2019-11-25 | -91.1429 | 2019-12-09 | -89.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-09-25 14:25 | 2020-09-10 14:43
2022 WL Proto 1 PHEV | 2022 | WL | Proto | 1 PHEV | Active |  | 2019-09-30 | -99.1429 | 2019-10-14 | -97.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-09-23 16:24 | 2020-01-15 12:50
2021 JL Mule 3 J9 | 2021 | JL | Mule | 3 J9 | Completed | 13 | 2019-09-30 | -99.1429 | 2019-10-14 | -97.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-09-19 12:53 | 2020-01-15 12:50
2021 WD Mule 2 | 2021 | WD | Mule | 2 | Active | 28 | 2019-08-26 | -104.1429 | 2019-09-09 | -102.1429 | Harvey Gavin (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-09-11 13:58 | 2020-01-15 12:50
2023 RD Mule 1 CUV | 2023 | RD | Mule | 1 CUV | Active | 10 | 2020-04-20 | -70.1429 | 2020-05-04 | -68.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-08-28 12:37 | 2020-01-15 12:50
2023 RU Mule 2 BEV | 2023 | RU | Mule | 2 BEV | Active | 32 | 2020-10-26 | -43.1429 | 2020-11-09 | -41.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-08-28 12:35 | 2020-01-15 12:49
2023 RU Mule 1 BEV | 2023 | RU | Mule | 1 BEV | Active | 6 | 2020-05-18 | -66.1429 | 2020-06-01 | -64.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-08-28 12:33 | 2020-02-21 11:41
2021 WL Mule 75-1 | 2021 | WL | Mule | 75-1 | Active | 9 | 2019-05-13 | -119.1429 | 2019-05-27 | -117.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-08-06 07:27 | 2020-01-15 12:49
2022 RU Mule 2 iDCM | 2022 | RU | Mule | 2 iDCM | Active | 7 | 2019-10-21 | -96.1429 | 2019-11-04 | -94.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-07-19 08:19 | 2020-02-13 14:34
2022 LD Mule 1 | 2022 | LD | Mule | 1 | Active |  | 2019-10-21 | -96.1429 | 2019-11-04 | -94.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-07-18 11:17 | 2020-01-15 12:49
2022 LA Mule 1 | 2022 | LA | Mule | 1 | Active |  | 2019-10-21 | -96.1429 | 2019-11-04 | -94.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-07-18 11:16 | 2020-01-15 12:49
2030 ZE Proto 2 | 2030 | ZE | Proto | 2 | Active |  |  | No Date |  | No Date | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-07-18 10:17 | 2020-01-15 12:49
2022 WL Proto 1 PHEV | 2022 | WL | Proto | 1 PHEV | Cancelled |  | 2019-09-30 | -99.1429 | 2019-10-14 | -97.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-06-28 16:50 | 2020-01-15 12:49
2022 DT Mule 1 BIN30 | 2022 | DT | Mule | 1 BIN30 | Active | 19 | 2020-07-20 | -57.1429 | 2020-08-03 | -55.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-06-19 09:13 | 2020-03-12 11:19
2020 JT Mule 6 | 2020 | JT | Mule | 6 | Active | 2 | 2019-08-12 | -106.1429 | 2019-08-26 | -104.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-06-18 11:32 | 2020-01-15 12:49
2022 WS Proto 2A | 2022 | WS | Proto | 2A | Active | 44 | 2019-11-04 | -94.1429 | 2019-11-18 | -92.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-06-14 13:16 | 2020-09-10 14:43
2020 JL Mule PHEV VP-B Bucks | 2020 | JL | Mule | PHEV VP-B Bucks | Active | 10 | 2019-08-26 | -104.1429 | 2019-09-09 | -102.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-06-13 13:22 | 2020-01-15 12:49
2020 JT Mule BUX VP Bucks | 2020 | JT | Mule | BUX VP Bucks | Active | 9 | 2019-08-26 | -104.1429 | 2019-09-09 | -102.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-06-13 13:18 | 2020-01-15 12:49
2021 JL Mule J9 Mule-4 | 2021 | JL | Mule | J9 Mule-4 | Active |  | 2019-12-16 | -88.1429 | 2020-01-06 | -85.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-06-12 17:03 | 2020-01-15 12:49
2021 HD Mule 2 | 2021 | HD | Mule | 2 | Active | 9 | 2019-10-07 | -98.1429 | 2019-10-21 | -96.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-06-07 06:49 | 2020-01-15 12:49
2022 WS Mule 1A | 2022 | WS | Mule | 1A | Active | 8 | 2019-06-17 | -114.1429 | 2019-07-01 | -112.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-06-06 07:55 | 2020-01-15 12:49
2020 JL Mule 2 | 2020 | JL | Mule | 2 | Active | 8 | 2019-08-26 | -104.1429 | 2019-09-09 | -102.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-06-04 11:52 | 2020-01-15 12:49
2020 JL Mule 2 | 2020 | JL | Mule | 2 | Active |  | 2019-08-26 | -104.1429 | 2019-09-09 | -102.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-05-22 13:09 | 2020-01-15 12:49
2021 WL Mule 75-2 | 2021 | WL | Mule | 75-2 | Active | 21 | 2019-06-03 | -116.1429 | 2019-06-17 | -114.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-05-22 10:51 | 2020-01-15 12:49
2020 JL Mule 1 | 2020 | JL | Mule | 1 | Active | 20 | 2019-05-27 | -117.1429 | 2019-06-10 | -115.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-05-13 09:45 | 2020-01-15 12:49
2021 WL Mule 75-3 | 2021 | WL | Mule | 75-3 | Active |  | 2019-07-22 | -109.1429 | 2019-08-05 | -107.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-05-08 17:37 | 2020-01-15 12:49
2023 DT Mule 1 | 2023 | DT | Mule | 1 | Active | 1 | 2019-10-28 | -95.1429 | 2019-11-11 | -93.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-05-02 15:31 | 2020-01-15 12:49
2020 RU VP Buck | 2020 | RU | VP | Buck | Completed | 4 | 2019-09-02 | -103.1429 | 2019-09-16 | -101.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-05-01 09:11 | 2020-02-21 12:01
2023 RU Mule 1 EVA | 2023 | RU | Mule | 1 EVA | Active | 2 | 2020-03-30 | -73.1429 | 2020-04-13 | -71.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-05-01 09:09 | 2020-02-13 14:38
2021 WL Mule 1 | 2021 | WL | Mule | 1 | Active | 9 | 2019-05-06 | -120.1429 | 2019-05-20 | -118.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-04-30 08:32 | 2020-01-15 12:49
2021 WS Mule 4 | 2021 | WS | Mule | 4 | Active | 6 | 2019-10-14 | -97.1429 | 2019-10-28 | -95.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-04-23 11:12 | 2020-01-15 12:49
2021 WS Mule 2C | 2021 | WS | Mule | 2C | Active | 5 | 2019-05-20 | -118.1429 | 2019-06-03 | -116.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-04-23 10:55 | 2020-01-15 12:49
2020 JT Mule 5 | 2020 | JT | Mule | 5 | Active | 9 | 2019-04-22 | -122.1429 | 2019-05-06 | -120.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-03-27 07:43 | 2020-01-15 12:49
2020 JT Mule 5 | 2020 | JT | Mule | 5 | Active |  | 2019-04-22 | -122.1429 | 2019-05-06 | -120.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-03-18 14:24 | 2020-01-15 12:49
2021 DS Mule 1 | 2021 | DS | Mule | 1 | Active | 9 | 2019-09-16 | -101.1429 | 2019-09-30 | -99.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-03-12 07:47 | 2020-01-15 12:49
2022 WL Proto PHEV-1 | 2022 | WL | Proto | PHEV-1 | Active | 52 | 2019-09-30 | -99.1429 | 2019-10-14 | -97.1429 | Harvey Gavin (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-03-08 15:00 | 2020-01-21 09:35
2021 WL Proto 75-1 | 2021 | WL | Proto | 75-1 | Active | 37 | 2019-08-26 | -104.1429 | 2019-09-09 | -102.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-03-08 10:19 | 2020-09-10 14:44
2020 JL Mule PHEV VP-B Bucks | 2020 | JL | Mule | PHEV VP-B Bucks | Active |  | 2019-08-19 | -105.1429 | 2019-09-02 | -103.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-03-05 09:05 | 2020-01-15 12:49
2021 WS Mule 3B | 2021 | WS | Mule | 3B | Active | 28 | 2019-04-01 | -125.1429 | 2019-04-15 | -123.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-03-05 07:31 | 2020-09-10 14:45
2020 JL Mule PHEV VP-A Bucks | 2020 | JL | Mule | PHEV VP-A Bucks | Active |  | 2019-05-27 | -117.1429 | 2019-06-10 | -115.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-03-04 07:34 | 2020-01-15 12:49
2021 WD Mule SRT Mule-1 | 2021 | WD | Mule | SRT Mule-1 | Active | 13 | 2019-01-28 | -134.1429 | 2019-02-11 | -132.1429 | Stuglin Jeff (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-02-09 09:30 | 2020-01-15 12:49
2021 WS Mule 3C | 2021 | WS | Mule | 3C | Active | 16 | 2019-07-01 | -112.1429 | 2019-07-15 | -110.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-02-04 12:18 | 2020-04-01 13:15
2021 WS Proto 1 | 2021 | WS | Proto | 1 | Active | 25 | 2019-07-08 | -111.1429 | 2019-07-22 | -109.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-02-04 11:44 | 2020-04-01 13:15
2020 JT Mule BUX VP Bucks | 2020 | JT | Mule | BUX VP Bucks | Active |  | 2019-06-10 | -115.1429 | 2019-06-24 | -113.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-02-04 07:20 | 2020-01-15 12:49
2021 LD Mule 1 Pursuit | 2021 | LD | Mule | 1 Pursuit | Active | 14 | 2019-04-29 | -121.1429 | 2019-05-13 | -119.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-01-11 12:20 | 2020-01-15 12:49
2020 JL Mule PHEV VP-A Bucks | 2020 | JL | Mule | PHEV VP-A Bucks | Active | 18 | 2019-05-27 | -117.1429 | 2019-06-10 | -115.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2019-01-07 11:47 | 2020-01-15 12:49
2022 RU Mule 1 PHEV | 2022 | RU | Mule | 1 PHEV | Completed | 2 | 2019-11-18 | -92.1429 | 2019-12-02 | -90.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-12-19 08:59 | 2020-02-21 12:03
2021 WL Mule 5 | 2021 | WL | Mule | 5 | Active | 9 | 2019-01-07 | -137.1429 | 2019-01-21 | -135.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-12-11 09:23 | 2020-01-15 12:49
2021 HD Mule 1 | 2021 | HD | Mule | 1 | Active | 18 | 2019-03-18 | -127.1429 | 2019-04-01 | -125.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-11-14 07:46 | 2020-01-15 12:49
2021 DT Mule 1 | 2021 | DT | Mule | 1 | Active | 2 | 2019-08-19 | -105.1429 | 2019-09-02 | -103.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-11-14 07:43 | 2020-01-15 12:49
2019 DT VP Compliance Buck | 2019 | DT | VP | Compliance Buck | Completed | 90 | 2018-10-08 | -150.1429 | 2018-10-22 | -148.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-10-31 10:50 | 2020-01-15 12:49
2020 JT VP Buck | 2020 | JT | VP | Buck | Active |  | 2018-09-24 | -152.1429 | 2018-10-08 | -150.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-10-18 13:25 | 2020-01-15 12:49
2021 WL Mule PHEV 8 | 2021 | WL | Mule | PHEV 8 | Active |  | 2019-06-03 | -116.1429 | 2019-06-17 | -114.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-09-25 08:40 | 2020-01-15 12:49
2021 WL Mule 4B | 2021 | WL | Mule | 4B | Active |  | 2019-04-08 | -124.1429 | 2019-04-22 | -122.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-09-25 08:22 | 2020-01-15 12:49
2021 WL Mule 8 | 2021 | WL | Mule | 8 | Active |  | 2019-04-01 | -125.1429 | 2019-04-15 | -123.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-09-23 22:02 | 2020-01-15 12:49
2021 WL Mule 6 | 2021 | WL | Mule | 6 | Active |  | 2019-02-25 | -130.1429 | 2019-03-11 | -128.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-09-23 21:35 | 2020-01-15 12:49
2021 WS Mule 2B | 2021 | WS | Mule | 2B | Active | 21 | 2018-11-12 | -145.1429 | 2018-11-26 | -143.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-09-07 15:54 | 2020-04-01 13:15
2021 WL Mule 4 | 2021 | WL | Mule | 4 | Active | 22 | 2018-10-29 | -147.1429 | 2018-10-15 | -149.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-08-30 07:37 | 2020-01-15 12:49
2021 LA Mule Mule-1 | 2021 | LA | Mule | Mule-1 | Active |  | 2019-02-18 | -131.1429 | 2019-03-04 | -129.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-08-24 11:53 | 2020-01-15 12:49
2021 WL Mule 3B | 2021 | WL | Mule | 3B | Active | 6 | 2018-10-15 | -149.1429 | 2018-10-29 | -147.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-07-31 12:23 | 2020-01-15 12:49
2020 LD Mule Mule-2 | 2020 | LD | Mule | Mule-2 | Active | 9 | 2018-06-25 | -165.1429 | 2018-07-09 | -163.1429 | Stuglin Jeff (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-07-10 12:58 | 2020-01-15 12:49
2020 DJ Mule 2 | 2020 | DJ | Mule | 2 | Completed | 21 | 2019-02-18 | -131.1429 | 2019-03-04 | -129.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-07-06 09:41 | 2020-01-15 12:49
2021 WL Mule PHEV 4 | 2021 | WL | Mule | PHEV 4 | Active |  | 2018-11-05 | -146.1429 | 2018-11-19 | -144.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-06-27 12:19 | 2020-01-15 12:49
2020 M4 Mule 2 | 2020 | M4 | Mule | 2 | Active |  | 2018-12-03 | -142.1429 | 2018-12-17 | -140.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-06-08 16:04 | 2020-01-15 12:49
2021 DT Mule TR Mule-3 | 2021 | DT | Mule | TR Mule-3 | Active |  | 2018-12-17 | -140.1429 | 2019-01-07 | -137.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-05-24 08:18 | 2020-01-15 12:49
2020 M4 Mule 1 | 2020 | M4 | Mule | 1 | Active |  | 2018-04-30 | -173.1429 | 2018-05-14 | -171.1429 | Podczervinski Brian (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-05-15 10:48 | 2020-01-15 12:49
2021 WS Mule 2/3 | 2021 | WS | Mule | 2/3 | Active |  | 2018-11-19 | -144.1429 | 2018-12-03 | -142.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-05-09 14:26 | 2020-01-15 12:49
2019 M4 Mule 4 | 2019 | M4 | Mule | 4 | Active | 2 | 2018-05-14 | -171.1429 | 2018-05-28 | -169.1429 | Podczervinski Brian (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-05-08 12:11 | 2020-01-15 12:49
2021 WL Proto 2 | 2021 | WL | Proto | 2 | Active |  | 2019-02-11 | -132.1429 | 2019-02-25 | -130.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-04-30 11:15 | 2020-01-15 12:49
2020 JL Proto 1- PHEV | 2020 | JL | Proto | 1- PHEV | Active | 60 | 2018-11-12 | -145.1429 | 2018-11-26 | -143.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-04-17 13:01 | 2020-01-21 09:36
2021 WL Mule 3 | 2021 | WL | Mule | 3 | Active |  | 2018-05-21 | -170.1429 | 2018-06-04 | -168.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-04-04 08:10 | 2020-01-15 12:49
2021 DT Mule TR Mule-2 | 2021 | DT | Mule | TR Mule-2 | Active |  | 2018-10-15 | -149.1429 | 2018-10-29 | -147.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-03-23 10:33 | 2020-01-15 12:49
2021 MP Mule 1 | 2021 | MP | Mule | 1 | Active |  | 2018-10-15 | -149.1429 | 2018-10-29 | -147.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-03-22 11:56 | 2020-01-15 12:49
2021 WS Mule 2 | 2021 | WS | Mule | 2 | Active |  | 2018-07-09 | -163.1429 | 2018-07-23 | -161.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-03-12 08:32 | 2020-01-15 12:49
2021 WL Proto PHEV 1 | 2021 | WL | Proto | PHEV 1 | Cancelled | 52 | 2019-03-18 | -127.1429 | 2019-04-01 | -125.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-03-02 15:32 | 2020-05-29 15:19
2020 RU Mule 2 | 2020 | RU | Mule | 2 | Completed | 32 | 2018-09-24 | -152.1429 | 2018-10-08 | -150.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-03-01 10:35 | 2020-01-15 12:49
2021 WS Mule 3A | 2021 | WS | Mule | 3A | Active | 45 | 2019-01-07 | -137.1429 | 2019-01-21 | -135.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-02-19 07:10 | 2020-04-01 13:15
2020 WD Mule 3 | 2020 | WD | Mule | 3 | Active |  | 2018-02-19 | -183.1429 | 2018-03-05 | -181.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-02-02 09:19 | 2020-01-15 12:49
2021 WL Proto 1 | 2021 | WL | Proto | 1 | Active | 142 | 2019-01-21 | -135.1429 | 2019-02-04 | -133.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-02-01 14:59 | 2020-01-21 09:36
2020 LD Mule SRT 1 | 2020 | LD | Mule | SRT 1 | Active | 12 | 2018-03-26 | -178.1429 | 2018-04-09 | -176.1429 | Stuglin Jeff (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-01-31 09:44 | 2020-01-15 12:49
2019 K8 Mule PHEV 1 | 2019 | K8 | Mule | PHEV 1 | Active | 12 | 2018-01-15 | -188.1429 | 2018-01-29 | -186.1429 | Stuglin Jeff (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-01-31 09:36 | 2020-01-15 12:49
2020 JT Mule 4 | 2020 | JT | Mule | 4 | Active |  | 2018-08-20 | -157.1429 | 2018-09-03 | -155.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-01-25 16:29 | 2020-01-15 12:49
2021 WS Mule 1 | 2021 | WS | Mule | 1 | Active | 2 | 2018-01-15 | -188.1429 | 2018-01-29 | -186.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-01-22 13:45 | 2020-01-15 12:49
2020 JL Mule 2A- PHEV | 2020 | JL | Mule | 2A- PHEV | Active | 8 | 2018-01-08 | -189.1429 | 2018-01-22 | -187.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-01-22 13:41 | 2020-01-15 12:49
2020 VM Mule 1 | 2020 | VM | Mule | 1 | Active |  |  | No Date |  | No Date | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-01-17 15:26 | 2020-01-15 12:49
2020 RU Mule 1 | 2020 | RU | Mule | 1 | Completed | 8 | 2018-05-28 | -169.1429 | 2018-06-11 | -167.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-01-11 16:14 | 2020-01-15 12:49
2020 DT Mule Bucks | 2020 | DT | Mule | Bucks | Active |  |  | No Date |  | No Date | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-01-10 11:23 | 2020-01-15 12:49
2020 LX Mule 1 | 2020 | LX | Mule | 1 | Active | 9 | 2017-12-18 | -192.1429 | 2018-01-08 | -189.1429 | Stuglin Jeff (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-01-03 09:39 | 2020-01-15 12:49
2020 LD Mule 1 | 2020 | LD | Mule | 1 | Active | 29 | 2017-12-04 | -194.1429 | 2017-12-18 | -192.1429 | Stuglin Jeff (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-01-03 09:37 | 2020-01-15 12:49
2020 LA Mule 1 | 2020 | LA | Mule | 1 | Active | 28 | 2017-12-04 | -194.1429 | 2017-12-18 | -192.1429 | Stuglin Jeff (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2018-01-03 09:32 | 2020-01-15 12:49
2020 JL Mule 2B- PHEV | 2020 | JL | Mule | 2B- PHEV | Active | 13 | 2018-04-23 | -174.1429 | 2018-05-07 | -172.1429 | Stafford Mollie (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-12-21 13:35 | 2020-01-15 12:49
2021 WL Mule 1 | 2021 | WL | Mule | 1 | Active |  | 2018-04-16 | -175.1429 | 2018-04-30 | -173.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-12-18 15:12 | 2020-01-15 12:49
2019 DJ VP Pre-VP | 2019 | DJ | VP | Pre-VP | Completed | 6 | 2017-10-30 | -199.1429 | 2017-11-13 | -197.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-12-15 10:52 | 2020-01-15 12:49
2020 JT Mule VP BUCKS | 2020 | JT | Mule | VP BUCKS | Active |  | 2018-06-25 | -165.1429 | 2018-07-09 | -163.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-12-14 14:56 | 2020-01-15 12:49
2021 WL Mule PHEV 1 | 2021 | WL | Mule | PHEV 1 | Cancelled |  | 2018-03-26 | -178.1429 | 2018-04-09 | -176.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-12-13 07:22 | 2020-01-15 12:49
2019 K4 Mule 3 | 2019 | K4 | Mule | 3 | Active | 6 | 2017-11-06 | -198.1429 | 2017-11-20 | -196.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-12-11 14:35 | 2020-01-15 12:48
2030 ZE Mule Test | 2030 | ZE | Mule | Test | Active | 25 | 2018-01-05 | -189.5714 | 2018-01-12 | -188.5714 | Thyagaraj Meena (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-11-29 09:33 | 2020-10-09 13:08
2019 M4 Mule 2 | 2019 | M4 | Mule | 2 | Active | 38 | 2017-10-30 | -199.1429 | 2017-11-13 | -197.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-11-17 15:57 | 2020-01-15 12:48
2020 DJ Mule 1 | 2020 | DJ | Mule | 1 | Completed | 49 | 2018-01-29 | -186.1429 | 2018-02-12 | -184.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-10-17 12:40 | 2020-01-15 12:48
2019 HD VP A | 2019 | HD | VP | A | Completed | 26 | 2018-02-05 | -185.1429 | 2018-02-19 | -183.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-09-25 15:27 | 2020-01-15 12:48
2021 WL Mule 2 | 2021 | WL | Mule | 2 | Active |  | 2018-01-29 | -186.1429 | 2018-02-12 | -184.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-09-19 16:54 | 2020-01-15 12:48
2019 K4 Mule 2 | 2019 | K4 | Mule | 2 | Active |  | 2017-10-16 | -201.1429 | 2017-10-30 | -199.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-09-11 16:24 | 2020-01-15 12:48
2020 JL Mule 2A- PHEV | 2020 | JL | Mule | 2A- PHEV | Active | 8 | 2017-10-30 | -199.1429 | 2017-11-13 | -197.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-07-14 13:45 | 2020-01-15 12:48
2019 KL Mule VP-B Compliance Bucks | 2019 | KL | Mule | VP-B Compliance Bucks | Active |  | 2017-05-29 | -221.1429 | 2017-06-12 | -219.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-07-13 09:16 | 2020-01-15 12:48
2019 LA Mule SRT Mule 1 | 2019 | LA | Mule | SRT Mule 1 | Active | 29 | 2017-06-12 | -219.1429 | 2017-06-26 | -217.1429 | Stuglin Jeff (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-06-27 16:01 | 2020-01-15 12:48
2019 KL Mule PS-A Compliance Bucks | 2019 | KL | Mule | PS-A Compliance Bucks | Active |  | 2017-08-14 | -210.1429 | 2017-08-28 | -208.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-06-02 13:10 | 2020-01-15 12:48
2019 M4 Mule 1 | 2019 | M4 | Mule | 1 | Active |  | 2017-09-04 | -207.1429 | 2017-09-18 | -205.1429 | Podczervinski Brian (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-05-17 15:37 | 2020-01-15 12:48
2019 MP Mule 1 | 2019 | MP | Mule | 1 | Active | 19 | 2017-04-24 | -226.1429 | 2017-05-08 | -224.1429 | Podczervinski Brian (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-05-17 14:22 | 2020-01-15 12:48
2019 DJ Mule 4B | 2019 | DJ | Mule | 4B | Completed | 2 | 2017-06-05 | -220.1429 | 2017-06-19 | -218.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-05-16 07:08 | 2020-02-21 11:53
2020 WL Mule 3 | 2020 | WL | Mule | 3 | Active |  | 2018-01-29 | -186.1429 | 2018-02-12 | -184.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-05-09 10:09 | 2020-01-15 12:48
2019 K4 Mule 1 | 2019 | K4 | Mule | 1 | Active |  | 2017-09-18 | -205.1429 | 2017-10-02 | -203.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-05-02 14:32 | 2020-01-15 12:48
2020 WD Mule 2 | 2020 | WD | Mule | 2 | Active |  | 2017-10-23 | -200.1429 | 2017-11-06 | -198.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-03-31 16:31 | 2020-01-15 12:48
2020 WK Mule 2 | 2020 | WK | Mule | 2 | Active |  | 2017-10-23 | -200.1429 | 2017-11-06 | -198.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-03-31 16:27 | 2020-01-15 12:48
2019 KL Mule MCA VP-B Bucks | 2019 | KL | Mule | MCA VP-B Bucks | Active |  | 2017-05-29 | -221.1429 | 2017-06-12 | -219.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-03-24 14:26 | 2020-01-15 12:48
2018 JL Proto VP 2 Door Bucks | 2018 | JL | Proto | VP 2 Door Bucks | Active | 25 | 2017-05-29 | -221.1429 | 2017-06-12 | -219.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-03-20 15:33 | 2020-01-15 12:48
2019 KL Mule 4-Repower | 2019 | KL | Mule | 4-Repower | Active | 20 | 2017-02-20 | -235.1429 | 2017-03-06 | -233.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-03-15 09:47 | 2020-01-15 12:48
2020 WL Mule 2 | 2020 | WL | Mule | 2 | Active |  | 2017-09-18 | -205.1429 | 2017-10-02 | -203.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-03-01 10:56 | 2020-01-15 12:48
2019 DT Mule VP Compliance Bucks | 2019 | DT | Mule | VP Compliance Bucks | Active |  | 2017-05-22 | -222.1429 | 2017-06-05 | -220.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-02-03 19:11 | 2020-01-15 12:48
2019 KL Mule 3B | 2019 | KL | Mule | 3B | Active | 22 | 2017-01-16 | -240.1429 | 2017-01-30 | -238.1429 | Kulkarni Ruturaj (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-02-03 10:50 | 2020-01-15 12:48
2019 JT Proto 3 | 2019 | JT | Proto | 3 | Active | 53 | 2017-08-21 | -209.1429 | 2017-09-05 | -207 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-01-20 16:44 | 2020-04-01 13:23
2019 JT Proto ALL | 2019 | JT | Proto | ALL | Active |  |  | No Date |  | No Date | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-01-18 13:07 | 2020-01-15 12:48
2018 JL Proto VP Compliance Bucks | 2018 | JL | Proto | VP Compliance Bucks | Active | 144 | 2017-03-20 | -231.1429 | 2017-04-03 | -229.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2017-01-03 10:07 | 2020-01-15 12:48
2019 JT Proto 2 | 2019 | JT | Proto | 2 | Active | 110 | 2017-05-01 | -225.1429 | 2017-05-15 | -223.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-12-19 10:33 | 2020-04-01 13:23
2019 JL Mule 6A | 2019 | JL | Mule | 6A | Active |  | 2017-03-13 | -232.1429 | 2017-03-27 | -230.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-12-08 09:34 | 2020-01-15 12:48
2019 KL Mule MCA- VP Compliance Buck build | 2019 | KL | Mule | MCA- VP Compliance Buck build | Active |  | 2017-04-03 | -229.1429 | 2017-04-17 | -227.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-12-06 18:48 | 2020-01-15 12:48
2018 RU Mule PC0 Compliance Bucks | 2018 | RU | Mule | PC0 Compliance Bucks | Active |  | 2017-01-16 | -240.1429 | 2017-01-30 | -238.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-12-05 14:34 | 2020-01-15 12:48
2019 DJ Proto 1 | 2019 | DJ | Proto | 1 | Completed | 63 | 2017-02-27 | -234.1429 | 2017-03-13 | -232.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-11-04 16:22 | 2020-02-21 11:51
2019 KL Mule 2D | 2019 | KL | Mule | 2D | Active | 81 | 2016-09-26 | -256.1429 | 2016-10-10 | -254.1429 | Kulkarni Ruturaj (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-10-20 10:44 | 2020-01-15 12:48
2019 HD Proto 2 | 2019 | HD | Proto | 2 | Active | 97 | 2017-05-01 | -225.1429 | 2017-05-15 | -223.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-10-18 06:58 | 2020-01-15 12:48
2019 DD Proto A | 2019 | DD | Proto | A | Completed | 119 | 2017-02-27 | -234.1429 | 2017-03-13 | -232.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-10-13 10:56 | 2020-02-21 11:55
2019 D2 Proto A | 2019 | D2 | Proto | A | Completed | 119 | 2017-02-27 | -234.1429 | 2017-03-13 | -232.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-10-13 10:54 | 2020-02-21 11:54
2019 DP Proto A | 2019 | DP | Proto | A | Completed | 119 | 2017-02-27 | -234.1429 | 2017-03-13 | -232.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-10-13 10:40 | 2020-02-21 11:55
2019 DJ Proto A | 2019 | DJ | Proto | A | Active | 119 | 2017-02-27 | -234.1429 | 2017-03-13 | -232.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-08-25 11:30 | 2020-01-15 12:48
2019 K8 Proto PHEV 2 | 2019 | K8 | Proto | PHEV 2 | Active | 47 | 2017-02-20 | -235.1429 | 2017-03-06 | -233.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-08-09 07:46 | 2020-01-15 12:48
2019 K8 Proto PHEV 1B | 2019 | K8 | Proto | PHEV 1B | Active | 5 | 2016-11-14 | -249.1429 | 2016-11-28 | -247.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-08-09 07:42 | 2020-01-15 12:48
2019 K8 Proto 2 | 2019 | K8 | Proto | 2 | Active |  | 2016-02-22 | -287.1429 | 2017-03-06 | -233.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-07-27 10:17 | 2020-01-15 12:48
2018 JL Proto 4C | 2018 | JL | Proto | 4C | Active | 2 | 2016-10-31 | -251.1429 | 2016-11-14 | -249.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-07-07 15:17 | 2020-04-01 13:23
2018 JL Mule 3B | 2018 | JL | Mule | 3B | Active | 2 | 2016-12-19 | -244.1429 | 2017-01-02 | -242.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-07-07 13:56 | 2020-01-15 12:48
2019 HD Proto 1 | 2019 | HD | Proto | 1 | Active | 117 | 2017-02-27 | -234.1429 | 2017-03-13 | -232.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-06-22 07:53 | 2020-01-15 12:48
2019 HD Mule 4 | 2019 | HD | Mule | 4 | Completed | 77 | 2016-10-17 | -253.1429 | 2016-10-31 | -251.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-06-22 07:52 | 2020-02-21 11:53
2019 DT Proto C | 2019 | DT | Proto | C | Active |  | 2016-06-27 | -269.1429 | 2016-07-11 | -267.1429 | Podczervinski Brian (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-06-21 13:01 | 2020-01-15 12:48
2019 DT Proto B | 2019 | DT | Proto | B | Active |  | 2016-05-23 | -274.1429 | 2016-06-06 | -272.1429 | Podczervinski Brian (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-06-21 12:54 | 2020-01-15 12:48
2018 JL Proto 2C | 2018 | JL | Proto | 2C | Active | 4 | 2016-05-16 | -275.1429 | 2016-05-30 | -273.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-06-06 13:41 | 2020-01-15 12:48
2019 KL Mule 3 | 2019 | KL | Mule | 3 | Active |  | 2016-08-08 | -263.1429 | 2016-08-22 | -261.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-05-05 16:37 | 2020-01-15 12:48
2017 MP VP VP Bucks | 2017 | MP | VP | VP Bucks | Completed | 16 | 2016-05-30 | -273.1429 | 2016-06-13 | -271.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-04-28 12:33 | 2020-02-21 11:58
2019 JL Proto 6A | 2019 | JL | Proto | 6A | Active | 21 | 2016-09-05 | -259.1429 | 2016-09-19 | -257.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-04-27 13:55 | 2020-01-15 12:48
2019 HD Mule 3A | 2019 | HD | Mule | 3A | Active | 10 | 2016-04-04 | -281.1429 | 2016-04-18 | -279.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-04-26 10:07 | 2020-01-15 12:48
2018 RU Mule 1- China Build | 2018 | RU | Mule | 1- China Build | Active |  | 2016-05-02 | -277.1429 | 2016-05-16 | -275.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-04-18 08:16 | 2020-01-15 12:48
2018 RU Mule 1- PHEV China | 2018 | RU | Mule | 1- PHEV China | Active |  | 2016-05-02 | -277.1429 | 2016-05-16 | -275.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-04-12 15:59 | 2020-01-15 12:48
2019 K8 Proto PHEV 1 | 2019 | K8 | Proto | PHEV 1 | Active | 6 | 2016-11-14 | -249.1429 | 2016-11-28 | -247.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-04-04 10:39 | 2020-01-15 12:48
2019 DT Proto D | 2019 | DT | Proto | D | Active |  | 2016-11-14 | -249.1429 | 2016-10-31 | -251.1429 | Podczervinski Brian (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-04-01 07:20 | 2020-01-15 12:48
2018 K8 Mule 5 | 2018 | K8 | Mule | 5 | Active |  | 2016-08-29 | -260.1429 | 2016-09-12 | -258.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-03-30 16:35 | 2020-01-15 12:48
2018 KL Mule 3 | 2018 | KL | Mule | 3 | Active |  | 2016-07-18 | -266.1429 | 2016-08-01 | -264.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-03-18 12:33 | 2020-01-15 12:48
2018 WD Mule 2- SRT | 2018 | WD | Mule | 2- SRT | Active |  | 2016-01-04 | -294.1429 | 2016-01-18 | -292.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-03-11 12:53 | 2020-01-15 12:48
2019 DT Mule 2B | 2019 | DT | Mule | 2B | Active | 11 | 2016-07-04 | -268.1429 | 2016-07-18 | -266.1429 | Podczervinski Brian (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-03-10 07:47 | 2020-01-15 12:48
2019 RA Mule 1A- PHEV | 2019 | RA | Mule | 1A- PHEV | Active |  | 2016-09-19 | -257.1429 | 2016-10-03 | -255.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-03-09 13:12 | 2020-01-15 12:48
2019 DK Mule 4 | 2019 | DK | Mule | 4 | Active | 86 | 2016-09-05 | -259.1429 | 2016-09-19 | -257.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-03-01 13:42 | 2020-01-15 12:48
2018 JL Proto 2E | 2018 | JL | Proto | 2E | Active | 10 | 2016-08-29 | -260.1429 | 2016-09-12 | -258.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-03-01 10:10 | 2020-04-01 13:23
2018 K8 Mule 4B | 2018 | K8 | Mule | 4B | Active | 13 | 2016-05-30 | -273.1429 | 2016-06-13 | -271.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-02-15 09:29 | 2020-01-15 12:48
2019 WN Mule 1 and 2 | 2019 | WN | Mule | 1 and 2 | Active |  | 2016-07-11 | -267.1429 | 2016-07-25 | -265.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-02-10 17:00 | 2020-01-15 12:48
2018 JL Proto 2D PWB | 2018 | JL | Proto | 2D PWB | Active |  | 2016-01-25 | -291.1429 | 2016-02-08 | -289.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-01-28 13:05 | 2020-01-15 12:48
2018 JL Proto 4A PWB | 2018 | JL | Proto | 4A PWB | Active |  | 2016-01-25 | -291.1429 | 2016-02-08 | -289.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-01-28 13:04 | 2020-01-15 12:48
2018 JL Proto 5A PWB | 2018 | JL | Proto | 5A PWB | Active |  | 2015-11-30 | -299.1429 | 2015-12-14 | -297.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-01-28 13:02 | 2020-01-15 12:48
2018 JL Proto 2B PWB | 2018 | JL | Proto | 2B PWB | Active |  | 2016-01-16 | -292.4286 | 2016-01-30 | -290.4286 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-01-28 12:58 | 2020-01-15 12:48
2019 RA Mule 1A | 2019 | RA | Mule | 1A | Active |  | 2016-06-08 | -271.8571 | 2016-06-23 | -269.7143 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-01-11 13:26 | 2020-01-15 12:48
2017 LA Mule B | 2017 | LA | Mule | B | Active | 4 | 2016-04-18 | -279.1429 | 2016-05-02 | -277.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-01-08 07:58 | 2020-01-15 12:48
2018 K8 Mule 3 | 2018 | K8 | Mule | 3 | Active | 4 | 2016-03-07 | -285.1429 | 2016-03-21 | -283.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-01-05 12:14 | 2020-01-15 12:48
2018 JL Proto 4B | 2018 | JL | Proto | 4B | Active | 20 | 2016-05-16 | -275.1429 | 2016-05-30 | -273.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2016-01-05 09:39 | 2020-01-15 12:48
2018 K8 Mule 4 | 2018 | K8 | Mule | 4 | Active | 27 | 2016-05-23 | -274.1429 | 2016-06-06 | -272.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-12-17 07:36 | 2020-01-15 12:48
2018 JL Mule 2C | 2018 | JL | Mule | 2C | Active | 5 | 2016-01-18 | -292.1429 | 2016-02-01 | -290.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-12-08 11:34 | 2020-01-15 12:48
2018 DT Proto C | 2018 | DT | Proto | C | Active |  | 2016-06-27 | -269.1429 | 2016-07-11 | -267.1429 | Podczervinski Brian (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-11-30 15:39 | 2020-01-15 12:48
2019 JT Proto 1 | 2019 | JT | Proto | 1 | Active | 20 | 2017-01-30 | -238.1429 | 2017-02-13 | -236.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-11-23 11:39 | 2020-04-01 13:23
2018 JL Proto ALL | 2018 | JL | Proto | ALL | Active |  | 2015-11-09 | -302.1429 | 2015-11-09 | -302.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-11-09 11:07 | 2020-01-15 12:48
2017 MP Mule 5 | 2017 | MP | Mule | 5 | Completed | 16 | 2015-12-28 | -295.1429 | 2016-01-11 | -293.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-11-05 13:32 | 2020-02-21 11:58
2017 RU Mule PHEV CHina Mule 1 | 2017 | RU | Mule | PHEV CHina Mule 1 | Active |  | 2015-12-21 | -296.1429 | 2016-01-04 | -294.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-10-21 11:38 | 2020-01-15 12:48
2018 WD Mule 1 | 2018 | WD | Mule | 1 | Active |  | 2016-02-14 | -288.2857 | 2016-02-29 | -286.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-10-15 12:44 | 2020-01-15 12:48
2018 WK Mule 1 | 2018 | WK | Mule | 1 | Active |  | 2016-02-14 | -288.2857 | 2016-02-29 | -286.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-10-15 12:42 | 2020-01-15 12:48
2019 LA Mule 1- SRT | 2019 | LA | Mule | 1- SRT | Active | 36 | 2016-01-04 | -294.1429 | 2016-01-18 | -292.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-10-13 14:14 | 2020-01-15 12:48
2018 WD Mule 1 and 2- SRT | 2018 | WD | Mule | 1 and 2- SRT | Active |  | 2016-01-04 | -294.1429 | 2016-01-18 | -292.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-10-13 12:21 | 2020-01-15 12:48
2019 DK Mule 2 | 2019 | DK | Mule | 2 | Active | 7 | 2016-02-01 | -290.1429 | 2016-02-15 | -288.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-10-08 11:48 | 2020-01-15 12:48
2018 JL Mule 3A | 2018 | JL | Mule | 3A | Active |  | 2015-11-16 | -301.1429 | 2015-11-30 | -299.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-10-08 10:45 | 2020-01-15 12:48
2017 LA Mule A | 2017 | LA | Mule | A | Active | 17 | 2015-10-26 | -304.1429 | 2015-11-09 | -302.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-10-07 09:38 | 2020-01-15 12:48
2018 DS Mule 1 | 2018 | DS | Mule | 1 | Active | 18 | 2016-02-22 | -287.1429 | 2016-03-07 | -285.1429 | Podczervinski Brian (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-10-02 08:27 | 2020-01-15 12:48
2018 JL Proto 5B | 2018 | JL | Proto | 5B | Active | 30 | 2016-03-28 | -282.1429 | 2016-04-11 | -280.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-09-30 06:51 | 2020-01-15 12:47
2018 JL Proto 3A | 2018 | JL | Proto | 3A | Active | 30 | 2016-04-11 | -280.1429 | 2016-04-25 | -278.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-09-30 06:50 | 2020-01-15 12:47
2017 RU Mule 1 - PHEV China | 2017 | RU | Mule | 1 - PHEV China | Active |  | 2016-01-04 | -294.1429 | 2016-01-18 | -292.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-09-28 09:08 | 2020-01-15 12:47
2017 M1 Mule VP Bucks | 2017 | M1 | Mule | VP Bucks | Completed | 106 | 2015-10-26 | -304.1429 | 2015-11-09 | -302.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-09-21 09:55 | 2020-02-21 12:00
2018 K8 Proto 1C | 2018 | K8 | Proto | 1C | Active | 3 | 2016-01-18 | -292.1429 | 2016-02-01 | -290.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-09-17 13:54 | 2020-01-15 12:47
2018 KL Mule 2D | 2018 | KL | Mule | 2D | On Hold | 58 | 2016-04-25 | -278.1429 | 2016-05-09 | -276.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-09-11 07:19 | 2020-01-15 12:47
2018 JL Proto Architecture 2A | 2018 | JL | Proto | Architecture 2A |  | 82 | 2015-08-31 | -312.1429 | 2015-09-14 | -310.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-09-09 09:25 | 2020-01-15 12:47
2017 MP Mule 4 | 2017 | MP | Mule | 4 | Completed | 30 | 2015-08-03 | -316.1429 | 2015-08-17 | -314.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-08-31 09:41 | 2020-02-21 11:57
2018 DT Mule 2D3 | 2018 | DT | Mule | 2D3 | Active | 30 | 2016-02-08 | -289.1429 | 2016-02-22 | -287.1429 | Podczervinski Brian (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-08-25 14:04 | 2020-01-15 12:47
2018 JL Proto 2D | 2018 | JL | Proto | 2D | Active | 14 | 2016-03-21 | -283.1429 | 2016-04-04 | -281.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-08-24 11:08 | 2020-04-01 13:23
2017 K4 Mule 2 | 2017 | K4 | Mule | 2 | Completed | 8 | 2015-11-16 | -301.1429 | 2015-11-30 | -299.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-08-05 22:02 | 2020-01-15 12:47
2018 WD Mule SRT- 2 | 2018 | WD | Mule | SRT- 2 | Active | 12 | 2016-01-04 | -294.1429 | 2016-01-18 | -292.1429 | Kulkarni Ruturaj (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-08-04 16:07 | 2020-01-15 12:47
2017 M4 Mule 3 | 2017 | M4 | Mule | 3 | Active |  | 2015-10-19 | -305.1429 | 2015-11-02 | -303.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-08-04 15:42 | 2020-01-15 12:47
2017 RU Mule 1- PHEV China | 2017 | RU | Mule | 1- PHEV China | Active |  | 2015-12-21 | -296.1429 | 2016-01-04 | -294.1429 | Kulkarni Ruturaj (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-08-04 13:29 | 2020-01-15 12:47
2018 K8 Proto 1B | 2018 | K8 | Proto | 1B | Active | 5 | 2015-11-16 | -301.1429 | 2015-11-30 | -299.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-07-29 13:33 | 2020-01-15 12:47
2018 JL Proto Architecture 1C | 2018 | JL | Proto | Architecture 1C |  | 4 | 2015-12-21 | -296.1429 | 2016-01-04 | -294.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-07-14 15:55 | 2020-01-15 12:47
2017 MP Mule 2017 M6 Mule 1 | 2017 | MP | Mule | 2017 M6 Mule 1 | Completed | 18 | 2015-06-29 | -321.1429 | 2015-07-13 | -319.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-07-14 13:58 | 2020-01-15 12:47
2017 WK Mule SRT-1 | 2017 | WK | Mule | SRT-1 | Cancelled |  | 2015-10-12 | -306.1429 | 2015-10-26 | -304.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-07-13 08:31 | 2020-01-15 12:47
2017 RU VP Bucks | 2017 | RU | VP | Bucks | Active | 149 | 2015-06-23 | -322 | 2015-07-07 | -320 | Kulkarni Ruturaj (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-07-07 15:28 | 2020-01-15 12:47
2018 JL Proto 5A | 2018 | JL | Proto | 5A | Active | 10 | 2015-11-30 | -299.1429 | 2015-12-14 | -297.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-07-02 13:11 | 2020-01-15 12:47
2018 JL Proto 4A | 2018 | JL | Proto | 4A | Active | 38 | 2015-11-16 | -301.1429 | 2015-11-30 | -299.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-07-02 13:09 | 2020-01-15 12:47
2018 WD Mule 1- Scat Pack | 2018 | WD | Mule | 1- Scat Pack | Active | 31 | 2015-10-19 | -305.1429 | 2015-11-02 | -303.1429 | Kulkarni Ruturaj (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-06-12 09:31 | 2020-01-15 12:47
2018 WK Mule 2- Hellcat | 2018 | WK | Mule | 2- Hellcat | Active | 27 | 2016-01-04 | -294.1429 | 2016-01-11 | -293.1429 | Kulkarni Ruturaj (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-06-12 09:29 | 2020-01-15 12:47
2018 WK Mule 1- Hellcat | 2018 | WK | Mule | 1- Hellcat | Active | 5 | 2015-10-26 | -304.1429 | 2015-11-09 | -302.1429 | Kulkarni Ruturaj (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-06-12 09:01 | 2020-01-15 12:47
2017 WK Mule 2 | 2017 | WK | Mule | 2 | Active | 50 | 2015-05-25 | -326.1429 | 2015-06-08 | -324.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-06-12 08:35 | 2020-01-15 12:47
2017 RU Golden Car | 2017 | RU |  | Golden Car | Completed | 1 | 2015-05-22 | -326.5714 | 2015-06-08 | -324.1429 | Vartti Shane (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-06-10 14:30 | 2020-01-15 12:47
2018 JL Proto 2B | 2018 | JL | Proto | 2B | Active | 39 | 2016-02-08 | -289.1429 | 2016-02-22 | -287.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-05-20 16:04 | 2020-04-01 13:23
2018 WL Mule Mule 2 | 2018 | WL | Mule | Mule 2 | Cancelled |  | 2015-05-25 | -326.1429 | 2015-06-08 | -324.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-05-04 15:45 | 2020-01-15 12:47
2018 DT Mule 2A | 2018 | DT | Mule | 2A | Completed |  | 2015-03-16 | -336.1429 | 2015-03-30 | -334.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-04-20 16:04 | 2020-01-15 12:47
2018 KL Proto 1 | 2018 | KL | Proto | 1 | On Hold | 68 | 2016-04-25 | -278.1429 | 2016-05-09 | -276.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-03-27 15:48 | 2020-01-15 12:47
2018 KL Mule 2B | 2018 | KL | Mule | 2B | Completed | 21 | 2015-08-10 | -315.1429 | 2015-08-24 | -313.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-03-27 15:45 | 2020-01-15 12:47
2018 KL Mule 2A | 2018 | KL | Mule | 2A | Completed | 28 | 2015-04-09 | -332.7143 | 2015-04-23 | -330.7143 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-03-27 15:30 | 2020-01-15 12:47
2018 WL Mule SRT- Mule 1 | 2018 | WL | Mule | SRT- Mule 1 | Cancelled |  | 2015-09-21 | -309.1429 | 2015-10-05 | -307.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-03-27 14:31 | 2020-01-15 12:47
2018 K8 Mule 2B | 2018 | K8 | Mule | 2B | Active | 2 | 2015-09-21 | -309.1429 | 2015-10-05 | -307.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-03-26 11:50 | 2020-01-15 12:47
2018 KL Mule 2C | 2018 | KL | Mule | 2C | Completed | 2 | 2015-09-14 | -310.1429 | 2015-09-28 | -308.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-03-26 11:49 | 2020-01-15 12:47
2018 DT Mule 1 | 2018 | DT | Mule | 1 | Completed |  | 2014-10-15 | -357.8571 | 2014-10-15 | -357.8571 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-03-25 13:56 | 2020-01-15 12:47
2017 WK Mule 1 | 2017 | WK | Mule | 1 | Completed | 2 | 2015-02-16 | -340.1429 | 2015-03-02 | -338.1429 | Kulkarni Ruturaj (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-03-20 14:44 | 2020-01-15 12:47
2016.5 JK Mule 2 | 2016.5 | JK | Mule | 2 | Completed | 12 | 2015-02-16 | -340.1429 | 2015-03-02 | -338.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-03-20 14:43 | 2020-01-15 12:47
2017 MP Mule 2B | 2017 | MP | Mule | 2B | Completed | 27 | 2015-01-05 | -346.1429 | 2015-01-19 | -344.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-03-20 14:39 | 2020-01-15 12:47
2017 WK Mule 1- SRT | 2017 | WK | Mule | 1- SRT | On Hold |  | 2015-10-12 | -306.1429 | 2015-10-26 | -304.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-03-18 22:03 | 2020-01-15 12:47
2017 M4 Mule test | 2017 | M4 | Mule | test | Completed |  | 2026-03-02 | 235.8571 | 2026-03-02 | 235.8571 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-02-26 07:28 | 2020-01-15 12:47
2018 K8 Proto 1 | 2018 | K8 | Proto | 1 | Completed | 22 | 2015-08-24 | -313.1429 | 2015-09-08 | -311 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-02-20 10:27 | 2020-01-15 12:47
2018 JL Proto Functional 2C | 2018 | JL | Proto | Functional 2C |  |  | 2015-11-09 | -302.1429 | 2015-11-23 | -300.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-02-12 14:35 | 2020-01-15 12:47
2018 JL Mule 2B | 2018 | JL | Mule | 2B | Completed |  | 2015-06-29 | -321.1429 | 2015-07-13 | -319.1429 | [10 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-02-12 14:33 | 2020-01-15 12:47
2018 JL Proto 2A | 2018 | JL | Proto | 2A | Active | 82 | 2015-08-31 | -312.1429 | 2015-09-14 | -310.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-02-12 11:10 | 2020-01-15 12:47
2016.5 JK Mule Mule 1 | 2016.5 | JK | Mule | Mule 1 | Completed | 6 | 2014-12-15 | -349.1429 | 2015-01-05 | -346.1429 | Costello Steve (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-01-09 11:37 | 2020-01-15 12:50
2018 DT Mule 1D3 | 2018 | DT | Mule | 1D3 | Completed | 7 | 2015-03-02 | -338.1429 | 2015-03-16 | -336.1429 | Mutrynowski Scott (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2015-01-09 11:09 | 2020-01-15 12:47
2018 K8 Mule 1 | 2018 | K8 | Mule | 1 | Completed | 1 | 2014-11-17 | -353.1429 | 2014-12-01 | -351.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-10-24 14:22 | 2020-01-15 12:47
2018 JL Proto Architecture - 1B Body Bucks | 2018 | JL | Proto | Architecture - 1B Body Bucks | Completed | 13 | 2015-04-13 | -332.1429 | 2015-04-27 | -330.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-10-07 14:02 | 2020-01-15 12:47
2018 DT Proto B | 2018 | DT | Proto | B | Active |  | 2015-06-08 | -324.1429 | 2014-06-22 | -374.2857 | Podczervinski Brian (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-09-19 13:39 | 2020-01-15 12:47
2016 BA Mule 3 | 2016 | BA | Mule | 3 | Completed | 8 | 2014-05-26 | -378.1429 | 2014-06-09 | -376.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-08-20 10:03 | 2020-01-15 12:47
2017 UF Mule 1 - Hurricane | 2017 | UF | Mule | 1 - Hurricane | Completed | 2 | 2014-04-07 | -385.1429 | 2014-04-21 | -383.1429 | Mutrynowski Scott (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-08-20 09:59 | 2020-01-15 12:47
2025 EE Proto Random Phase | 2025 | EE | Proto | Random Phase | Cancelled | 50 | 2014-09-23 | -361 | 2014-09-30 | -360 | Vincent Eric (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-08-04 14:27 | 2020-01-15 12:47
2016.5 RU Proto 1A - PHEV | 2016.5 | RU | Proto | 1A - PHEV | Completed | 9 | 2014-07-07 | -372.1429 | 2014-07-21 | -370.1429 | Schoenherr Anthony (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-16 15:27 | 2020-01-15 12:47
2016 RU Proto 1 | 2016 | RU | Proto | 1 | Completed | 43 | 2014-06-09 | -376.1429 | 2014-06-23 | -374.1429 | Schoenherr Anthony (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-16 15:26 | 2020-01-15 12:47
2018 JL Proto Architecture 1A | 2018 | JL | Proto | Architecture 1A | Completed | 43 | 2015-01-19 | -344.1429 | 2015-02-02 | -342.1429 | Sovis Jim (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:31 | 2020-01-15 12:47
2017 UF Mule 3 - GMET4 | 2017 | UF | Mule | 3 - GMET4 | Cancelled | 14 | 2015-08-17 | -314.1429 | 2015-08-31 | -312.1429 | Mutrynowski Scott (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:30 | 2020-01-15 12:47
2016 BA Proto 1 | 2016 | BA | Proto | 1 | Completed | 70 | 2015-04-09 | -332.7143 | 2015-04-23 | -330.7143 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:29 | 2020-01-15 12:47
2016 BA Proto 2 | 2016 | BA | Proto | 2 | Completed | 37 | 2015-04-13 | -332.1429 | 2015-04-27 | -330.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:28 | 2020-01-15 12:47
2016 M4 Mule 2C | 2016 | M4 | Mule | 2C | Completed | 21 | 2015-03-23 | -335.1429 | 2015-04-06 | -333.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:28 | 2020-01-15 12:47
2018 DT Proto A | 2018 | DT | Proto | A | Completed | 20 | 2015-03-02 | -338.1429 | 2015-03-16 | -336.1429 | Mutrynowski Scott (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:27 | 2020-01-15 12:47
2016 MP Mule 2A | 2016 | MP | Mule | 2A | Completed | 30 | 2015-02-02 | -342.1429 | 2015-02-16 | -340.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:26 | 2020-01-15 12:47
2017 UF Mule 2B - GMET4 | 2017 | UF | Mule | 2B - GMET4 | Completed | 20 | 2015-03-30 | -334.1429 | 2015-04-13 | -332.1429 | Mutrynowski Scott (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:25 | 2020-01-15 12:47
2017 RA Mule 1 | 2017 | RA | Mule | 1 | Cancelled | 16 | 2015-01-12 | -345.1429 | 2015-01-26 | -343.1429 | Schoenherr Anthony (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:24 | 2020-01-15 12:47
2016 MP Mule 2B - ESS | 2016 | MP | Mule | 2B - ESS | Completed | 35 | 2015-01-05 | -346.1429 | 2015-01-19 | -344.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:23 | 2020-01-15 12:47
2017 UF Mule 2A - GMET4 | 2017 | UF | Mule | 2A - GMET4 | Completed | 14 | 2015-01-05 | -346.1429 | 2014-01-19 | -396.2857 | Mutrynowski Scott (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:22 | 2020-01-15 12:47
2016 WD Mule 4 | 2016 | WD | Mule | 4 | Completed | 3 | 2014-12-08 | -350.1429 | 2014-01-05 | -398.2857 | Costello Steve (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:21 | 2020-01-15 12:47
2016 WK Mule 4 | 2016 | WK | Mule | 4 | Completed | 13 | 2014-12-08 | -350.1429 | 2014-01-05 | -398.2857 | Costello Steve (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 13:20 | 2020-01-15 12:47
2016 BA Mule 4 | 2016 | BA | Mule | 4 | Completed | 14 | 2014-11-17 | -353.1429 | 2014-12-01 | -351.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 11:38 | 2020-01-15 12:47
2016 M1 Mule 2B | 2016 | M1 | Mule | 2B | Completed | 16 | 2014-10-20 | -357.1429 | 2014-11-03 | -355.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 11:37 | 2020-01-15 12:47
2016 K4 Mule 2A | 2016 | K4 | Mule | 2A | Completed | 2 | 2014-09-01 | -364.1429 | 2014-09-15 | -362.1429 | Mutrynowski Scott (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 11:35 | 2020-01-15 12:47
2016 MP Mule 3 | 2016 | MP | Mule | 3 | Completed | 3 | 2014-08-25 | -365.1429 | 2014-09-08 | -363.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 11:35 | 2020-01-15 12:47
2016 KL Mule 2 | 2016 | KL | Mule | 2 | Completed | 10 | 2014-08-18 | -366.1429 | 2014-09-01 | -364.1429 | Mutrynowski Scott (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 11:34 | 2020-01-15 12:47
2016 K4 Mule 2B | 2016 | K4 | Mule | 2B | Completed | 11 | 2014-08-04 | -368.1429 | 2014-08-18 | -366.1429 | Mutrynowski Scott (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 11:34 | 2020-01-15 12:47
2016 DS Mule 1 | 2016 | DS | Mule | 1 | Completed | 18 | 2014-07-21 | -370.1429 | 2014-08-04 | -368.1429 | Costello Steve (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 11:32 | 2020-01-15 12:47
2017 RU Proto 1 - ESS | 2017 | RU | Proto | 1 - ESS | Completed | 18 | 2014-09-15 | -362.1429 | 2014-09-29 | -360.1429 | Schoenherr Anthony (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 11:29 | 2020-01-15 12:47
2016.5 RU Proto 1B - PHEV | 2016.5 | RU | Proto | 1B - PHEV | Completed | 58 | 2014-08-19 | -366 | 2014-09-02 | -364 | Schoenherr Anthony (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 11:29 | 2020-01-15 12:47
2016 RU Proto 3 - International | 2016 | RU | Proto | 3 - International | Completed | 9 | 2014-08-11 | -367.1429 | 2014-08-25 | -365.1429 | Schoenherr Anthony (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 11:25 | 2020-01-15 12:47
2016 WK Mule 1 - SRT | 2016 | WK | Mule | 1 - SRT | Completed | 32 | 2014-06-02 | -377.1429 | 2014-06-16 | -375.1429 | Gajewski Walt (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 11:06 | 2020-01-15 12:46
2017 RU Mule 1 | 2017 | RU | Mule | 1 | Completed | 3 | 2014-05-26 | -378.1429 | 2014-06-09 | -376.1429 | Schoenherr Anthony (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 10:55 | 2020-01-15 12:46
2016 WD Mule 3B | 2016 | WD | Mule | 3B | Completed | 41 | 2014-06-09 | -376.1429 | 2014-06-23 | -374.1429 | Costello Steve (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 10:54 | 2020-01-15 12:46
2016 WD Mule 3A | 2016 | WD | Mule | 3A | Completed | 32 | 2014-04-21 | -383.1429 | 2014-05-05 | -381.1429 | Costello Steve (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 10:53 | 2020-01-15 12:46
2016 DD Mule 2 | 2016 | DD | Mule | 2 | Completed | 29 | 2014-04-14 | -384.1429 | 2014-04-28 | -382.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 10:51 | 2020-01-15 12:46
2016 WK Mule 3B | 2016 | WK | Mule | 3B | Completed | 56 | 2014-06-09 | -376.1429 | 2014-06-23 | -374.1429 | Costello Steve (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 10:51 | 2020-01-15 12:46
2016 WK Mule 3A | 2016 | WK | Mule | 3A | Completed | 84 | 2014-04-14 | -384.1429 | 2014-04-28 | -382.1429 | Costello Steve (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 10:49 | 2020-01-15 12:46
2017 KL Mule 1 - GMET4 | 2017 | KL | Mule | 1 - GMET4 | Completed | 5 | 2014-03-31 | -386.1429 | 2014-04-14 | -384.1429 | Kaslly Mike (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 10:48 | 2020-01-15 12:46
2018 JL Mule 1 | 2018 | JL | Mule | 1 | Completed | 8 | 2014-10-20 | -357.1429 | 2014-11-03 | -355.1429 | Costello Steve (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 10:46 | 2020-01-15 12:46
2016 RU Proto 2 | 2016 | RU | Proto | 2 | Completed | 46 | 2014-07-14 | -371.1429 | 2014-07-28 | -369.1429 | Schoenherr Anthony (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 10:44 | 2020-01-15 12:46
2016 M1 Mule 2A | 2016 | M1 | Mule | 2A | Completed | 56 | 2014-07-21 | -370.1429 | 2014-08-04 | -368.1429 | Fallert Joe (FCA) | [9 empty] | https://docs.google.com/spreadsheets/d/1nfIP_OtZOujhiVO95Zpyos5kR8b8db6G5K3e6a9MZNc/edit?usp=sharing | 2014-07-14 10:40 | 2020-01-15 12:46

## PBE Build List
Build Title | Model Year | Vehicle Family | Build Type | Build Phase | Build Status | Vehicle Quantity | TCF MRD | Weeks to MRD | TCF Build Start | Weeks to Build Start | X-Flag Due Date | Final BOM Due Date | Process Sheet Due Date | BOM Review Date | Build Lead | Build Location | Build Strategy | WBS Code | Work Scope - 32wk (Plan) | Work Scope - 32wk (Actual) | Work Scope - 32wk (Pulse) | Noun Name Delivered - 30wk (Plan) | Noun Name Delivered - 30wk (Actual) | Noun Name Delivered - 30wk (Pulse) | Build Phase Funding Approved - 19wk (Plan) | Build Phase Funding Approved - 19wk (Actual) | Build Phase Funding Approved - 19wk (Pulse) | Vehicle QTY Published - 26wk (Plan) | Vehicle QTY Published - 26wk (Actual) | Vehicle QTY Published - 26wk (Pulse) | Carrier Specs Published - 18wk (Plan) | Carrier Specs Published - 18wk (Actual) | Carrier Specs Published - 18wk (Pulse) | Build Plan Complete - 16wk (Plan) | Build Plan Complete - 16wk (Actual) | Build Plan Complete - 16wk (Pulse) | Donor Order Pulse - 14wk (Plan) | Donor Order Pulse - 14wk (Actual) | Donor Order Pulse - 14wk (Pulse) | Bridge Design Complete - 12wk (Plan) | Bridge Design Complete - 12wk (Actual) | Bridge Design Complete - 12wk (Pulse) | Overall Build Pulse | Build Status Comments | Build Shop Readiness | Part Delivery Pulse | Program Scope | Carrier | Tree FC# | Build Total # of Parts | Build % REQ | Build % PO | Build % Received | Build Cost | Build Tracker URL | Date Created | Last Modified
2026 XX Mule 4 | 2026 | XX | Mule | 4 | Active | 55 | 2021-07-05 | -7.1429 | 2021-07-19 | -5.1429 | 2021-06-21 | 2021-06-25 | 2021-07-05 | 2021-07-14 | Anurag Bansal | Truck Garage |  | VD00111_EBPS_MU04 | 2020-12-07 | 2020-12-07 | Green | 2020-12-21 | 2020-12-21 | Green | 2021-03-08 | 2021-03-08 | Yellow | 2021-01-18 | 2021-01-18 | Red | 2021-03-15 | 2021-03-15 | Yellow | 2021-03-29 | 2021-03-29 | Green | 2021-04-12 | 2021-04-12 | Green | 2021-04-26 | 2021-04-26 | Green | Yellow | test | Green | Red |  |  | FC00ABC98876/0.001 |  |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/ | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/ | 2021-08-03 | 2021-07-28
2025 HD Mule 2 Diesel | 2025 | HD | Mule | 2 Diesel | Active | 6 | 2022-01-03 | 18.8571 | 2022-01-17 | 20.8571 |  |  |  |  | Joe Fallert | Truck | Hoist | VD00243_EBPS_MU02 | 2021-06-07 |  |  | 2021-06-21 |  |  | 2021-09-06 |  |  | 2021-07-19 |  |  | 2021-09-13 |  |  | 2021-09-27 |  |  | 2021-10-11 |  |  | 2021-10-25 | [14 empty] | https://docs.google.com/spreadsheets/d/1tzfGtKXNDlo-snT1hfs3xMez_fsv7BOsXLLWoY5BxXA/ | 2021-07-06 | 2021-07-06
2025 LB Mule 2 | 2025 | LB | Mule | 2 | Active | 17 | 2022-01-03 | 18.8571 | 2022-01-17 | 20.8571 | 2021-11-08 | 2021-11-22 | 2021-12-13 | 2021-12-20 | Ryan Sheen | PVO | Hoist/Carrier | VD00322_EBPS_MU02 | 2021-06-07 |  |  | 2021-06-21 |  |  | 2021-09-06 |  |  | 2021-07-19 |  |  | 2021-09-13 |  |  | 2021-09-27 |  |  | 2021-10-11 |  |  | 2021-10-25 | [7 empty] | 22 WL75 VP | [6 empty] | https://docs.google.com/spreadsheets/d/1X5IGZe0si7HazoXD8FaO7BQY-nIOUN0csRzH1hwU8g0/ | 2021-07-06 | 2021-08-20
2025 LB Mule 1 | 2025 | LB | Mule | 1 | Active | 3 | 2021-10-18 | 7.8571 | 2021-11-01 | 9.8571 | 2021-08-23 | 2021-09-06 | 2021-09-27 | 2021-10-04 | Ryan Sheen | PVO | Hoist | VD00322_EBPS_MU01 | 2021-03-22 |  |  | 2021-04-05 |  |  | 2021-06-21 |  |  | 2021-05-03 |  |  | 2021-06-28 |  |  | 2021-07-12 |  |  | 2021-07-26 |  |  | 2021-08-09 | [8 empty] | FC00ABY75203/001 | [5 empty] | https://docs.google.com/spreadsheets/d/1i8J0eSKbe6sgLXIHnha8xdEhCExoA0oPKbw6eZ93PMY/ | 2021-07-08 | 2021-08-20
2023 VF BEV Mule 2 | 2023 | VF BEV | Mule | 2 | Active | 26 | 2021-04-26 | -17.1429 | 2021-05-17 | -14.1429 | 2021-03-01 | 2021-03-15 | 2021-04-05 | 2021-04-12 | Mollie Stafford | PVO/ Truck |  | VD00583 | 2020-10-05 |  |  | 2020-10-19 |  |  | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-25 |  |  | 2021-02-08 |  |  | 2021-02-22 | [8 empty] | FA00ADV39660 & FA00ADV39701 | [5 empty] | https://docs.google.com/spreadsheets/d/1WfsgfBPvWlWIsajfbpaMw-LZ-hOZAORh_h4CIm9j3b0/ | 2021-07-28 | 2021-07-28
2024 JL Mule 1 | 2024 | JL | Mule | 1 | Active | 153v+2b | 2021-11-15 | 11.8571 | 2021-11-29 | 13.8571 | 2021-09-20 | 2021-10-04 | 2021-10-25 | 2021-11-01 | Mollie Stafford |  | Hoist/Carrier | VD00713_EBPS_MU01 | 2021-04-19 |  |  | 2021-05-03 |  |  | 2021-07-19 |  |  | 2021-05-31 |  |  | 2021-07-26 |  |  | 2021-08-09 |  |  | 2021-08-23 |  |  | 2021-09-06 | [8 empty] | N/A | [5 empty] | https://docs.google.com/spreadsheets/d/1I06FDo2lu1Xb4hyqvSW9JyOj7bKYvd1fr-cIk_d4ppo/ | 2021-07-28 | 2021-07-30
2024 JT Mule 1 | 2024 | JT | Mule | 1 | Active | 21 | 2022-01-31 | 22.8571 | 2022-02-14 | 24.8571 |  |  |  |  | Mollie Stafford |  | Hoist/ Carrier |  | 2021-07-05 |  |  | 2021-07-19 |  |  | 2021-10-04 |  |  | 2021-08-16 |  |  | 2021-10-11 |  |  | 2021-10-25 |  |  | 2021-11-08 |  |  | 2021-11-22 | [8 empty] | N/A | [5 empty] | https://docs.google.com/spreadsheets/d/1EvmtR1L3y_OWxvrti3jNwUo6IjzykEWEGhEIr5q7kcc/ | 2021-07-28 | 2021-07-30
Formulas:
Work Scope - 32wk (Plan) = [TCF Build Start]-7*32
Noun Name Delivered - 30wk (Plan) = [TCF Build Start]-7*30
Vehicle QTY Published - 26wk (Plan) = [TCF Build Start]-7*26
Carrier Specs Published - 18wk (Plan) = [TCF Build Start]-7*18
Build Plan Complete - 16wk (Plan) = [TCF Build Start]-7*16
Donor Order Pulse - 14wk (Plan) = [TCF Build Start]-7*14
Bridge Design Complete - 12wk (Plan) = [TCF Build Start]-7*12

## Add New Build
Add New Build
Model Year
Vehicle Family
Build Type
Build Phase
Vehicle Quantity
TCF MRD
TCF Build Start
Build Location
Build Strategy
WBS Code
Tree FC#
Program Scope
Carrier

## Edit Build Info
Edit Build Info
Build Title | 2025 LB Mule 1
| Current Info | New Info
Model Year | 2025
Vehicle Family | LB
Build Type | Mule
Build Phase | 1
Vehicle Quantity | 3
TCF MRD | 2021-10-18
TCF Build Start | 2021-11-01
Build Location | PVO
Build Strategy | Hoist
WBS Code | VD00322_EBPS_MU01
Tree FC# | FC00ABY75203/001
X-Flag Due Date | 2021-08-23
Final BOM Due Date | 2021-09-06
Process Sheet Due Date | 2021-09-27
BOM Review Date | 2021-10-04
Program Scope
Carrier

## Build Detail Status
[14 empty] | Designs | [5 empty] | Ordering | [5 empty] | Delivery | [5 empty] | BOM | [5 empty] | Designs | [5 empty] | Ordering | [5 empty] | Delivery | [5 empty] | BOM
Build Title | Vehicle Family | Build Status | Vehicle Quantity | TCF MRD | Weeks to MRD | TCF Build Start | Weeks to Build Start | Build Lead | Build Location | BICEEP | System | PBE Engineer | Total # of Parts | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | G | Y | R | B | N | 0 | Build Tracker URL
Build Title | Vehicle Family | Build Status | Vehicle Quantity | TCF MRD | Weeks to MRD | TCF Build Start | Weeks to Build Start | Build Lead | Build Location | BICEEP | System | PBE Engineer | Total # of Parts | Designs-G-% | Designs-Y-% | Designs-R-% | Designs-B-% | Designs-N-% | Designs-0-% | Ordering-G-% | Ordering-Y-% | Ordering-R-% | Ordering-B-% | Ordering-N-% | Ordering-0-% | Delivery-G-% | Delivery-Y-% | Delivery-R-% | Delivery-B-% | Delivery-N-% | Delivery-0-% | BOM-G-% | BOM-Y-% | BOM-R-% | BOM-B-% | BOM-N-% | BOM-0-% | Designs-G-# | Designs-Y-# | Designs-R-# | Designs-B-# | Designs-N-# | Designs-0-# | Ordering-G-# | Ordering-Y-# | Ordering-R-# | Ordering-B-# | Ordering-N-# | Ordering-0-# | Delivery-G-# | Delivery-Y-# | Delivery-R-# | Delivery-B-# | Delivery-N-# | Delivery-0-# | BOM-G-# | BOM-Y-# | BOM-R-# | BOM-B-# | BOM-N-# | BOM-0-# | Build Tracker URL
2024 XX Mule 2A | XX | Active | 23 | 2021-08-23 | 8 | 2021-09-06 | 10 | Anurag Bansal | PVO | Electrical | Modules | Anurag Bansal | 1 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/145-bO92-jIPbsmTw5W_AXOrPx-MVwkyfxWWwme5uHvs/
2023 XX Mule 1 | XX | Active | 22 | 2021-07-05 | 1 | 2021-07-19 | 3 | Michael Kaslly | PVO | Engine Systems | Exhaust | Anurag Bansal | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1j3LMeuuT7H62jMx2O2jZNHPC_aiNGw8XfTWVCA9By9A/
2023 XX Mule 1 | XX | Active | 22 | 2021-07-05 | 1 | 2021-07-19 | 3 | Michael Kaslly | PVO | Int/Ext | FEM | Ryan Andres | 42 | 88% | 10% | 2% | 0% | 0% | 0% | 81% | 2% | 17% | 0% | 0% | 0% | 0% | 93% | 7% | 0% | 0% | 0% | 0% | 88% | 12% | 0% | 0% | 0% | 37 | 4 | 1 | 0 | 0 | 0 | 34 | 1 | 7 | 0 | 0 | 0 | 0 | 39 | 3 | 0 | 0 | 0 | 0 | 37 | 5 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1j3LMeuuT7H62jMx2O2jZNHPC_aiNGw8XfTWVCA9By9A/
2023 XX Mule 1 | XX | Active | 22 | 2021-07-05 | 1 | 2021-07-19 | 3 | Michael Kaslly | PVO | Electrical | Radio | Anurag Bansal | 22 | 0% | 0% | 100% | 0% | 0% | 0% | 77% | 9% | 14% | 0% | 0% | 0% | 68% | 18% | 14% | 0% | 0% | 0% | 82% | 14% | 5% | 0% | 0% | 0% | 0 | 0 | 22 | 0 | 0 | 0 | 17 | 2 | 3 | 0 | 0 | 0 | 15 | 4 | 3 | 0 | 0 | 0 | 18 | 3 | 1 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1j3LMeuuT7H62jMx2O2jZNHPC_aiNGw8XfTWVCA9By9A/
2026 XX Mule 2B | XX | Active | 25 | 2021-08-09 | 6 | 2021-08-23 | 8 | Anurag Bansal | PVO | Int/Ext | Mirrors | Shrey Arodia | 17 | 0% | 0% | 24% | 0% | 0% | 76% | 0% | 0% | 24% | 0% | 0% | 76% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 12% | 0% | 0% | 88% | 0 | 0 | 4 | 0 | 0 | 13 | 0 | 0 | 4 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 2 | 0 | 0 | 15 | https://docs.google.com/spreadsheets/d/1Cx70dibMWlYuTFN8xMNG85n4Whq6raCZL0qwko0WVbE/
2026 XX Mule 2B | XX | Active | 25 | 2021-08-09 | 6 | 2021-08-23 | 8 | Anurag Bansal | PVO | Int/Ext | Doors | Anurag Bansal | 12 | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 42% | 0% | 0% | 58% | 0% | 0% | 17% | 0% | 0% | 83% | 0% | 0% | 33% | 0% | 0% | 67% | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 5 | 0 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 10 | 0 | 0 | 4 | 0 | 0 | 8 | https://docs.google.com/spreadsheets/d/1Cx70dibMWlYuTFN8xMNG85n4Whq6raCZL0qwko0WVbE/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Powertrain | Powertrain | Chris Engles | 1 | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Int/Ext | Doors | Shrey Arodia | 23 | 61% | 30% | 9% | 0% | 0% | 0% | 30% | 39% | 30% | 0% | 0% | 0% | 9% | 61% | 30% | 0% | 0% | 0% | 9% | 30% | 61% | 0% | 0% | 0% | 14 | 7 | 2 | 0 | 0 | 0 | 7 | 9 | 7 | 0 | 0 | 0 | 2 | 14 | 7 | 0 | 0 | 0 | 2 | 7 | 14 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Electrical | Wiring | Ashar Khan | 16 | 0% | 100% | 0% | 0% | 0% | 0% | 38% | 25% | 38% | 0% | 0% | 0% | 31% | 25% | 44% | 0% | 0% | 0% | 50% | 38% | 13% | 0% | 0% | 0% | 0 | 16 | 0 | 0 | 0 | 0 | 6 | 4 | 6 | 0 | 0 | 0 | 5 | 4 | 7 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Body | End Items | Wesley Cialek | 2 | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 0% | 0% | 0% | 0% | 50% | 50% | 0% | 0% | 0% | 50% | 50% | 0% | 0% | 0% | 0% | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Engine Systems | Exhaust | Susan Burhan | 22 | 45% | 0% | 55% | 0% | 0% | 0% | 77% | 9% | 14% | 0% | 0% | 0% | 68% | 18% | 14% | 0% | 0% | 0% | 82% | 14% | 5% | 0% | 0% | 0% | 10 | 0 | 12 | 0 | 0 | 0 | 17 | 2 | 3 | 0 | 0 | 0 | 15 | 4 | 3 | 0 | 0 | 0 | 18 | 3 | 1 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Chassis | Knuckles | Zunaid Khan | 22 | 86% | 0% | 14% | 0% | 0% | 0% | 82% | 0% | 18% | 0% | 0% | 0% | 82% | 0% | 18% | 0% | 0% | 0% | 91% | 0% | 9% | 0% | 0% | 0% | 19 | 0 | 3 | 0 | 0 | 0 | 18 | 0 | 4 | 0 | 0 | 0 | 18 | 0 | 4 | 0 | 0 | 0 | 20 | 0 | 2 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/

## Red Item Details
Build Title | Vehicle Family | Build Status | Vehicle Quantity | TCF MRD | Weeks to MRD | TCF Build Start | Weeks to Build Start | Build Lead | Build Location | Issue Category | BICEEP | System | PBE Engineer | Part Description | Part Number | Total Quantity | Comments to Report | REQ # | PO # | Supplier Name | Build Tracker URL
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Chassis | Knuckles | Zunaid Khan | Diesel Line Bracket | 1670H07448 |  | Design revision pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Chassis | Knuckles | Zunaid Khan | FUEL BUNDLE - CHASSIS DSL - DP 173WB/52GAL | 1670D77194 |  | Design not available in TeamCenter |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Chassis | Knuckles | Zunaid Khan | Fuel Delivery Module | 57008982AA | 2 | Need to confirm PN |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Engine Systems | Exhaust | Susan Burhan | FILLER PATCH PIECE - UREA TANK CROSSMEMBER | 1670H91792 |  | Design not released, long lead item |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Engine Systems | Exhaust | Susan Burhan | FUEL LINE TRANS BRKT | 1670H52564 |  | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Engine Systems | Exhaust | Susan Burhan | Diesel Line Bracket | 1670H07448 |  | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Engine Systems | Exhaust | Susan Burhan | TUBE ASSY - CHASSIS RETURN | 1670D72093 |  | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Engine Systems | Exhaust | Susan Burhan | FUEL TUBE - CHASSIS SUPPLY | 1670D72094 | 10 | Design not released | 4500720 |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Engine Systems | Exhaust | Susan Burhan | FSOV LINE | 1670D74120 | 10 | Design not released, can't send for RFQ, long lead item | 4500720 |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Engine Systems | Exhaust | Susan Burhan | FSOC TO HC DOSER LINE | 1670D72096 | 10 | Design not released | 4500720 |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Engine Systems | Exhaust | Susan Burhan | FUEL BUNDLE - CHASSIS DSL - DP 197WB/52GAL | 1670D76972 |  | Design not released | 4500720 |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Engine Systems | Exhaust | Susan Burhan | Fuel Delivery Module | 57008984AA | 3 | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Engine Systems | Exhaust | Susan Burhan | Fuel Delivery Module | 57008983AA | 1 | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Engine Systems | Exhaust | Susan Burhan | Fuel Delivery Module | 57008982AA | 2 | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Engine Systems | Exhaust | Susan Burhan | Fuel Delivery Module | 57008981AA | 7 | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Int/Ext | Doors | Shrey Arodia | APPLIQUE - RR QTR LT | 6UN17TRMAA | 45 |  |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Design Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - A-PILLAR RT | 6LF10TRMAA | 45 | Design Issues |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Chassis | Knuckles | Zunaid Khan | FSOV LINE | 1670D74120 | 10 | Req in approval for 3 weeks |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Chassis | Knuckles | Zunaid Khan | FUEL BUNDLE - CHASSIS DSL HO - DJ 160WB/31GAL | 1670D75635 | 2 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Chassis | Knuckles | Zunaid Khan | FUEL BUNDLE - CHASSIS DSL HO - DJ 149WB/31GAL | 1670D68770 | 3 | Req in approval for 3 weeks |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Chassis | Knuckles | Zunaid Khan | Fuel Delivery Module | 57008982AA | 2 | Need to confirm PN |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Engine Systems | Exhaust | Susan Burhan | FSOV LINE | 1670D74120 | 10 | Design not released, can't send for RFQ, long lead item | 4500720 |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Engine Systems | Exhaust | Susan Burhan | FUEL BUNDLE - CHASSIS DSL HO - DJ 160WB/31GAL | 1670D75635 | 2 | Design not released, long lead item |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Engine Systems | Exhaust | Susan Burhan | FUEL BUNDLE - CHASSIS DSL HO - DJ 149WB/31GAL | 1670D68770 | 3 | Design not released, potential delay ordering |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Body | End Items | Wesley Cialek | BRACKET ASSY - FENDER TO HOOD HINGE RT | 68444808AA | 2 | Quote Pending |  |  | RCO | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Electrical | Wiring | Ashar Khan | WIRING ASSY - FRONT END MODULE | 68343527AB |  | Design Revision pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Electrical | Wiring | Ashar Khan | CHARGER - WIRELESS DEVICE | 68487354AA |  | REQ Submitted |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Electrical | Wiring | Ashar Khan | USB CHARGING PORT - DUAL | 68487349AB |  | Quote Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Electrical | Wiring | Ashar Khan | TOUCH DISPLAY - HVAC CONTROLS COMFORT & CONVENIENCE | 68438397AA |  | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Electrical | Wiring | Ashar Khan | SWITCH ASSY - DOOR MOUNTED 24 WAY DRIVER | 68341963AB |  | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Electrical | Wiring | Ashar Khan | MICROPHONE ASSY - MODULE & BEZEL | 6UA07TRMAA |  | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Int/Ext | Doors | Shrey Arodia | ARM - SIDE RT | 6UN92TRMAA | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Int/Ext | Doors | Shrey Arodia | BEZEL - UPR SEAT BELT QTR LWR TRIM PANEL LT | 6TL03TRMAA | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - D-PILLAR W/POWER LIFTGATE LT | 6TK98TRMAB | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - C-D PILLAR UPR BRIDGE RT | 6RS02TRMAA | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - C-PILLAR UPR LT | 6LF51TRMAA | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - B-PILLAR UPR LT | 6LF29TRMAA | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Order Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - A-PILLAR LT | 6LF11TRMAA | 45 | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Chassis | Knuckles | Zunaid Khan | FILLER PATCH PIECE - UREA TANK CROSSMEMBER | 1670H91792 |  | PO Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Chassis | Knuckles | Zunaid Khan | FUEL BUNDLE - CHASSIS DSL - DP 197WB/52GAL | 1670D76970 | [5 empty] | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Chassis | Knuckles | Zunaid Khan | FUEL BUNDLE - CHASSIS DSL HO - DJ 169WB/32GAL | 1670D77196 | 2 |  |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Chassis | Knuckles | Zunaid Khan | Fuel Delivery Module | 57008982AA | 2 | Need to confirm PN |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Engine Systems | Exhaust | Susan Burhan | FILLER PATCH PIECE - UREA TANK CROSSMEMBER | 1670H91792 |  | Design not released, long lead item |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Engine Systems | Exhaust | Susan Burhan | FUEL BUNDLE - CHASSIS DSL - DP 197WB/52GAL | 1670D76970 |  | Design not released, long lead item |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Engine Systems | Exhaust | Susan Burhan | FUEL BUNDLE - CHASSIS DSL HO - DJ 169WB/32GAL | 1670D77196 | 2 | Mfg issue, supplier needs design revised |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Body | End Items | Wesley Cialek | BRACKET ASSY - FENDER TO HOOD HINGE LT | 68444809AA | 2 | REQ pending approval for 3 weeks |  |  | RCO | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Electrical | Wiring | Ashar Khan | BEZEL ASSY - OVERHEAD | 6WC60TRMAA |  | Part will be available after MRD |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Electrical | Wiring | Ashar Khan | WIRING ASSY - FRONT END MODULE | 68343527AB |  | Design Revision pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Electrical | Wiring | Ashar Khan | SC/HEX.FLG.HD - PILOT.PT | 06506188AA |  | Part will be available after MRD but before TCF |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Electrical | Wiring | Ashar Khan | CHARGER - WIRELESS DEVICE | 68487354AA |  | REQ Submitted |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Electrical | Wiring | Ashar Khan | USB CHARGING PORT - DUAL | 68487349AB |  | Quote Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Electrical | Wiring | Ashar Khan | TOUCH DISPLAY - HVAC CONTROLS COMFORT & CONVENIENCE | 68438397AA |  | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Electrical | Wiring | Ashar Khan | MICROPHONE ASSY - MODULE & BEZEL | 6UA07TRMAA |  | RFQ Pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Int/Ext | Doors | Shrey Arodia | ARM - SIDE LT | 6UN93TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Int/Ext | Doors | Shrey Arodia | TRIM PANEL ASSY - RR QTR LWR RT | 6LF66TRMAB | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Int/Ext | Doors | Shrey Arodia | BEZEL - C-PILLAR BELT OPENING RT | 6TL00TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - C-D PILLAR UPR BRIDGE LT | 6RS03TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - D-PILLAR UPR RT | 6LF52TRMAC | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - B-PILLAR LWR RT | 6LF30TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | Delivery Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - B-PILLAR RT | 6LF26TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Chassis | Knuckles | Zunaid Khan | Fuel Delivery Module | 57008982AA | 2 | Need to confirm PN |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Chassis | Knuckles | Zunaid Khan | Fuel Delivery Module | 57008981AA | 7 | Need to confirm C/L |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Engine Systems | Exhaust | Susan Burhan | Fuel Delivery Module | 57008981AA | 7 | Design not released |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Electrical | Wiring | Ashar Khan | WIRING ASSY - FRONT END MODULE | 68343527AB |  | Design Revision pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Electrical | Wiring | Ashar Khan | SENSOR MODULE - RAIN | 68384226AA |  | Part Number Confirmation reqd |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM PANEL ASSY - RR QTR LWR LT | 6YS96TRMAB | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | ARM - SIDE LT | 6UN93TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | APPLIQUE - RR QTR RT | 6UN16TRMAA | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM PANEL ASSY - RR QTR LWR RT | 6LF66TRMAB | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | BEZEL - C-PILLAR BELT OPENING LT | 6TL01TRMAA | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | BEZEL - C-PILLAR BELT OPENING RT | 6TL00TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | HANDLE - ASSIST RT | 6TE92TRMAA | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - C-D PILLAR UPR BRIDGE LT | 6RS03TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - D-PILLAR UPR LT | 6LF52TRMAC | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - D-PILLAR UPR RT | 6LF52TRMAC | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - B-PILLAR LWR LT | 6LF31TRMAA | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - B-PILLAR LWR RT | 6LF30TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - B-PILLAR LT | 6LF27TRMAA | 45 | Part Number confirmation pending |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Int/Ext | Doors | Shrey Arodia | TRIM COVER ASSY - B-PILLAR RT | 6LF26TRMAA | 45 | Long lead time, Meeting with supplier to confirm timing |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/
2026 XX Mule 4 | XX | Active | 45 | 2021-07-05 | 1 | 2021-07-19 | 3 | Anurag Bansal | PVO | BOM Issues | Powertrain | Powertrain | Chris Engles | SENSOR - AMBIENT TEMPERATURE | 05149265AB | 45 | Part number to be revised |  |  |  | https://docs.google.com/spreadsheets/d/1YeRyQI7qWCX0X2vHIVj3t9kq8fmiJ1N4d4QzylGEPfw/

## Build KPI Assessment
Edit Build Info
Build Title | 2026 XX Mule 4
| Current Info | New Info
Work Scope - 32wk (Plan) | 2020-12-07 |  | Work Scope - 32wk
Work Scope - 32wk (Actual) | 2020-12-07
Work Scope - 32wk (Pulse) | Green
Noun Name Delivered - 30wk (Plan) | 2020-12-21 |  | Noun Name Delivered - 30wk
Noun Name Delivered - 30wk (Actual) | 2020-12-21
Noun Name Delivered - 30wk (Pulse) | Green
Build Phase Funding Approved - 19wk (Plan) | 2021-03-08 |  | Build Phase Funding Approved - 19wk
Build Phase Funding Approved - 19wk (Actual) | 2021-03-08
Build Phase Funding Approved - 19wk (Pulse) | Yellow
Vehicle QTY Published - 26wk (Plan) | 2021-01-18 |  | Vehicle QTY Published - 26wk
Vehicle QTY Published - 26wk (Actual) | 2021-01-18
Vehicle QTY Published - 26wk (Pulse) | Red
Carrier Specs Published - 18wk (Plan) | 2021-03-15 |  | Carrier Specs Published - 18wk
Carrier Specs Published - 18wk (Actual) | 2021-03-15
Carrier Specs Published - 18wk (Pulse) | Yellow
Build Plan Complete - 16wk (Plan) | 2021-03-29 |  | Build Plan Complete - 16wk
Build Plan Complete - 16wk (Actual) | 2021-03-29
Build Plan Complete - 16wk (Pulse) | Green
Donor Order Pulse - 14wk (Plan) | 2021-04-12 |  | Donor Order Pulse - 14wk
Donor Order Pulse - 14wk (Actual) | 2021-04-12
Donor Order Pulse - 14wk (Pulse) | Green
Bridge Design Complete - 12wk (Plan) | 2021-04-26 |  | Bridge Design Complete - 12wk
Bridge Design Complete - 12wk (Actual) | 2021-04-26
Bridge Design Complete - 12wk (Pulse) | Green
Overall Build Pulse | Yellow |  | Overall Pulse & Comments
Build Shop Readiness | Green
Part Delivery Pulse | Red
Build Status Comments | test

## Build KPI Data
Build Title | SEQ | Build # | Plan MRD | Plan TCF Start | Plan Build Complete | Plan Delivery | Projected Delivery | Actual TCF Start | Actual Build Complete | Actual Delivery | Delivery Delta (Weeks) | Early Delivery | On-Time Delivery | 1 - 2 Week Late Delivery | More Than 2 Week Late Delivery | Chassis Shortages @ MRD | Electrical Shortages @ MRD | Engine Systems Shortages @ MRD | Exterior Shortages @ MRD | Interior Shortages @ MRD | Powertrain Shortages @ MRD | % Available @ MRD | Chassis Shortages @ Build Start | Electrical Shortages @ Build Start | Engine Systems Shortages @ Build Start | Exterior Shortages @ Build Start | Interior Shortages @ Build Start | Powertrain Shortages @ Build Start | % Available @ Build Start | Plan Build | Plan Validation | Week-of Effect | In Process Build | In Process Validation | Actual Build | Actual Validation | Plan Build + Plan Validation | Build Tracker URL
| 1 | R3MP-54178 | 2021-05-03 | 2021-05-17 | 2021-06-07 | 2021-06-21 |  | 2021-05-06 | 2021-06-11 | 2021-07-01 | 1.4 | 0 | 0 | 1 | 0 | 8 | 3 | 33 | 9 | 3 | 1 | 70% | 2 | 1 | 13 | 1 | 0 | 1 | 90% | 16 | 11 | 5 | #N/A | #N/A | 27 | 15 | 27
| 2 | R3MP-54181 | 2021-05-10 | 2021-05-24 | 2021-06-07 | 2021-06-21 |  | 2021-05-20 | 2021-06-15 | 2021-07-01 | 1.4 | 0 | 0 | 1 | 0 | 7 | 3 | 32 | 7 | 2 | 1 | 74% | 1 | 0 | 7 | 1 | 0 | 1 | 95% | 11 | 11 | 5 | #N/A | #N/A | 19 | 13 | 22
| 3 | R3MP-54183 | 2021-05-10 | 2021-05-24 | 2021-06-07 | 2021-06-21 |  | 2021-05-20 | 2021-06-18 | 2021-07-02 | 1.6 | 0 | 0 | 1 | 0 | 7 | 3 | 32 | 7 | 2 | 1 | 74% | 1 | 0 | 8 | 1 | 0 | 1 | 94% | 11 | 11 | 5 | #N/A | #N/A | 22 | 11 | 22
| 4 | R3MP-54186 | 2021-05-10 | 2021-05-24 | 2021-06-07 | 2021-06-21 |  | 2021-05-20 | 2021-06-15 | 2021-07-01 | 1.4 | 0 | 0 | 1 | 0 | 7 | 3 | 32 | 7 | 2 | 1 | 74% | 1 | 0 | 8 | 1 | 0 | 1 | 94% | 11 | 11 | 5 | #N/A | #N/A | 19 | 13 | 22
| 5 | R3MP-54187 | 2021-05-17 | 2021-05-31 | 2021-06-14 | 2021-06-28 |  | 2021-06-01 | 2021-06-21 | 2021-07-02 | 0.6 | 0 | 1 | 0 | 0 | 3 | 2 | 16 | 1 | 0 | 1 | 88% | 1 | 0 | 4 | 0 | 0 | 1 | 97% | 11 | 11 | 5 | #N/A | #N/A | 15 | 10 | 22
| 6 | R3MP-54199 | 2021-05-17 | 2021-05-31 | 2021-06-14 | 2021-06-28 |  | 2021-06-04 | 2021-06-23 | 2021-07-02 | 0.6 | 0 | 1 | 0 | 0 | 9 | 2 | 21 | 1 | 0 | 1 | 84% | 7 | 0 | 8 | 0 | 0 | 1 | 92% | 11 | 11 | 5 | #N/A | #N/A | 14 | 8 | 22
| 7 | R3MP-54192 | 2021-05-17 | 2021-05-31 | 2021-06-14 | 2021-06-28 |  | 2021-06-03 | 2021-06-22 | 2021-07-02 | 0.6 | 0 | 1 | 0 | 0 | 7 | 2 | 23 | 1 | 0 | 2 | 83% | 5 | 0 | 8 | 0 | 0 | 1 | 93% | 11 | 11 | 5 | #N/A | #N/A | 14 | 9 | 22
| 8 | R3MP-54205 | 2021-05-24 | 2021-06-07 | 2021-06-21 | 2021-07-05 |  | 2021-06-10 |  |  | -6340.3 | 0 | 0 | 0 | 0 | 6 | 0 | 20 | 2 | 0 | 1 | 85% | 4 | 0 | 6 | 0 | 0 | 0 | 95% | 11 | 11 | 5 | 38 | #N/A | #N/A | #N/A | 22
| 9 | R3MP-54198 | 2021-05-24 | 2021-06-07 | 2021-06-21 | 2021-07-05 |  | 2021-06-09 |  |  | -6340.3 | 0 | 0 | 0 | 0 | 9 | 0 | 20 | 2 | 0 | 1 | 85% | 6 | 0 | 6 | 0 | 0 | 1 | 94% | 11 | 11 | 5 | 39 | #N/A | #N/A | #N/A | 22
| 10 | R3MP-54200 | 2021-05-24 | 2021-06-07 | 2021-06-21 | 2021-07-05 |  | 2021-06-10 |  |  | -6340.3 | 0 | 0 | 0 | 0 | 9 | 0 | 20 | 2 | 0 | 1 | 85% | 7 | 0 | 8 | 0 | 0 | 1 | 92% | 11 | 11 | 5 | 38 | #N/A | #N/A | #N/A | 22
| 11 | R3MP-54201 | 2021-05-31 | 2021-06-14 | 2021-06-28 | 2021-07-12 |  | 2021-06-15 |  |  | -6341.3 | 0 | 0 | 0 | 0 | 5 | 0 | 11 | 0 | 0 | 1 | 91% | 4 | 0 | 10 | 0 | 0 | 1 | 92% | 11 | 11 | 5 | 35 | #N/A | #N/A | #N/A | 22
| 12 | R3MP-54202 | 2021-05-31 | 2021-06-14 | 2021-06-28 | 2021-07-12 |  | 2021-06-15 |  |  | -6341.3 | 0 | 0 | 0 | 0 | 8 | 1 | 12 | 0 | 0 | 1 | 89% | 6 | 0 | 11 | 0 | 0 | 1 | 91% | 11 | 11 | 5 | 35 | #N/A | #N/A | #N/A | 22
| 13 | R3MP-54203 | 2021-05-31 | 2021-06-14 | 2021-06-28 | 2021-07-12 |  | 2021-06-15 |  |  | -6341.3 | 0 | 0 | 0 | 0 | 8 | 1 | 12 | 0 | 0 | 2 | 89% | 6 | 0 | 12 | 0 | 0 | 1 | 91% | 11 | 11 | 5 | 35 | #N/A | #N/A | #N/A | 22
| 14 | R3MP-54204 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-07-19 |  | 2021-06-22 |  |  | -6342.3 | 0 | 0 | 0 | 0 | 7 | 1 | 10 | 0 | 0 | 1 | 91% | 0 | 1 | 6 | 0 | 0 | 1 | 96% | 11 | 11 | 5 | 30 | #N/A | #N/A | #N/A | 22
| 15 | R3MP-54182 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-07-19 |  | 2021-06-17 |  |  | -6342.3 | 0 | 0 | 0 | 0 | 4 | 3 | 10 | 0 | 0 | 1 | 91% | 0 | 0 | 6 | 0 | 0 | 1 | 96% | 11 | 11 | 5 | 33 | #N/A | #N/A | #N/A | 22
| 16 | R3MP-54185 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-07-19 |  | 2021-06-21 |  |  | -6342.3 | 0 | 0 | 0 | 0 | 4 | 5 | 10 | 0 | 0 | 1 | 90% | 0 | 3 | 6 | 0 | 0 | 1 | 95% | 11 | 11 | 5 | 31 | #N/A | #N/A | #N/A | 22
| 17 | R3MP-54196 | 2021-06-14 | 2021-06-28 | 2021-07-12 | 2021-07-26 |  | 2021-06-29 |  |  | -6343.3 | 0 | 0 | 0 | 0 | 6 | 5 | 12 | 0 | 0 | 2 | 88% | 0 | 3 | 4 | 0 | 0 | 0 | 96% | 11 | 11 | 5 | 25 | #N/A | #N/A | #N/A | 22
| 18 | R3MP-54197 | 2021-06-14 | 2021-06-28 | 2021-07-12 | 2021-07-26 |  | 2021-06-23 |  |  | -6343.3 | 0 | 0 | 0 | 0 | 4 | 5 | 12 | 0 | 0 | 2 | 89% | 0 | 3 | 4 | 0 | 0 | 0 | 96% | 11 | 11 | 5 | 29 | #N/A | #N/A | #N/A | 22
| 19 | R3MP-54195 | 2021-07-26 | 2021-08-09 | 2021-08-23 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 20 | R3MP-54194 | 2021-07-26 | 2021-08-09 | 2021-08-23 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 1 | R4DT-55621 | 2021-04-12 | 2021-04-26 | 2021-07-26 | 2021-08-09 |  | 2021-04-20 |  |  | -6345.3 | 0 | 0 | 0 | 0 | 42 | 6 | 10 | 3 | 1 | 1 | 70% | 2 | 1 | 1 | 0 | 0 | 0 | 98% | 66 | 11 | 5 | 75 | #N/A | #N/A | #N/A | 77
| 2 | R4DT-55622 | 2021-04-26 | 2021-05-10 | 2021-06-07 | 2021-06-28 |  | 2021-05-07 | 2021-06-18 | 2021-07-02 | 0.6 | 0 | 1 | 0 | 0 | 8 | 1 | 5 | 0 | 1 | 0 | 92% | 5 | 1 | 3 | 0 | 0 | 0 | 95% | 21 | 16 | 5 | #N/A | #N/A | 31 | 11 | 37
| 1 | K3VF-54405 | 2021-05-03 | 2021-05-17 | 2021-06-14 | 2021-08-09 |  | 2021-05-24 |  |  | -6345.3 | 0 | 0 | 0 | 0 | 46 | 49 | 35 | 0 | 3 | 9 | 28% | 13 | 46 | 17 | 80 | 16 | 4 | 42% | 21 | 41 | 5 | 51 | #N/A | #N/A | #N/A | 62
| 2 | K3VF-54404 | 2021-05-10 | 2021-05-24 | 2021-06-21 | 2021-08-16 |  | 2021-06-16 |  |  | -6346.3 | 0 | 0 | 0 | 0 | 31 | 49 | 35 | 0 | 3 | 7 | 36% | 12 | 25 | 13 | 78 | 7 | 4 | 55% | 21 | 41 | 5 | 34 | #N/A | #N/A | #N/A | 62
| 3 | K3VF-54406 | 2021-05-10 | 2021-05-24 | 2021-06-21 | 2021-08-16 |  | 2021-06-25 |  |  | -6346.3 | 0 | 0 | 0 | 0 | 31 | 49 | 35 | 0 | 3 | 7 | 36% | 12 | 25 | 13 | 78 | 7 | 4 | 55% | 21 | 41 | 5 | 27 | #N/A | #N/A | #N/A | 62
| 4 | K3VF-54416 | 2021-05-17 | 2021-05-31 | 2021-06-28 | 2021-08-23 |  | 2021-06-23 |  |  | -6347.3 | 0 | 0 | 0 | 0 | 13 | 46 | 17 | 80 | 16 | 4 | 42% | 12 | 25 | 9 | 72 | 6 | 3 | 59% | 21 | 41 | 5 | 29 | #N/A | #N/A | #N/A | 62
| 5 | K3VF-54418 | 2021-05-17 | 2021-05-31 | 2021-06-28 | 2021-08-23 |  |  |  |  | -6347.3 | 0 | 0 | 0 | 0 | 13 | 46 | 18 | 80 | 16 | 5 | 41% | 12 | 25 | 10 | 72 | 6 | 4 | 58% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 6 | K3VF-54397 | 2021-05-24 | 2021-06-07 | 2021-07-05 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | 15 | 25 | 14 | 78 | 7 | 4 | 53% | 12 | 21 | 5 | 64 | 9 | 4 | 65% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 7 | K3VF-54398 | 2021-05-24 | 2021-06-07 | 2021-07-05 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | 16 | 25 | 14 | 78 | 7 | 6 | 52% | 12 | 21 | 5 | 64 | 9 | 5 | 64% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 8 | K3VF-54394 | 2021-05-31 | 2021-06-14 | 2021-07-12 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | 16 | 25 | 10 | 73 | 6 | 5 | 56% | 8 | 20 | 2 | 55 | 7 | 2 | 71% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 9 | K3VF-54395 | 2021-05-31 | 2021-06-14 | 2021-07-12 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | 16 | 25 | 10 | 73 | 6 | 5 | 56% | 8 | 20 | 2 | 55 | 7 | 1 | 72% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 10 | K3VF-54396 | 2021-06-07 | 2021-06-21 | 2021-07-19 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | 12 | 21 | 5 | 65 | 9 | 4 | 64% | 8 | 20 | 2 | 22 | 7 | 1 | 82% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 11 | K3VF-54402 | 2021-06-07 | 2021-06-21 | 2021-07-19 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | 12 | 21 | 5 | 65 | 9 | 4 | 64% | 8 | 20 | 2 | 25 | 7 | 3 | 80% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 12 | K3VF-54403 | 2021-06-14 | 2021-06-28 | 2021-07-26 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | 12 | 20 | 2 | 57 | 8 | 4 | 69% | 6 | 20 | 4 | 18 | 8 | 3 | 81% | 21 | 36 | 5 | #N/A | #N/A | #N/A | #N/A | 57
| 13 | K3VF-54399 | 2021-06-14 | 2021-06-28 | 2021-07-26 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | 10 | 20 | 2 | 57 | 8 | 3 | 70% | 6 | 20 | 4 | 18 | 8 | 4 | 81% | 21 | 41 | 5 | #N/A | #N/A | #N/A | #N/A | 62
| 14 | K3VF-54400 | 2021-06-21 | 2021-07-05 | 2021-08-02 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | 9 | 20 | 3 | 25 | 7 | 4 | 79% | 5 | 18 | 4 | 9 | 3 | 3 | 87% | 21 | 36 | 5 | #N/A | #N/A | #N/A | #N/A | 57
| 15 | K3VF-54401 | 2021-06-21 | 2021-07-05 | 2021-08-02 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | 9 | 20 | 3 | 25 | 7 | 5 | 79% | 5 | 18 | 4 | 9 | 3 | 5 | 87% | 21 | 36 | 5 | #N/A | #N/A | #N/A | #N/A | 57
| 16 | K3VF-54411 | 2021-06-28 | 2021-07-12 | 2021-08-09 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | 7 | 20 | 4 | 21 | 8 | 7 | 80% | 5 | 16 | 2 | 7 | 3 | 5 | 88% | 21 | 36 | 5 | #N/A | #N/A | #N/A | #N/A | 57
| 17 | K3VF-54412 | 2021-06-28 | 2021-07-12 | 2021-08-09 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | 8 | 20 | 4 | 21 | 8 | 7 | 80% | 6 | 17 | 2 | 7 | 3 | 5 | 88% | 21 | 36 | 5 | #N/A | #N/A | #N/A | #N/A | 57
| 18 | K3VF-54417 | 2021-07-05 | 2021-07-19 | 2021-08-16 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | 7 | 19 | 4 | 10 | 3 | 7 | 85% | [7 empty] | 21 | 31 | 5 | #N/A | #N/A | #N/A | #N/A | 52
| 19 | K3VF-54419 | 2021-07-05 | 2021-07-19 | 2021-08-16 | 2021-10-04 |  |  |  |  | -6353.3 | 0 | 0 | 0 | 0 | 8 | 19 | 5 | 11 | 3 | 7 | 84% | [7 empty] | 21 | 36 | 5 | #N/A | #N/A | #N/A | #N/A | 57
| 20 | K3VF-54410 | 2021-07-12 | 2021-07-26 | 2021-08-23 | 2021-10-04 |  |  |  |  | -6353.3 | 0 | 0 | 0 | 0 | 7 | 17 | 4 | 9 | 3 | 6 | 86% | [7 empty] | 21 | 31 | 5 | #N/A | #N/A | #N/A | #N/A | 52
| 21 | K3VF-54413 | 2021-07-12 | 2021-07-26 | 2021-08-23 | 2021-10-04 |  |  |  |  | -6353.3 | 0 | 0 | 0 | 0 | 7 | 17 | 5 | 11 | 3 | 5 | 86% | [7 empty] | 21 | 31 | 5 | #N/A | #N/A | #N/A | #N/A | 52
| 22 | K3VF-54407 | 2021-07-19 | 2021-08-02 | 2021-08-30 | 2021-10-11 |  |  |  |  | -6354.3 | 0 | 0 | 0 | 0 | [14 empty] | 21 | 31 | 5 | #N/A | #N/A | #N/A | #N/A | 52
| 23 | K3VF-54408 | 2021-07-19 | 2021-08-02 | 2021-08-30 | 2021-10-11 |  |  |  |  | -6354.3 | 0 | 0 | 0 | 0 | [14 empty] | 21 | 31 | 5 | #N/A | #N/A | #N/A | #N/A | 52
| 24 | K3VF-54409 | 2021-07-26 | 2021-08-09 | 2021-09-06 | 2021-10-11 |  |  |  |  | -6354.3 | 0 | 0 | 0 | 0 | [14 empty] | 21 | 26 | 5 | #N/A | #N/A | #N/A | #N/A | 47
| 1 | R4DT-55602 | 2021-03-22 | 2021-04-05 | 2021-04-26 | 2021-05-03 |  | 2021-04-06 | 2021-04-30 | 2021-05-26 | 3.3 | 0 | 0 | 0 | 1 | 3 | 4 | 2 | 8 | 6 | 2 | 73% | 0 | 0 | 1 | 7 | 2 | 0 | 89% | 16 | 6 | 5 | #N/A | #N/A | 19 | 19 | 22
| 2 | R4DT-55492 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-05-17 |  | 2021-04-20 | 2021-05-04 | 2021-05-26 | 1.3 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 8 | 8 | 1 | 79% | 0 | 3 | 1 | 2 | 2 | 1 | 91% | 16 | 6 | 5 | #N/A | #N/A | 11 | 17 | 22
| 3 | R4DT-55490 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-05-17 |  | 2021-04-14 | 2021-05-04 | 2021-05-26 | 1.3 | 0 | 0 | 1 | 0 | 0 | 2 | 3 | 8 | 8 | 1 | 79% | 0 | 3 | 1 | 2 | 2 | 1 | 91% | 16 | 6 | 5 | #N/A | #N/A | 15 | 17 | 22
| 4 | R4DT-55493 | 2021-04-12 | 2021-04-26 | 2021-05-17 | 2021-05-24 |  | 2021-04-28 | 2021-05-26 | 2021-05-26 | 0.3 | 0 | 1 | 0 | 0 | 1 | 1 | 2 | 8 | 4 | 2 | 82% | 0 | 3 | 1 | 0 | 2 | 1 | 93% | 16 | 6 | 5 | #N/A | #N/A | 21 | 1 | 22
| 5 | R4DT-55568 | 2021-04-12 | 2021-04-26 | 2021-05-17 | 2021-07-19 |  | 2021-04-28 | 2021-06-10 |  | -6342.3 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 8 | 4 | 6 | 76% | 5 | 6 | 13 | 0 | 0 | 3 | 88% | 16 | 46 | 5 | #N/A | 38 | 32 | #N/A | 62
| 6 | R4DT-55571 | 2021-04-19 | 2021-05-03 | 2021-05-24 | 2021-07-19 |  | 2021-05-04 | 2021-06-15 |  | -6342.3 | 0 | 0 | 0 | 0 | 11 | 7 | 21 | 7 | 5 | 4 | 77% | 0 | 0 | 2 | 3 | 1 | 0 | 97% | 16 | 41 | 5 | #N/A | 35 | 31 | #N/A | 57
| 7 | R4DT-55570 | 2021-04-19 | 2021-05-03 | 2021-05-24 | 2021-07-26 |  | 2021-05-05 | 2021-06-15 |  | -6343.3 | 0 | 0 | 0 | 0 | 11 | 9 | 25 | 7 | 5 | 6 | 73% | 0 | 0 | 2 | 3 | 1 | 0 | 97% | 16 | 46 | 5 | #N/A | 35 | 30 | #N/A | 62
| 8 | R4DT-55494 | 2021-04-19 | 2021-05-03 | 2021-05-24 | 2021-07-26 |  | 2021-05-06 | 2021-06-15 |  | -6343.3 | 0 | 0 | 0 | 0 | 9 | 10 | 25 | 7 | 5 | 6 | 72% | 0 | 0 | 0 | 2 | 0 | 0 | 99% | 16 | 46 | 5 | #N/A | 35 | 29 | #N/A | 62
| 9 | R4DT-55567 | 2021-04-26 | 2021-05-10 | 2021-05-31 | 2021-08-02 |  | 2021-05-11 | 2021-06-25 |  | -6344.3 | 0 | 0 | 0 | 0 | 7 | 8 | 20 | 5 | 4 | 5 | 80% | 0 | 1 | 1 | 3 | 0 | 0 | 97% | 16 | 46 | 5 | #N/A | 27 | 34 | #N/A | 62
| 10 | R4DT-55562 | 2021-04-26 | 2021-05-10 | 2021-05-31 | 2021-08-02 |  | 2021-05-27 | 2021-07-07 |  | -6344.3 | 0 | 0 | 0 | 0 | 11 | 8 | 20 | 5 | 4 | 5 | 77% | 0 | 1 | 1 | 5 | 0 | 0 | 97% | 16 | 46 | 5 | #N/A | 19 | 30 | #N/A | 62
| 11 | R4DT-55488 | 2021-04-26 | 2021-05-10 | 2021-05-31 | 2021-08-09 |  | 2021-06-16 | 2021-07-07 |  | -6345.3 | 0 | 0 | 0 | 0 | 11 | 7 | 20 | 5 | 4 | 5 | 77% | 0 | 1 | 1 | 5 | 0 | 1 | 96% | 16 | 51 | 5 | #N/A | 19 | 16 | #N/A | 67
| 12 | R4DT-55569 | 2021-05-03 | 2021-05-17 | 2021-06-07 | 2021-08-09 |  | 2021-06-11 |  |  | -6345.3 | 0 | 0 | 0 | 0 | 1 | 4 | 5 | 8 | 1 | 1 | 92% | 0 | 1 | 1 | 5 | 0 | 1 | 96% | 16 | 46 | 5 | 37 | #N/A | #N/A | #N/A | 62
| 13 | R4DT-55563 | 2021-05-03 | 2021-05-17 | 2021-06-07 | 2021-08-16 |  | 2021-06-18 |  |  | -6346.3 | 0 | 0 | 0 | 0 | 1 | 6 | 7 | 8 | 1 | 2 | 90% | 0 | 2 | 1 | 5 | 0 | 1 | 96% | 16 | 51 | 5 | 32 | #N/A | #N/A | #N/A | 67
| 14 | R4DT-55566 | 2021-05-03 | 2021-05-17 | 2021-06-07 | 2021-08-16 |  | 2021-06-25 |  |  | -6346.3 | 0 | 0 | 0 | 0 | 1 | 5 | 7 | 8 | 1 | 3 | 89% | 0 | 2 | 1 | 5 | 0 | 1 | 96% | 16 | 51 | 5 | 27 | #N/A | #N/A | #N/A | 67
| 15 | R4DT-55564 | 2021-05-10 | 2021-05-24 | 2021-06-14 | 2021-08-23 |  | 2021-06-29 |  |  | -6347.3 | 0 | 0 | 0 | 0 | 2 | 5 | 8 | 8 | 1 | 3 | 89% | 0 | 2 | 1 | 5 | 0 | 2 | 96% | 16 | 51 | 5 | 25 | #N/A | #N/A | #N/A | 67
| 16 | R4DT-55565 | 2021-05-10 | 2021-05-24 | 2021-06-14 | 2021-08-23 |  | 2021-07-07 |  |  | -6347.3 | 0 | 0 | 0 | 0 | 2 | 6 | 8 | 8 | 1 | 2 | 89% | 0 | 3 | 1 | 5 | 0 | 2 | 95% | 16 | 51 | 5 | 19 | #N/A | #N/A | #N/A | 67
| 1 | R4DT-55581 | 2021-05-31 | 2021-06-14 | 2021-07-05 | 2021-07-12 |  | 2021-06-10 | 2021-06-21 |  | -6341.3 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 5 | 1 | 3 | 79% | 0 | 4 | 0 | 4 | 1 | 1 | 91% | 16 | 6 | 5 | #N/A | 31 | 8 | #N/A | 22
| 2 | R4DT-55580 | 2021-06-14 | 2021-06-28 | 2021-07-19 | 2021-07-26 |  | 2021-06-15 | 2021-06-24 |  | -6343.3 | 0 | 0 | 0 | 0 | 2 | 7 | 14 | 5 | 1 | 1 | 85% | 0 | 0 | 0 | 0 | 0 | 1 | 98% | 16 | 6 | 5 | #N/A | 28 | 8 | #N/A | 22
| 3 | R4DT-55575 | 2021-06-14 | 2021-06-28 | 2021-07-19 | 2021-07-26 |  | 2021-06-21 | 2021-06-27 |  | -6343.3 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 1 | 3 | 77% | 0 | 2 | 1 | 1 | 1 | 1 | 97% | 16 | 6 | 5 | #N/A | 26 | 5 | #N/A | 22
| 4 | R4DT-55593 | 2021-06-21 | 2021-07-05 | 2021-07-26 | 2021-08-02 |  | 2021-06-24 | 2021-06-30 |  | -6344.3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 95% | 2 | 2 | 3 | 0 | 0 | 2 | 96% | 16 | 6 | 5 | #N/A | 24 | 5 | #N/A | 22
| 5 | R4DT-55586 | 2021-06-21 | 2021-07-05 | 2021-07-26 | 2021-08-02 |  | 2021-06-29 |  |  | -6344.3 | 0 | 0 | 0 | 0 | 1 | 3 | 6 | 1 | 0 | 3 | 94% | 0 | 1 | 0 | 0 | 0 | 0 | 99% | 16 | 6 | 5 | 25 | #N/A | #N/A | #N/A | 22
| 6 | R4DT-55573 | 2021-06-28 | 2021-07-12 | 2021-08-02 | 2021-08-09 |  | 2021-07-02 |  |  | -6345.3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 96% | 0 | 1 | 0 | 0 | 0 | 0 | 99% | 16 | 6 | 5 | 22 | #N/A | #N/A | #N/A | 22
| 7 | R4DT-55598 | 2021-06-28 | 2021-07-12 | 2021-08-02 | 2021-08-09 |  | 2021-07-06 |  |  | -6345.3 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 1 | 0 | 2 | 95% | 0 | 2 | 1 | 0 | 0 | 0 | 98% | 16 | 6 | 5 | 20 | #N/A | #N/A | #N/A | 22
| 8 | R4DT-55596 | 2021-07-05 | 2021-07-19 | 2021-08-09 | 2021-08-16 |  | 2021-07-12 |  |  | -6346.3 | 0 | 0 | 0 | 0 | 4 | 4 | 3 | 1 | 1 | 2 | 93% | 0 | 0 | 0 | 0 | 0 | 1 | 99% | 16 | 6 | 5 | 16 | #N/A | #N/A | #N/A | 22
| 9 | R4DT-55594 | 2021-07-05 | 2021-07-19 | 2021-08-09 | 2021-08-16 |  |  |  |  | -6346.3 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 1 | 96% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 10 | R4DT-55595 | 2021-07-12 | 2021-07-26 | 2021-08-16 | 2021-08-23 |  |  |  |  | -6347.3 | 0 | 0 | 0 | 0 | 2 | 3 | 4 | 0 | 0 | 2 | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 11 | R4DT-55601 | 2021-07-12 | 2021-07-26 | 2021-08-16 | 2021-08-23 |  |  |  |  | -6347.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 12 | R4DT-55579 | 2021-07-12 | 2021-07-26 | 2021-08-16 | 2021-08-23 |  |  |  |  | -6347.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 13 | R4DT-55587 | 2021-07-19 | 2021-08-02 | 2021-08-23 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 14 | R4DT-55584 | 2021-07-19 | 2021-08-02 | 2021-08-23 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 15 | R4DT-55592 | 2021-07-19 | 2021-08-02 | 2021-08-23 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 16 | R4DT-55585 | 2021-07-26 | 2021-08-09 | 2021-08-30 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 17 | R4DT-55574 | 2021-07-26 | 2021-08-09 | 2021-08-30 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 18 | R4DT-55578 | 2021-08-02 | 2021-08-16 | 2021-09-06 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 19 | R4DT-55589 | 2021-08-02 | 2021-08-16 | 2021-09-06 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 20 | R4DT-55572 | 2021-08-02 | 2021-08-16 | 2021-09-06 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 21 | R4DT-55588 | 2021-08-09 | 2021-08-23 | 2021-09-13 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 22 | R4DT-55489 | 2021-08-09 | 2021-08-23 | 2021-09-13 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 23 | R4DT-55577 | 2021-08-16 | 2021-08-30 | 2021-09-20 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 24 | R4DT-55590 | 2021-08-16 | 2021-08-30 | 2021-09-20 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 25 | R4DT-55591 | 2021-08-16 | 2021-08-30 | 2021-09-20 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 26 | R4DT-55583 | 2021-08-16 | 2021-08-30 | 2021-09-20 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 1 | R3MP-54314 | 2021-06-21 | 2021-07-05 | 2021-07-19 | 2021-08-02 |  |  |  |  | -6344.3 | 0 | 0 | 0 | 0 | 7 | 3 | 11 | 1 | 2 | 4 | 87% | 8 | 3 | 9 | 0 | 1 | 3 | 89% | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 2 | R3MP-54369 | 2021-06-21 | 2021-07-05 | 2021-07-19 | 2021-08-02 |  |  |  |  | -6344.3 | 0 | 0 | 0 | 0 | 7 | 3 | 11 | 1 | 2 | 4 | 87% | 8 | 3 | 10 | 0 | 1 | 3 | 89% | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 3 | R3MP-54317 | 2021-06-21 | 2021-07-05 | 2021-07-19 | 2021-08-02 |  |  |  |  | -6344.3 | 0 | 0 | 0 | 0 | 7 | 3 | 11 | 1 | 2 | 4 | 87% | 7 | 3 | 11 | 0 | 1 | 3 | 89% | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 4 | R3MP-54372 | 2021-06-21 | 2021-07-05 | 2021-07-19 | 2021-08-02 |  |  |  |  | -6344.3 | 0 | 0 | 0 | 0 | 7 | 3 | 13 | 1 | 2 | 4 | 86% | 8 | 3 | 15 | 0 | 1 | 3 | 87% | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 5 | R3MP-54320 | 2021-06-28 | 2021-07-12 | 2021-07-26 | 2021-08-09 |  |  |  |  | -6345.3 | 0 | 0 | 0 | 0 | 7 | 3 | 16 | 1 | 1 | 3 | 86% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 6 | R3MP-54321 | 2021-06-28 | 2021-07-12 | 2021-07-26 | 2021-08-09 |  |  |  |  | -6345.3 | 0 | 0 | 0 | 0 | 10 | 3 | 17 | 1 | 1 | 3 | 84% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 7 | R3MP-54322 | 2021-06-28 | 2021-07-12 | 2021-07-26 | 2021-08-09 |  |  |  |  | -6345.3 | 0 | 0 | 0 | 0 | 10 | 5 | 17 | 2 | 1 | 4 | 82% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 8 | R3MP-54318 | 2021-06-28 | 2021-07-12 | 2021-07-26 | 2021-08-09 |  |  |  |  | -6345.3 | 0 | 0 | 0 | 0 | 10 | 5 | 17 | 2 | 1 | 4 | 82% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 9 | R3MP-54323 | 2021-07-05 | 2021-07-19 | 2021-08-02 | 2021-08-16 |  |  |  |  | -6346.3 | 0 | 0 | 0 | 0 | 10 | 5 | 16 | 0 | 1 | 5 | 83% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 10 | R3MP-54324 | 2021-07-05 | 2021-07-19 | 2021-08-02 | 2021-08-16 |  |  |  |  | -6346.3 | 0 | 0 | 0 | 0 | 9 | 5 | 16 | 0 | 1 | 6 | 83% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 11 | R3MP-54325 | 2021-07-05 | 2021-07-19 | 2021-08-02 | 2021-08-16 |  |  |  |  | -6346.3 | 0 | 0 | 0 | 0 | 11 | 5 | 17 | 0 | 1 | 8 | 81% | [7 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 12 | R3MP-54375 | 2021-07-12 | 2021-07-26 | 2021-08-09 | 2021-08-23 |  |  |  |  | -6347.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 13 | R3MP-54327 | 2021-07-12 | 2021-07-26 | 2021-08-09 | 2021-08-23 |  |  |  |  | -6347.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 14 | R3MP-54368 | 2021-07-19 | 2021-08-02 | 2021-08-16 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 15 | R3MP-54370 | 2021-07-19 | 2021-08-02 | 2021-08-16 | 2021-08-30 |  |  |  |  | -6348.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 16 | R3MP-54371 | 2021-08-02 | 2021-08-16 | 2021-08-30 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 17 | R3MP-54373 | 2021-08-02 | 2021-08-16 | 2021-08-30 | 2021-09-13 |  |  |  |  | -6350.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 18 | R3MP-54374 | 2021-08-09 | 2021-08-23 | 2021-09-06 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 19 | R3MP-54326 | 2021-08-09 | 2021-08-23 | 2021-09-06 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 20 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 5 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 6 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 7 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 8 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 9 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 10 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 11 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 12 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 13 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 14 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 15 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 16 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 17 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 18 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 19 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 20 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | K3WS-54828 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | K3WS-54809 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | K3WS-54815 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | K3WS-54823 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 5 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 6 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 7 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 8 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 9 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 10 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 11 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 12 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 13 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 14 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 15 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 16 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 17 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 18 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 19 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 20 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | K3WS-54828 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | K3WS-54809 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | K3WS-54815 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | K3WS-54828 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | K3WS-54809 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | K3WS-54815 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | K3WS-54823 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | K3WS-54828 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | K3WS-54809 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | K3WS-54815 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | K3WS-54823 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | K3WS-54828 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | K3WS-54809 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | K3WS-54815 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | K3WS-54823 | [8 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | R4DT-P1288 | 2021-10-11 | 2021-10-25 | 2021-11-08 | 2021-11-22 |  |  |  |  | -6360.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 2 | R4DT-P1289 | 2021-10-25 | 2021-11-08 | 2021-11-22 | 2021-12-06 |  |  |  |  | -6362.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 3 | R4DT-P1251 | 2021-10-25 | 2021-11-08 | 2021-11-22 | 2021-12-06 |  |  |  |  | -6362.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 4 | R4DT-P1183 | 2021-11-01 | 2021-11-15 | 2021-11-29 | 2021-12-13 |  |  |  |  | -6363.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 5 | R4DT-P1341 | 2021-11-01 | 2021-11-15 | 2021-11-29 | 2021-12-13 |  |  |  |  | -6363.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 6 | R4DT-P1152 | 2021-11-01 | 2021-11-15 | 2021-11-29 | 2021-12-13 |  |  |  |  | -6363.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 7 | R4DT-P1319 | 2021-11-08 | 2021-11-22 | 2021-12-06 | 2021-12-20 |  |  |  |  | -6364.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 8 | R4DT-P1347 | 2021-11-08 | 2021-11-22 | 2021-12-06 | 2021-12-20 |  |  |  |  | -6364.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 9 | R4DT-P1346 | 2021-11-08 | 2021-11-22 | 2021-12-06 | 2021-12-20 |  |  |  |  | -6364.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 10 | R4DT-P1344 | 2021-11-08 | 2021-11-22 | 2021-12-06 | 2021-12-20 |  |  |  |  | -6364.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 11 | R4DT-P1345 | 2021-11-15 | 2021-11-29 | 2021-12-13 | 2022-01-03 |  |  |  |  | -6366.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 12 | R4DT-P1329 | 2021-11-15 | 2021-11-29 | 2021-12-13 | 2022-01-03 |  |  |  |  | -6366.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 13 | R4DT-P1253 | 2021-11-15 | 2021-11-29 | 2021-12-13 | 2022-01-03 |  |  |  |  | -6366.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 14 | R4DT-P1255 | 2021-11-15 | 2021-11-29 | 2021-12-13 | 2022-01-03 |  |  |  |  | -6366.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 15 | R4DT-P1332 | 2021-11-15 | 2021-11-29 | 2021-12-13 | 2022-01-03 |  |  |  |  | -6366.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 16 | R4DT-P1176 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-10 |  |  |  |  | -6367.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 17 | R4DT-P1354 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-10 |  |  |  |  | -6367.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 18 | R4DT-P1165 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-10 |  |  |  |  | -6367.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 19 | R4DT-P1257 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-10 |  |  |  |  | -6367.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 20 | R4DT-P1258 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-10 |  |  |  |  | -6367.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 21 | R4DT-P1261 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-10 |  |  |  |  | -6367.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 22 | R4DT-P1177 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-17 |  |  |  |  | -6368.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 23 | R4DT-P1184 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-17 |  |  |  |  | -6368.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 24 | R4DT-P1323 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-17 |  |  |  |  | -6368.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 25 | R4DT-P1166 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-17 |  |  |  |  | -6368.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 26 | R4DT-P1153 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-17 |  |  |  |  | -6368.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 27 | R4DT-P1248 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 32
| 28 | R4DT-P1240 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 32
| 29 | R4DT-P1189 | 2021-11-29 | 2021-12-13 | 2022-01-03 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 16 | 5 | #N/A | #N/A | #N/A | #N/A | 32
| 30 | R4DT-P1193 | 2021-12-06 | 2021-12-20 | 2022-01-10 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 31 | R4DT-P1196 | 2021-12-06 | 2021-12-20 | 2022-01-10 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 32 | R4DT-P1217 | 2021-12-06 | 2021-12-20 | 2022-01-10 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 33 | R4DT-P1167 | 2021-12-06 | 2021-12-20 | 2022-01-10 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 34 | R4DT-P1172 | 2021-12-06 | 2021-12-20 | 2022-01-10 | 2022-01-24 |  |  |  |  | -6369.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 27
| 35 | R4DT-P1178 | 2021-12-20 | 2022-01-03 | 2022-01-17 | 2022-01-31 |  |  |  |  | -6370.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 36 | R4DT-P1160 | 2021-12-20 | 2022-01-03 | 2022-01-17 | 2022-01-31 |  |  |  |  | -6370.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 37 | R4DT-P1181 | 2021-12-20 | 2022-01-03 | 2022-01-17 | 2022-01-31 |  |  |  |  | -6370.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 38 | R4DT-P1199 | 2021-12-20 | 2022-01-03 | 2022-01-17 | 2022-01-31 |  |  |  |  | -6370.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 39 | R4DT-P1210 | 2021-12-20 | 2022-01-03 | 2022-01-17 | 2022-01-31 |  |  |  |  | -6370.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 40 | R4DT-P1185 | 2021-12-20 | 2022-01-03 | 2022-01-17 | 2022-01-31 |  |  |  |  | -6370.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 41 | R4DT-P1161 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 42 | R4DT-P1244 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 43 | R4DT-P1343 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 44 | R4DT-P1194 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 45 | R4DT-P1219 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 46 | R4DT-P1168 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 47 | R4DT-P1173 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 48 | R4DT-P1170 | 2021-12-27 | 2022-01-10 | 2022-01-24 | 2022-02-07 |  |  |  |  | -6371.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 49 | R4DT-P1162 | 2022-01-03 | 2022-01-17 | 2022-01-31 | 2022-02-14 |  |  |  |  | -6372.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 50 | R4DT-P1182 | 2022-01-03 | 2022-01-17 | 2022-01-31 | 2022-02-14 |  |  |  |  | -6372.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 51 | R4DT-P1245 | 2022-01-03 | 2022-01-17 | 2022-01-31 | 2022-02-14 |  |  |  |  | -6372.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 52 | R4DT-P1327 | 2022-01-03 | 2022-01-17 | 2022-01-31 | 2022-02-14 |  |  |  |  | -6372.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 53 | R4DT-P1211 | 2022-01-03 | 2022-01-17 | 2022-01-31 | 2022-02-14 |  |  |  |  | -6372.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 54 | R4DT-P1233 | 2022-01-03 | 2022-01-17 | 2022-01-31 | 2022-02-14 |  |  |  |  | -6372.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 55 | R4DT-P1254 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 56 | R4DT-P1256 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 57 | R4DT-P1399 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 58 | R4DT-P1212 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 59 | R4DT-P1190 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 60 | R4DT-P1154 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 61 | R4DT-P1175 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 62 | R4DT-P1171 | 2022-01-10 | 2022-01-24 | 2022-02-07 | 2022-02-21 |  |  |  |  | -6373.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 63 | R4DT-P1252 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 64 | R4DT-P1259 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 65 | R4DT-P1260 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 66 | R4DT-P1314 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 67 | R4DT-P1223 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 68 | R4DT-P1204 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 69 | R4DT-P1169 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 70 | R4DT-P1186 | 2022-01-17 | 2022-01-31 | 2022-02-14 | 2022-02-28 |  |  |  |  | -6374.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 71 | R4DT-P1312 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 72 | R4DT-P1353 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 73 | R4DT-P1317 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 74 | R4DT-P1195 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 75 | R4DT-P1235 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 76 | R4DT-P1191 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 77 | R4DT-P1174 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 78 | R4DT-P1320 | 2022-01-24 | 2022-02-07 | 2022-02-21 | 2022-03-07 |  |  |  |  | -6375.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 79 | R4DT-P1316 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 80 | R4DT-P1328 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 81 | R4DT-P1355 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 82 | R4DT-P1352 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 83 | R4DT-P1224 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 84 | R4DT-P1205 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 85 | R4DT-P1203 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 86 | R4DT-P1231 | 2022-01-31 | 2022-02-14 | 2022-02-28 | 2022-03-14 |  |  |  |  | -6376.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 87 | R4DT-P1313 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 88 | R4DT-P1334 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 89 | R4DT-P1350 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 90 | R4DT-P1351 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 91 | R4DT-P1192 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 92 | R4DT-P1322 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 93 | R4DT-P1232 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 94 | R4DT-P1216 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-21 |  |  |  |  | -6377.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 95 | R4DT-P1324 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 96 | R4DT-P1348 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 97 | R4DT-P1349 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 98 | R4DT-P1206 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 99 | R4DT-P1226 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 100 | R4DT-P1227 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 101 | R4DT-P1187 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 102 | R4DT-P1236 | 2022-02-14 | 2022-02-28 | 2022-03-14 | 2022-03-28 |  |  |  |  | -6378.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 103 | R4DT-P1228 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 104 | R4DT-P1218 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 105 | R4DT-P1200 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 106 | R4DT-P1225 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 107 | R4DT-P1237 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 108 | R4DT-P1213 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 109 | R4DT-P1208 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 110 | R4DT-P1336 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-04-04 |  |  |  |  | -6379.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 111 | R4DT-P1331 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 112 | R4DT-P1221 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 113 | R4DT-P1229 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 114 | R4DT-P1220 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 115 | R4DT-P1214 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 116 | R4DT-P1198 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 117 | R4DT-P1234 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 118 | R4DT-P1238 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-11 |  |  |  |  | -6380.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 119 | R4DT-P1287 | 2022-03-07 | 2022-03-21 | 2022-04-04 | 2022-04-18 |  |  |  |  | -6381.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 120 | R4DT-P1230 | 2022-03-07 | 2022-03-21 | 2022-04-04 | 2022-04-18 |  |  |  |  | -6381.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 121 | R4DT-P1209 | 2022-03-07 | 2022-03-21 | 2022-04-04 | 2022-04-18 |  |  |  |  | -6381.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 122 | R4DT-P1222 | 2022-03-07 | 2022-03-21 | 2022-04-04 | 2022-04-18 |  |  |  |  | -6381.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 123 | R4DT-P1400 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 124 | R4DT-P1311 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 125 | R4DT-P1318 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 126 | R4DT-P1188 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 127 | R4DT-P1201 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 128 | R4DT-P1202 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 129 | R4DT-P1215 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-25 |  |  |  |  | -6382.3 | 0 | 0 | 0 | 0 | [14 empty] | 11 | 11 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 1 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 5 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 6 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 7 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 8 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 9 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 10 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 11 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 12 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 13 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 14 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 15 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 16 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 5 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 6 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 7 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 8 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 9 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 2 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 3 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 4 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 5 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 6 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 7 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 8 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 9 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 10 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 11 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 12 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 13 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 14 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 15 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 16 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 17 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 18 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 19 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 20 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 21 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 22 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 23 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 24 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 25 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 26 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 27 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 28 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 29 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 30 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 31 | [9 empty] | 0 | 0 | 1 | 0 | 0 | [14 empty] | 0 | 0 | 5 | #N/A | #N/A | #N/A | #N/A | 0
| 1 | R5DJ-91896 | 2021-07-26 | 2021-08-09 | 2021-08-30 | 2021-09-06 |  |  |  |  | -6349.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 2 | R5DJ-91897 | 2021-08-09 | 2021-08-23 | 2021-09-13 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 3 | R5DJ-91898 | 2021-08-09 | 2021-08-23 | 2021-09-13 | 2021-09-20 |  |  |  |  | -6351.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 4 | R5DJ-91899 | 2021-08-16 | 2021-08-30 | 2021-09-20 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 5 | R5D2-54363 | 2021-08-16 | 2021-08-30 | 2021-09-20 | 2021-09-27 |  |  |  |  | -6352.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 6 | R5DD-54174 | 2021-08-23 | 2021-09-06 | 2021-09-27 | 2021-10-04 |  |  |  |  | -6353.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 7 | R5D2-54364 | 2021-08-23 | 2021-09-06 | 2021-09-27 | 2021-10-04 |  |  |  |  | -6353.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 8 | R5D2-54365 | 2021-08-30 | 2021-09-13 | 2021-10-04 | 2021-10-11 |  |  |  |  | -6354.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 9 | R5DP-64502 | 2021-08-30 | 2021-09-13 | 2021-10-04 | 2021-10-11 |  |  |  |  | -6354.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 10 | R5D2-54366 | 2021-09-06 | 2021-09-20 | 2021-10-11 | 2021-10-18 |  |  |  |  | -6355.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 11 | R5DP-64503 | 2021-09-06 | 2021-09-20 | 2021-10-11 | 2021-10-18 |  |  |  |  | -6355.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 12 | R5D2-54367 | 2021-09-13 | 2021-09-27 | 2021-10-18 | 2021-10-25 |  |  |  |  | -6356.3 | 0 | 0 | 0 | 0 | [14 empty] | 16 | 6 | 5 | #N/A | #N/A | #N/A | #N/A | 22
| 1 | K3WS-54828 | 2021-01-25 | 2021-02-08 | 2021-03-01 | 2021-03-22 | 2021-03-22 | 2021-02-11 | 2021-03-01 | 2021-03-26 | 0.6 | 0 | 1 | 0 | 0 | 28 | 9 | 31 | 46 | 96 | 9 | 79% | 14 | 2 | 7 | 21 | 38 | 1 | 92% | 16 | 16 | 5 | #N/A | #N/A | 13 | 20 | 32
| 2 | K3WS-54809 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-03-29 | 2021-02-23 | 2021-03-09 | 2021-04-09 | 1.6 | 0 | 0 | 1 | 0 | 15 | 4 | 7 | 22 | 41 | 1 | 91% | 1 | 4 | 4 | 17 | 20 | 2 | 95% | 11 | 16 | 5 | #N/A | #N/A | 11 | 24 | 27
| 3 | K3WS-54815 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-03-29 | 2021-02-25 | 2021-03-10 | 2021-04-14 | 2.3 | 0 | 0 | 0 | 1 | 13 | 8 | 8 | 28 | 39 | 2 | 90% | 2 | 4 | 2 | 16 | 9 | 1 | 96% | 11 | 16 | 5 | #N/A | #N/A | 10 | 26 | 27
| 4 | K3WS-54823 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-03-29 | 2021-02-26 | 2021-03-11 | 2021-04-16 | 2.6 | 0 | 0 | 0 | 1 | 18 | 2 | 13 | 30 | 44 | 2 | 89% | 2 | 6 | 3 | 16 | 11 | 5 | 95% | 11 | 16 | 5 | #N/A | #N/A | 10 | 27 | 27
| 5 | K3WS-54825 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-03-29 | 2021-03-03 | 2021-03-15 | 2021-04-09 | 1.6 | 0 | 0 | 1 | 0 | 14 | 10 | 10 | 30 | 48 | 4 | 88% | 3 | 7 | 3 | 18 | 12 | 7 | 95% | 11 | 16 | 5 | #N/A | #N/A | 9 | 20 | 27
| 6 | K3WS-54806 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-03-29 | 2021-03-04 | 2021-03-16 | 2021-04-16 | 2.6 | 0 | 0 | 0 | 1 | 19 | 3 | 14 | 34 | 57 | 4 | 87% | 4 | 2 | 6 | 14 | 17 | 3 | 95% | 11 | 16 | 5 | #N/A | #N/A | 9 | 24 | 27
| 7 | K3WS-54820 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-04-05 | 2021-04-05 | 2021-03-05 | 2021-03-29 | 2021-04-20 | 2.1 | 0 | 0 | 0 | 1 | 6 | 7 | 9 | 25 | 22 | 4 | 92% | 2 | 1 | 0 | 3 | 2 | 1 | 99% | 11 | 16 | 5 | #N/A | #N/A | 17 | 17 | 27
| 8 | K3WS-54805 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-04-05 | 2021-04-05 | 2021-03-08 | 2021-03-18 | 2021-04-26 | 3 | 0 | 0 | 0 | 1 | 11 | 2 | 9 | 24 | 27 | 2 | 92% | 2 | 1 | 1 | 0 | 5 | 0 | 99% | 11 | 16 | 5 | #N/A | #N/A | 9 | 28 | 27
| 9 | K3WS-54797 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-04-05 | 2021-04-05 | 2021-03-09 | 2021-03-19 | 2021-04-21 | 2.3 | 0 | 0 | 0 | 1 | 12 | 4 | 9 | 27 | 28 | 2 | 92% | 2 | 1 | 1 | 0 | 8 | 0 | 98% | 11 | 16 | 5 | #N/A | #N/A | 9 | 24 | 27
| 10 | K3WS-54804 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-04-05 | 2021-04-05 | 2021-03-11 | 2021-03-22 | 2021-04-22 | 2.4 | 0 | 0 | 0 | 1 | 13 | 4 | 11 | 27 | 28 | 2 | 91% | 2 | 1 | 0 | 0 | 8 | 0 | 98% | 11 | 16 | 5 | #N/A | #N/A | 8 | 24 | 27
| 11 | K3WS-54803 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-04-05 | 2021-04-12 | 2021-03-12 | 2021-03-23 | 2021-04-21 | 2.3 | 0 | 0 | 0 | 1 | 13 | 4 | 12 | 28 | 29 | 2 | 91% | 2 | 1 | 0 | 0 | 6 | 0 | 99% | 11 | 16 | 5 | #N/A | #N/A | 8 | 22 | 27
| 12 | K3WS-54830 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-04-12 | 2021-04-12 | 2021-03-16 | 2021-03-26 | 2021-04-22 | 1.4 | 0 | 0 | 1 | 0 | 10 | 8 | 10 | 25 | 24 | 3 | 92% | 2 | 1 | 0 | 3 | 6 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 9 | 20 | 27
| 13 | K3WS-54798 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-04-12 | 2021-04-19 | 2021-03-17 | 2021-04-07 | 2021-04-22 | 1.4 | 0 | 0 | 1 | 0 | 10 | 6 | 12 | 22 | 26 | 4 | 92% | 2 | 1 | 0 | 0 | 8 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 16 | 12 | 27
| 14 | K3WS-54799 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-04-12 | 2021-04-19 | 2021-03-17 | 2021-04-09 | 2021-04-28 | 2.3 | 0 | 0 | 0 | 1 | 10 | 6 | 13 | 25 | 27 | 5 | 91% | 2 | 2 | 1 | 0 | 11 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 18 | 14 | 27
| 15 | K3WS-54818 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-04-12 | 2021-04-19 | 2021-03-19 | 2021-04-06 | 2021-04-28 | 2.3 | 0 | 0 | 0 | 1 | 10 | 10 | 13 | 29 | 21 | 3 | 91% | 2 | 1 | 0 | 4 | 8 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 13 | 17 | 27
| 16 | K3WS-54821 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-04-19 | 2021-04-19 | 2021-03-22 | 2021-04-13 | 2021-04-28 | 1.3 | 0 | 0 | 1 | 0 | 2 | 1 | 5 | 5 | 13 | 1 | 97% | 2 | 0 | 0 | 0 | 1 | 0 | 99% | 11 | 16 | 5 | #N/A | #N/A | 17 | 12 | 27
| 17 | K3WS-54813 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-04-19 | 2021-04-19 | 2021-03-23 | 2021-04-14 | 2021-04-29 | 1.4 | 0 | 0 | 1 | 0 | 2 | 1 | 5 | 5 | 9 | 1 | 97% | 2 | 1 | 0 | 0 | 2 | 1 | 99% | 11 | 16 | 5 | #N/A | #N/A | 17 | 12 | 27
| 18 | K3WS-54827 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-04-19 | 2021-05-10 | 2021-03-24 | 2021-04-26 | 2021-05-03 | 2 | 0 | 0 | 1 | 0 | 4 | 2 | 5 | 3 | 15 | 2 | 97% | 3 | 1 | 2 | 0 | 7 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 24 | 6 | 27
| 19 | K3WS-54800 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-04-19 | 2021-04-26 | 2021-03-29 | 2021-04-19 | 2021-04-29 | 1.4 | 0 | 0 | 1 | 0 | 2 | 2 | 2 | 4 | 16 | 2 | 97% | 2 | 1 | 0 | 0 | 6 | 1 | 99% | 11 | 16 | 5 | #N/A | #N/A | 16 | 9 | 27
| 20 | K3WS-54816 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-26 | 2021-04-26 | 2021-03-31 | 2021-04-16 | 2021-04-28 | 0.3 | 0 | 1 | 0 | 0 | 2 | 2 | 5 | 7 | 11 | 2 | 97% | 2 | 1 | 0 | 0 | 2 | 2 | 99% | 11 | 16 | 5 | #N/A | #N/A | 13 | 9 | 27
| 21 | K3WS-54826 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-26 | 2021-04-26 | 2021-04-01 | 2021-04-20 | 2021-04-30 | 0.6 | 0 | 1 | 0 | 0 | 2 | 2 | 7 | 7 | 13 | 3 | 96% | 2 | 1 | 1 | 0 | 4 | 1 | 99% | 11 | 16 | 5 | #N/A | #N/A | 14 | 9 | 27
| 22 | K3WS-54819 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-26 | 2021-05-17 | 2021-04-07 | 2021-04-30 | 2021-05-07 | 1.6 | 0 | 0 | 1 | 0 | 2 | 3 | 7 | 7 | 13 | 2 | 96% | 2 | 2 | 1 | 0 | 3 | 1 | 99% | 11 | 16 | 5 | #N/A | #N/A | 18 | 6 | 27
| 23 | K3WS-54817 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-26 | 2021-05-31 | 2021-04-08 | 2021-04-21 | 2021-05-11 | 2.1 | 0 | 0 | 0 | 1 | 2 | 3 | 8 | 10 | 13 | 3 | 96% | 2 | 2 | 1 | 0 | 6 | 2 | 98% | 11 | 16 | 5 | #N/A | #N/A | 10 | 15 | 27
| 24 | K3WS-54810 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-05-03 | 2021-04-26 | 2021-04-09 | 2021-04-22 | 2021-04-30 | -0.4 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 8 | 1 | 98% | 2 | 2 | 2 | 1 | 8 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 10 | 7 | 27
| 25 | K3WS-54814 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-05-03 | 2021-05-31 | 2021-04-12 | 2021-04-23 | 2021-05-04 | 0.1 | 0 | 1 | 0 | 0 | 2 | 2 | 2 | 1 | 8 | 1 | 98% | 2 | 2 | 2 | 1 | 8 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 10 | 8 | 27
| 26 | K3WS-54808 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-05-03 | 2021-05-31 | 2021-04-14 | 2021-05-04 | 2021-05-11 | 1.1 | 0 | 0 | 1 | 0 | 2 | 2 | 1 | 1 | 11 | 1 | 98% | 2 | 2 | 1 | 1 | 11 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 15 | 6 | 27
| 27 | K3WS-54807 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-05-03 | 2021-06-07 | 2021-04-15 | 2021-04-28 | 2021-05-10 | 1 | 0 | 1 | 0 | 0 | 2 | 2 | 1 | 2 | 12 | 1 | 98% | 2 | 2 | 1 | 2 | 12 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 10 | 9 | 27
| 28 | K3WS-54811 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-06-07 | 2021-04-19 | 2021-04-29 | 2021-05-06 | -0.6 | 1 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 11 | 1 | 97% | 3 | 2 | 3 | 2 | 11 | 1 | 97% | 11 | 16 | 5 | #N/A | #N/A | 9 | 6 | 27
| 29 | K3WS-54812 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-06-07 | 2021-04-20 | 2021-05-04 | 2021-05-07 | -0.4 | 1 | 0 | 0 | 0 | 3 | 3 | 3 | 2 | 12 | 1 | 97% | 3 | 3 | 3 | 2 | 12 | 1 | 97% | 11 | 16 | 5 | #N/A | #N/A | 11 | 4 | 27
| 30 | K3WS-54822 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-06-07 | 2021-04-21 | 2021-05-05 | 2021-05-24 | 2 | 0 | 0 | 1 | 0 | 2 | 2 | 4 | 2 | 16 | 2 | 97% | 2 | 2 | 4 | 2 | 16 | 2 | 97% | 11 | 16 | 5 | #N/A | #N/A | 11 | 14 | 27
| 31 | K3WS-54824 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-06-14 | 2021-04-23 | 2021-05-06 | 2021-05-26 | 2.3 | 0 | 0 | 0 | 1 | 3 | 2 | 3 | 6 | 16 | 2 | 96% | 3 | 2 | 3 | 6 | 16 | 2 | 96% | 11 | 16 | 5 | #N/A | #N/A | 10 | 15 | 27
| 32 | K3WS-54801 | 2021-03-29 | 2021-04-12 | 2021-04-26 | 2021-05-17 | 2021-06-14 | 2021-04-26 | 2021-05-11 | 2021-05-27 | 1.4 | 0 | 0 | 1 | 0 | 2 | 4 | 1 | 3 | 16 | 3 | 97% | 1 | 1 | 0 | 1 | 5 | 0 | 99% | 11 | 16 | 5 | #N/A | #N/A | 12 | 13 | 27
| 33 | K3WS-54802 | 2021-03-29 | 2021-04-12 | 2021-04-26 | 2021-05-17 | 2021-06-14 | 2021-04-27 | 2021-05-12 | 2021-06-03 | 2.4 | 0 | 0 | 0 | 1 | 2 | 4 | 1 | 7 | 17 | 3 | 96% | 1 | 1 | 0 | 3 | 6 | 1 | 98% | 11 | 16 | 5 | #N/A | #N/A | 12 | 17 | 27
| 34 | K3WS-54835 | 2021-03-29 | 2021-04-12 | 2021-04-26 | 2021-05-17 | 2021-06-21 | 2021-04-29 | 2021-05-07 | 2021-05-07 | -1.4 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 6 | 14 | 0 | 95% | 0 | 0 | 0 | 1 | 4 | 0 | 98% | 11 | 16 | 5 | #N/A | #N/A | 7 | 1 | 27
| 35 | K3WS-54836 | 2021-04-05 | 2021-04-19 | 2021-05-03 | 2021-05-24 | 2021-06-21 | 2021-04-30 | 2021-05-12 | 2021-05-12 | -1.7 | 1 | 0 | 0 | 0 | 1 | 3 | 0 | 8 | 10 | 0 | 95% | 0 | 1 | 0 | 2 | 5 | 0 | 98% | 11 | 16 | 5 | #N/A | #N/A | 9 | 1 | 27
| 36 | K3WS-54829 | 2021-04-05 | 2021-04-19 | 2021-05-03 | 2021-05-24 | 2021-06-21 | 2021-05-04 | 2021-05-14 | 2021-05-26 | 0.3 | 0 | 1 | 0 | 0 | 8 | 5 | 4 | 7 | 19 | 3 | 95% | 1 | 1 | 0 | 1 | 7 | 0 | 99% | 11 | 16 | 5 | #N/A | #N/A | 9 | 9 | 27
| 37 | K3WS-55312 | 2021-05-10 | 2021-05-24 | 2021-06-07 | 2021-06-28 | 2021-06-28 | 2021-05-13 | 2021-06-04 | 2021-06-14 | -2 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 4 | 2 | 98% | 0 | 1 | 1 | 2 | 4 | 2 | 99% | 11 | 16 | 5 | #N/A | #N/A | 17 | 7 | 27
| 38 | K3WS-55313 | 2021-05-10 | 2021-05-24 | 2021-06-07 | 2021-06-28 | 2021-06-28 | 2021-05-14 | 2021-06-08 | 2021-06-15 | -1.9 | 1 | 0 | 0 | 0 | 2 | 1 | 3 | 2 | 4 | 3 | 98% | 0 | 1 | 3 | 2 | 4 | 2 | 98% | 11 | 16 | 5 | #N/A | #N/A | 18 | 6 | 27
| 39 | K3WS-55314 | 2021-05-10 | 2021-05-24 | 2021-06-07 | 2021-06-28 | 2021-06-28 | 2021-05-18 | 2021-06-09 | 2021-06-18 | -1.4 | 1 | 0 | 0 | 0 | 2 | 1 | 4 | 6 | 5 | 2 | 98% | 0 | 1 | 4 | 6 | 5 | 2 | 98% | 11 | 16 | 5 | #N/A | #N/A | 17 | 8 | 27
| 1 | 22JL-ML101 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-10 | 2021-03-16 | 2021-03-16 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 80% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 5 | 1 | 7
| 2 | 22JL-ML102 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-18 | 2021-03-23 | 2021-03-26 | 0.6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 4 | 7
| 3 | 22JL-ML103 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-10 | 2021-03-16 | 2021-03-16 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 80% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 5 | 1 | 7
| 4 | 22JL-ML104 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-10 | 2021-03-15 | 2021-03-16 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 80% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 4 | 2 | 7
| 5 | 22JL-ML105 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-10 | 2021-03-16 | 2021-03-24 | -0.7 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 5 | 7 | 7
| 6 | 22JL-ML106 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-10 | 2021-03-17 | 2021-03-17 | -1.7 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 7 | 22JL-ML107 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-10 | 2021-03-17 | 2021-03-18 | -1.6 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 6 | 2 | 7
| 8 | 22JL-ML108 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-11 | 2021-03-16 | 2021-03-19 | -1.4 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 4 | 4 | 7
| 9 | 22JL-ML109 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-18 | 2021-03-23 | 2021-03-24 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 2 | 7
| 10 | 22JL-ML110 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-11 | 2021-03-17 | 2021-03-17 | -1.7 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 5 | 1 | 7
| 11 | 22JL-ML111 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-12 | 2021-03-18 | 2021-03-18 | -1.6 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 5 | 1 | 7
| 12 | 22JL-ML112 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-12 | 2021-03-17 | 2021-03-17 | -1.7 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 2 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 4 | 1 | 7
| 13 | 22JL-ML113 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-15 | 2021-03-19 | 2021-03-19 | -2.4 | 1 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 82% | 7 | 0 | 0 | 0 | 0 | 0 | 82% | 6 | 1 | 5 | #N/A | #N/A | 5 | 1 | 7
| 14 | 22JL-ML114 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-16 | 2021-03-19 | 2021-03-24 | -1.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 4 | 4 | 7
| 15 | 22JL-ML115 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-24 | 2021-03-26 | 2021-03-26 | -1.4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 16 | 22JL-ML116 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-24 | 2021-03-30 | 2021-03-31 | -0.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 6 | 1 | 5 | #N/A | #N/A | 5 | 2 | 7
| 17 | 22JL-ML117 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-24 | 2021-03-30 | 2021-03-31 | -0.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 85% | 5 | 0 | 0 | 0 | 0 | 1 | 85% | 6 | 1 | 5 | #N/A | #N/A | 5 | 2 | 7
| 18 | 22JL-ML118 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-16 | 2021-03-23 | 2021-03-29 | -1 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 6 | 5 | 7
| 19 | 22JL-ML119 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-16 | 2021-03-23 | 2021-03-24 | -1.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 6 | 2 | 7
| 20 | 22JL-ML120 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-17 | 2021-03-18 | 2021-03-19 | -2.4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 2 | 2 | 7
| 21 | 22JL-ML121 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-19 | 2021-03-23 | 2021-03-24 | -2.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 3 | 2 | 7
| 22 | 22JL-ML122 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-19 | 2021-03-26 | 2021-03-26 | -2.4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 23 | 22JL-ML123 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-19 | 2021-03-23 | 2021-03-24 | -2.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 3 | 2 | 7
| 24 | 22JL-ML124 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-19 | 2021-03-24 | 2021-03-25 | -2.6 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 4 | 2 | 7
| 25 | 22JL-ML125 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-22 | 2021-03-25 | 2021-03-26 | -2.4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 4 | 2 | 7
| 26 | 22JL-ML126 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-22 | 2021-03-24 | 2021-03-25 | -2.6 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 5 | 0 | 0 | 0 | 0 | 0 | 87% | 6 | 1 | 5 | #N/A | #N/A | 3 | 2 | 7
| 27 | 22JL-ML127 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-22 | 2021-03-24 | 2021-03-25 | -2.6 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 6 | 1 | 5 | #N/A | #N/A | 3 | 2 | 7
| 28 | 22JL-ML128 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-03-22 | 2021-03-30 | 2021-03-31 | -1.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 6 | 1 | 5 | #N/A | #N/A | 7 | 2 | 7
| 29 | 22JL-ML130 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-19 |  | 2021-03-23 | 2021-03-31 | 2021-03-31 | -2.7 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 6 | 1 | 5 | #N/A | #N/A | 7 | 1 | 7
| 30 | 22JL-ML131 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-19 |  | 2021-03-24 | 2021-03-25 | 2021-03-26 | -3.4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 85% | 5 | 0 | 0 | 0 | 0 | 1 | 85% | 6 | 1 | 5 | #N/A | #N/A | 2 | 2 | 7
| 31 | 22JL-ML132 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-19 |  | 2021-03-24 | 2021-03-26 | 2021-03-26 | -3.4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 5 | 0 | 0 | 0 | 0 | 2 | 82% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 32 | 22JL-ML153 | 2021-04-12 | 2021-04-26 | 2021-05-03 | 2021-05-10 |  | 2021-04-22 | 2021-05-05 | 2021-05-06 | -0.6 | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 2 | 81% | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 6 | 6 | 5 | #N/A | #N/A | 10 | 2 | 12
| 33 | 22JL-ML151 | 2021-04-12 | 2021-04-26 | 2021-05-03 | 2021-05-10 |  | 2021-04-22 | 2021-05-05 | 2021-05-06 | -0.6 | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 2 | 82% | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 6 | 6 | 5 | #N/A | #N/A | 10 | 2 | 12
| 34 | 22JL-ML152 | 2021-04-12 | 2021-04-26 | 2021-05-03 | 2021-05-10 |  | 2021-04-22 | 2021-05-05 | 2021-05-06 | -0.6 | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 2 | 82% | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 6 | 6 | 5 | #N/A | #N/A | 10 | 2 | 12
| 35 | 22JL-ML154 | 2021-04-12 | 2021-04-26 | 2021-05-03 | 2021-05-10 |  | 2021-04-22 | 2021-05-05 | 2021-05-06 | -0.6 | 1 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 2 | 79% | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 6 | 6 | 5 | #N/A | #N/A | 10 | 2 | 12
| 36 | 22JL-ML138 | 2021-04-19 | 2021-05-03 | 2021-05-10 | 2021-05-17 |  | 2021-04-23 | 2021-05-06 | 2021-05-11 | -0.9 | 1 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 6 | 6 | 5 | #N/A | #N/A | 10 | 4 | 12
| 37 | 22JL-ML136 | 2021-04-19 | 2021-05-03 | 2021-05-10 | 2021-05-17 |  | 2021-04-26 | 2021-05-10 | 2021-05-10 | -1 | 1 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 6 | 6 | 5 | #N/A | #N/A | 11 | 1 | 12
| 38 | 22JL-ML133 | 2021-04-19 | 2021-05-03 | 2021-05-10 | 2021-05-17 |  | 2021-04-26 | 2021-05-06 | 2021-05-07 | -1.4 | 1 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 6 | 6 | 5 | #N/A | #N/A | 9 | 2 | 12
| 39 | 22JL-ML141 | 2021-04-19 | 2021-05-03 | 2021-05-10 | 2021-05-17 |  | 2021-05-12 | 2021-05-24 | 2021-05-28 | 1.6 | 0 | 0 | 1 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 90% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 9 | 5 | 12
| 40 | 22JL-ML139 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  | 2021-04-26 | 2021-05-11 | 2021-05-12 | -1.7 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 6 | 6 | 5 | #N/A | #N/A | 12 | 2 | 12
| 41 | 22JL-ML142 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  | 2021-05-04 | 2021-05-12 | 2021-05-13 | -1.6 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 2 | 12
| 42 | 22JL-ML160 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  | 2021-05-06 | 2021-05-17 | 2021-05-19 | -0.7 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 8 | 3 | 12
| 43 | 22JL-ML137 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  | 2021-05-04 | 2021-05-17 | 2021-05-25 | 0.1 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 97% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 10 | 7 | 12
| 44 | 22JL-ML149 | 2021-05-03 | 2021-05-17 | 2021-05-24 | 2021-05-31 |  | 2021-05-04 | 2021-05-18 | 2021-05-19 | -1.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 11 | 2 | 12
| 45 | 22JL-ML146 | 2021-05-03 | 2021-05-17 | 2021-05-24 | 2021-05-31 |  | 2021-05-04 | 2021-05-17 | 2021-05-19 | -1.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 10 | 3 | 12
| 46 | 22JL-ML157 | 2021-05-03 | 2021-05-17 | 2021-05-24 | 2021-05-31 |  | 2021-05-07 | 2021-05-19 | 2021-05-20 | -1.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 9 | 2 | 12
| 47 | 22JL-ML135 | 2021-05-03 | 2021-05-17 | 2021-05-24 | 2021-05-31 |  | 2021-05-11 | 2021-05-25 | 2021-06-01 | 0.1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 97% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 11 | 6 | 12
| 48 | 22JL-ML140 | 2021-05-10 | 2021-05-24 | 2021-05-31 | 2021-06-07 |  | 2021-05-12 | 2021-05-25 | 2021-06-01 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 10 | 6 | 12
| 49 | 22JL-ML158 | 2021-05-10 | 2021-05-24 | 2021-05-31 | 2021-06-07 |  | 2021-05-12 | 2021-05-25 | 2021-05-28 | -1.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 10 | 4 | 12
| 50 | 22JL-ML159 | 2021-05-10 | 2021-05-24 | 2021-05-31 | 2021-06-07 |  | 2021-05-06 | 2021-05-17 | 2021-05-19 | -2.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 8 | 3 | 12
| 51 | 22JL-ML134 | 2021-05-10 | 2021-05-24 | 2021-05-31 | 2021-06-07 |  | 2021-05-13 | 2021-05-26 | 2021-05-28 | -1.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 0 | 0 | 0 | 1 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 10 | 3 | 12
| 52 | 22JL-ML148 | 2021-05-17 | 2021-05-31 | 2021-06-07 | 2021-06-14 |  | 2021-05-14 | 2021-05-20 | 2021-05-20 | -3.6 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 97% | 1 | 0 | 0 | 1 | 0 | 0 | 97% | 6 | 6 | 5 | #N/A | #N/A | 5 | 1 | 12
| 53 | 22JL-ML156 | 2021-05-17 | 2021-05-31 | 2021-06-07 | 2021-06-14 |  | 2021-05-17 | 2021-05-26 | 2021-06-01 | -1.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 8 | 5 | 12
| 54 | 22JL-ML143 | 2021-05-17 | 2021-05-31 | 2021-06-07 | 2021-06-14 |  | 2021-05-18 | 2021-05-28 | 2021-06-01 | -1.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 9 | 3 | 12
| 55 | 22JL-ML155 | 2021-05-17 | 2021-05-31 | 2021-06-07 | 2021-06-14 |  | 2021-05-17 | 2021-05-20 | 2021-06-01 | -1.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 4 | 9 | 12
| 56 | 22JL-ML144 | 2021-05-24 | 2021-06-07 | 2021-06-14 | 2021-06-21 |  | 2021-05-18 | 2021-05-26 | 2021-06-01 | -2.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 5 | 12
| 57 | 22JL-ML145 | 2021-05-24 | 2021-06-07 | 2021-06-14 | 2021-06-21 |  | 2021-05-20 | 2021-05-28 | 2021-06-01 | -2.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 3 | 12
| 58 | 22JL-ML147 | 2021-05-24 | 2021-06-07 | 2021-06-14 | 2021-06-21 |  | 2021-05-20 | 2021-06-11 | 2021-06-15 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 98% | 0 | 0 | 0 | 0 | 0 | 0 | 98% | 6 | 6 | 5 | #N/A | #N/A | 17 | 3 | 12
| 59 | 22JL-ML161 | 2021-05-24 | 2021-06-07 | 2021-06-14 | 2021-06-21 |  | 2021-05-25 | 2021-06-09 | 2021-06-15 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 12 | 5 | 12
| 60 | 22JL-ML162 | 2021-05-31 | 2021-06-14 | 2021-06-21 | 2021-06-28 |  | 2021-06-01 | 2021-06-09 | 2021-06-11 | -2.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 3 | 12
| 61 | 22JL-ML163 | 2021-05-31 | 2021-06-14 | 2021-06-21 | 2021-06-28 |  | 2021-06-01 | 2021-06-09 | 2021-06-11 | -2.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 3 | 12
| 62 | 22JL-ML164 | 2021-05-31 | 2021-06-14 | 2021-06-21 | 2021-06-28 |  | 2021-06-01 | 2021-06-09 | 2021-06-11 | -2.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 3 | 12
| 63 | 22JL-ML165 | 2021-05-31 | 2021-06-14 | 2021-06-21 | 2021-06-28 |  | 2021-06-01 | 2021-06-09 | 2021-06-11 | -2.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 6 | 5 | #N/A | #N/A | 7 | 3 | 12
| 1 | L2WS-54764 | 2020-10-26 | 2020-11-16 | 2020-11-30 | 2020-12-07 |  | 2020-11-18 | 2020-12-01 | 2020-12-07 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 6 | 5 | #N/A | #N/A | 10 | 5 | 17
| 2 | L2WS-54765 | 2020-10-26 | 2020-11-16 | 2020-11-30 | 2020-12-07 |  | 2020-11-19 | 2020-12-03 | 2020-12-07 | 0 | 0 | 1 | 0 | 0 | 3 |  |  | 0 | 0 |  | 94% | 3 | - |  | 0 | 0 |  | 94% | 11 | 6 | 5 | #N/A | #N/A | 11 | 3 | 17
| 3 | L2WS-54713 | 2020-11-02 | 2020-11-23 | 2020-12-07 | 2020-12-14 |  | 2020-11-20 | 2020-12-09 | 2020-12-10 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 |  | 6 | 2 |  | 96% | 0 | 0 |  | 6 | 2 |  | 96% | 11 | 6 | 5 | #N/A | #N/A | 14 | 2 | 17
| 4 | L2WS-54761 | 2020-11-02 | 2020-11-23 | 2020-12-07 | 2020-12-14 |  | 2020-12-03 | 2020-12-11 | 2020-12-15 | 0.1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 6 | 2 |  | 96% | 0 | 0 |  | 2 | 1 |  | 99% | 11 | 6 | 5 | #N/A | #N/A | 7 | 3 | 17
| 5 | L2WS-54714 | 2020-11-02 | 2020-11-23 | 2020-12-07 | 2020-12-14 |  | 2020-11-30 | 2020-12-11 | 2020-12-14 | 0 | 0 | 1 | 0 | 0 | 0 |  |  | 5 | 1 |  | 93% | 0 |  |  | 2 |  |  | 97% | 11 | 6 | 5 | #N/A | #N/A | 10 | 2 | 17
| 6 | L2WS-54717 | 2020-11-02 | 2020-11-23 | 2020-12-07 | 2020-12-14 |  | 2020-11-23 | 2020-12-07 | 2020-12-11 | -0.4 | 1 | 0 | 0 | 0 |  |  |  | 2 | 0 |  | 97% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 11 | 5 | 17
| 7 | L2WS-54766 | 2020-11-02 | 2020-11-23 | 2020-12-07 | 2020-12-14 |  | 2020-12-01 | 2020-12-09 | 2020-12-11 | -0.4 | 1 | 0 | 0 | 0 |  | 0 |  | 1 | 1 |  | 95% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 7 | 3 | 17
| 8 | L2WS-54767 | 2020-11-02 | 2020-11-23 | 2020-12-07 | 2020-12-14 |  | 2020-12-01 | 2020-12-09 | 2020-12-11 | -0.4 | 1 | 0 | 0 | 0 |  | 0 |  | 1 | 1 |  | 95% |  |  |  |  | 1 |  | 97% | 11 | 6 | 5 | #N/A | #N/A | 7 | 3 | 17
| 9 | L2WS-54737 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-04 | 2021-01-11 | 2021-01-15 | 1.6 | 0 | 0 | 1 | 0 |  | 0 |  | 8 | 0 |  | 91% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 27 | 5 | 27
| 10 | L2WS-54718 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-11 | 2020-12-11 | 2020-12-17 | -2.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 0 |  | 97% |  |  |  | 1 |  |  | 99% | 11 | 16 | 5 | #N/A | #N/A | 1 | 5 | 27
| 11 | L2WS-54719 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-11 | 2020-12-11 | 2020-12-17 | -2.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 4 |  | 91% |  |  |  | 1 | 3 |  | 93% | 11 | 16 | 5 | #N/A | #N/A | 1 | 5 | 27
| 12 | L2WS-54750 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-08 | 2020-12-17 | 2021-01-06 | 0.3 | 0 | 1 | 0 | 0 | 0 | 0 |  | 9 | 3 |  | 94% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 8 | 15 | 27
| 13 | L2WS-54738 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-04 | 2020-12-04 | 2020-12-11 | -3.4 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 6 | 27
| 14 | L2WS-54739 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-03 | 2020-12-04 | 2020-12-11 | -3.4 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 2 | 6 | 27
| 15 | L2WS-54770 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-11-25 | 2020-11-25 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 10 | 27
| 16 | L2WS-54776 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-04 | 2020-12-04 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 3 | 27
| 17 | L2WS-54771 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-03 | 2020-12-03 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 4 | 27
| 18 | L2WS-54772 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-02 | 2020-12-02 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 5 | 27
| 19 | L2WS-54773 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-02 | 2020-12-02 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 5 | 27
| 20 | L2WS-54774 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-02 | 2020-12-02 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 5 | 27
| 21 | L2WS-54775 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-04 | 2020-12-04 | 2020-12-08 | -3.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 11 | 16 | 5 | #N/A | #N/A | 1 | 3 | 27
| 22 | L2WS-54711 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-07 | 2021-01-06 | 2021-01-06 | 0.3 | 0 | 1 | 0 | 0 |  | 3 |  | 6 | 1 |  | 90% |  |  |  |  | 12 |  | 91% | 11 | 16 | 5 | #N/A | #N/A | 23 | 1 | 27
| 23 | L2WS-54745 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-07 | 2021-01-06 | 2021-01-06 | 0.3 | 0 | 1 | 0 | 0 |  | 3 |  | 7 | 1 |  | 89% |  |  |  |  | 15 |  | 92% | 11 | 16 | 5 | #N/A | #N/A | 23 | 1 | 27
| 24 | L2WS-54795 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-11 | 2021-01-06 | 2021-01-06 | 0.3 | 0 | 1 | 0 | 0 |  | 3 |  | 7 | 2 |  | 89% |  |  |  | 1 | 17 |  | 89% | 11 | 16 | 5 | #N/A | #N/A | 19 | 1 | 27
| 25 | L2WS-54796 | 2020-11-09 | 2020-11-30 | 2020-12-14 | 2021-01-04 |  | 2020-12-11 | 2021-01-06 | 2021-01-06 | 0.3 | 0 | 1 | 0 | 0 |  | 3 |  | 7 | 1 |  | 90% |  |  |  | 1 | 17 |  | 89% | 11 | 16 | 5 | #N/A | #N/A | 19 | 1 | 27
| 26 | L2WS-54712 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-10 | 2021-01-07 | 2021-01-15 | 0.6 | 0 | 1 | 0 | 0 | 0 | 0 |  | 7 | 2 |  | 95% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 21 | 7 | 27
| 27 | L2WS-54715 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-15 | 2020-12-22 | 2021-01-06 | -0.7 | 1 | 0 | 0 | 0 | 0 |  |  | 6 | 1 |  | 92% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 6 | 12 | 27
| 28 | L2WS-54716 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-16 | 2021-01-06 | 2021-01-12 | 0.1 | 0 | 1 | 0 | 0 | 0 |  |  | 6 | 1 |  | 92% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 16 | 5 | 27
| 29 | L2WS-54720 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-16 | 2020-12-16 | 2021-01-07 | -0.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 4 |  | 91% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 17 | 27
| 30 | L2WS-54721 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-17 | 2020-12-17 | 2021-01-07 | -0.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 4 |  | 91% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 16 | 27
| 31 | L2WS-54722 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-17 | 2020-12-21 | 2021-01-07 | -0.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 4 |  | 91% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 3 | 14 | 27
| 32 | L2WS-54762 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-17 | 2020-12-18 | 2021-01-07 | -0.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 0 |  | 85% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 2 | 15 | 27
| 33 | L2WS-54763 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-17 | 2020-12-18 | 2021-01-07 | -0.6 | 1 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 2 | 15 | 27
| 34 | L2WS-54740 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-04 | 2020-12-04 | 2020-12-11 | -4.4 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 6 | 27
| 35 | L2WS-54741 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-04 | 2020-12-04 | 2020-12-11 | -4.4 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 6 | 27
| 36 | L2WS-54743 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-02 | 2020-12-02 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 5 | 27
| 37 | L2WS-54744 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-03 | 2020-12-03 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 4 | 27
| 38 | L2WS-54706 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-04 | 2020-12-04 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 3 | 27
| 39 | L2WS-54707 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-04 | 2020-12-04 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 3 | 27
| 40 | L2WS-54708 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-11-25 | 2020-11-25 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 10 | 27
| 41 | L2WS-54709 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-11-25 | 2020-11-25 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 10 | 27
| 42 | L2WS-54710 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-02 | 2020-12-02 | 2020-12-08 | -4.9 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 5 | 27
| 43 | L2WS-55019 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-04 | 2020-12-04 | 2020-12-11 | -4.4 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 6 | 27
| 44 | L2WS-55020 | 2020-11-16 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-14 | 2020-12-14 | 2020-12-14 | -4 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 1 | 27
| 45 | L2WS-54723 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2020-12-10 | 2020-12-21 | 2021-01-07 | -1.6 | 1 | 0 | 0 | 0 |  |  |  |  | 4 |  | 95% |  |  |  |  | 4 |  | 95% | 21 | 6 | 5 | #N/A | #N/A | 8 | 14 | 27
| 46 | L2WS-54724 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2020-12-10 | 2020-12-21 | 2021-01-07 | -1.6 | 1 | 0 | 0 | 0 |  |  |  |  | 4 |  | 95% |  |  |  |  | 4 |  | 95% | 21 | 6 | 5 | #N/A | #N/A | 8 | 14 | 27
| 47 | L2WS-54725 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2020-12-10 | 2020-12-22 | 2021-01-07 | -1.6 | 1 | 0 | 0 | 0 |  |  |  |  | 4 |  | 95% |  |  |  |  | 4 |  | 95% | 21 | 6 | 5 | #N/A | #N/A | 9 | 13 | 27
| 48 | L2WS-54726 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2020-12-10 | 2021-01-04 | 2021-01-07 | -1.6 | 1 | 0 | 0 | 0 |  |  |  |  | 4 |  | 95% |  |  |  |  | 4 |  | 95% | 21 | 6 | 5 | #N/A | #N/A | 18 | 4 | 27
| 49 | L2WS-54748 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2021-01-11 | 2021-01-15 | 2021-01-22 | 0.6 | 0 | 1 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 5 | 6 | 27
| 50 | L2WS-54749 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2021-01-12 | 2021-01-15 | 2021-01-22 | 0.6 | 0 | 1 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 4 | 6 | 27
| 51 | L2WS-54768 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2021-01-07 | 2021-01-14 | 2021-01-15 | -0.4 | 1 | 0 | 0 | 0 |  |  |  |  | 1 |  | 97% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 6 | 2 | 27
| 52 | L2WS-54769 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2021-01-07 | 2021-01-08 | 2021-01-12 | -0.9 | 1 | 0 | 0 | 0 |  |  |  |  | 1 |  | 97% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 2 | 3 | 27
| 53 | L2WS-54742 | 2020-11-23 | 2020-12-14 | 2021-01-11 | 2021-01-18 |  | 2020-12-04 | 2020-12-04 | 2020-12-17 | -4.6 | 1 | 0 | 0 | 0 | [6 empty] | 100% | [6 empty] | 100% | 21 | 6 | 5 | #N/A | #N/A | 1 | 10 | 27
| 54 | L2WS-54727 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-08 | 2021-01-11 | 2021-01-14 | -1.6 | 1 | 0 | 0 | 0 |  |  |  | 0 | 4 |  | 95% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 2 | 4 | 17
| 55 | L2WS-54728 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-12 | 2021-01-13 | 2021-01-14 | -1.6 | 1 | 0 | 0 | 0 |  |  |  | 0 | 4 |  | 95% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 2 | 2 | 17
| 56 | L2WS-54729 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-13 | 2021-01-14 | 2021-01-14 | -1.6 | 1 | 0 | 0 | 0 |  |  |  | 0 | 4 |  | 95% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 2 | 1 | 17
| 57 | L2WS-54699 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-13 | 2021-02-10 | 2021-02-11 | 2.4 | 0 | 0 | 0 | 1 |  |  |  | 0 | 0 |  | 100% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 21 | 2 | 17
| 58 | L2WS-54700 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-13 | 2021-02-10 | 2021-02-11 | 2.4 | 0 | 0 | 0 | 1 |  |  |  | 0 | 0 |  | 100% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 21 | 2 | 17
| 59 | L2WS-54701 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-13 | 2021-02-10 | 2021-02-11 | 2.4 | 0 | 0 | 0 | 1 |  |  |  | 1 | 0 |  | 97% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 21 | 2 | 17
| 60 | L2WS-54703 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-11 | 2021-02-12 | 2021-02-12 | 2.6 | 0 | 0 | 0 | 1 |  |  |  | 1 | 0 |  | 97% |  |  |  |  | 5 |  | 97% | 11 | 6 | 5 | #N/A | #N/A | 25 | 1 | 17
| 61 | L2WS-54730 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-01-29 | 2021-01-29 | 2021-02-04 | 0.4 | 0 | 1 | 0 | 0 |  |  |  | 2 | 2 |  | 98% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 1 | 5 | 17
| 62 | L2WS-54731 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-01 | 2021-02-02 | 2021-02-04 | 0.4 | 0 | 1 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 3 | 17
| 63 | L2WS-54732 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-03 | 2021-02-04 | 2021-02-08 | 1 | 0 | 1 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 3 | 17
| 64 | L2WS-54733 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-04 | 2021-02-05 | 2021-02-08 | 1 | 0 | 1 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 2 | 17
| 65 | L2WS-54734 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-05 | 2021-02-05 | 2021-02-11 | 1.4 | 0 | 0 | 1 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 1 | 5 | 17
| 66 | L2WS-54752 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-02 | 2021-02-02 | 2021-02-03 | 0.3 | 0 | 1 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 1 | 2 | 17
| 67 | L2WS-54753 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-06 | 2021-02-06 | 2021-02-08 | 1 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 0 | 1 | 17
| 68 | L2WS-54754 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-02-06 | 2021-02-06 | 2021-02-08 | 1 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 0 | 1 | 17
| 69 | L2WS-54735 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-09 | 2021-02-10 | 2021-02-11 | 0.4 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 2 | 17
| 70 | L2WS-54736 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-10 | 2021-02-11 | 2021-02-11 | 0.4 | 0 | 1 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 1 | 17
| 71 | L2WS-55013 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-01-15 | 2021-01-25 | 2021-01-28 | -1.6 | 1 | 0 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 7 | 4 | 17
| 72 | L2WS-55014 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-01-15 | 2021-01-25 | 2021-01-28 | -1.6 | 1 | 0 | 0 | 0 |  |  |  | 2 | 4 |  | 92% | [6 empty] | 100% | 11 | 6 | 5 | #N/A | #N/A | 7 | 4 | 17
| 73 | L2WS-54755 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-09 | 2021-02-12 | 2021-02-12 | 0.6 | 0 | 1 | 0 | 0 |  |  |  | 4 | 4 |  | 90% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 4 | 1 | 17
| 74 | L2WS-54756 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-09 | 2021-02-12 | 2021-02-12 | 0.6 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 4 | 1 | 17
| 75 | L2WS-54757 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-10 | 2021-02-12 | 2021-02-12 | 0.6 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 3 | 1 | 17
| 76 | L2WS-54758 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-10 | 2021-02-12 | 2021-02-12 | 0.6 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 3 | 1 | 17
| 77 | L2WS-54759 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-11 | 2021-02-12 | 2021-02-12 | 0.6 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 1 | 17
| 78 | L2WS-54760 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-02-11 | 2021-02-12 | 2021-02-12 | 0.6 | 0 | 1 | 0 | 0 |  |  |  | 2 |  |  | 95% | [7 empty] | 11 | 6 | 5 | #N/A | #N/A | 2 | 1 | 17
| 1 | L2WL-54548 | 2020-12-07 | 2021-01-04 | 2021-01-18 | 2021-01-18 |  | 2021-01-04 | 2021-01-22 | 2021-01-22 | 0.6 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 5 | 14 | 0 | 94% | 0 | 2 | 0 | 5 | 9 | 0 | 96% | 11 | 1 | 5 | #N/A | #N/A | 15 | 1 | 12
| 2 | L2WL-54603 | 2020-12-07 | 2021-01-04 | 2021-01-18 | 2021-01-18 |  | 2021-01-06 | 2021-01-22 | 2021-01-22 | 0.6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 93% | 0 | 0 | 0 | 0 | 2 | 0 | 96% | 11 | 1 | 5 | #N/A | #N/A | 13 | 1 | 12
| 3 | L2WL-54552 | 2020-12-14 | 2021-01-11 | 2021-01-25 | 2021-01-25 |  | 2021-01-11 | 2021-01-28 | 2021-01-28 | 0.4 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 5 | 13 | 0 | 95% | 0 | 1 | 0 | 6 | 10 | 0 | 95% | 11 | 1 | 5 | #N/A | #N/A | 14 | 1 | 12
| 4 | L2WL-54579 | 2020-12-24 | 2021-01-11 | 2021-01-25 | 2021-01-25 |  | 2021-01-11 | 2021-01-29 | 2021-01-29 | 0.6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 0 | 93% | 0 | 0 | 0 | 4 | 4 | 0 | 95% | 11 | 1 | 5 | #N/A | #N/A | 15 | 1 | 12
| 5 | L2WL-54573 | 2021-01-04 | 2021-01-18 | 2021-02-01 | 2021-02-01 |  | 2021-01-18 | 2021-02-01 | 2021-02-01 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 11 | 1 | 12
| 6 | L2WL-54551 | 2021-01-04 | 2021-01-18 | 2021-02-01 | 2021-02-01 |  | 2021-01-18 | 2021-02-08 | 2021-02-08 | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 5 | 11 | 0 | 95% | 0 | 3 | 0 | 6 | 10 | 0 | 95% | 11 | 1 | 5 | #N/A | #N/A | 16 | 1 | 12
| 7 | L2WL-54532 | 2021-01-11 | 2021-01-25 | 2021-02-08 | 2021-02-08 |  | 2021-01-25 | 2021-01-26 | 2021-01-26 | -1.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 97% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 2 | 1 | 12
| 8 | L2WL-54510 | 2021-01-11 | 2021-01-25 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-04 | 2021-02-04 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98% | 0 | 0 | 0 | 4 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 4 | 1 | 12
| 9 | L2WL-54511 | 2021-01-18 | 2021-02-01 | 2021-02-15 | 2021-02-15 |  | 2021-01-26 | 2021-02-05 | 2021-02-05 | -1.4 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 9 | 0 | 94% | 0 | 0 | 0 | 0 | 0 | 0 | 98% | 11 | 1 | 5 | #N/A | #N/A | 9 | 1 | 12
| 10 | L2WL-54601 | 2021-01-18 | 2021-02-01 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-04 | 2021-02-04 | -1.6 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 98% | 0 | 0 | 0 | 2 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 4 | 1 | 12
| 11 | L2WL-54581 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-01-28 | 2021-01-29 | 2021-01-29 | -1.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 12 | L2WL-54586 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-02 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 0 | 0 | 0 | 0 | 0 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 5 | 1 | 7
| 13 | L2WL-54514 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 14 | L2WL-54557 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 15 | L2WL-54571 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 16 | L2WL-54555 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 17 | L2WL-54545 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 18 | L2WL-54550 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 19 | L2WL-54602 | 2021-01-25 | 2021-02-08 | 2021-02-22 | 2021-02-22 |  | 2021-02-08 | 2021-02-10 | 2021-02-10 | -1.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 20 | L2WL-54575 | 2021-01-25 | 2021-02-08 | 2021-02-22 | 2021-02-22 |  | 2021-02-08 | 2021-02-10 | 2021-02-10 | -1.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 21 | L2WL-54604 | 2021-01-25 | 2021-02-08 | 2021-02-22 | 2021-02-22 |  | 2021-02-02 | 2021-02-03 | 2021-02-03 | -2.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 2 | 1 | 12
| 22 | L2WL-54587 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-08 | 2021-02-10 | 2021-02-10 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 23 | L2WL-55145 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-08 | 2021-02-10 | 2021-02-10 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 24 | L2WL-54556 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 25 | L2WL-54553 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 26 | L2WL-54566 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 27 | L2WL-54543 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 28 | L2WL-54561 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 29 | L2WL-54576 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-02-01 | 2021-02-08 | 2021-02-08 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 30 | L2WL-54580 | 2021-02-01 | 2021-02-15 | 2021-03-01 | 2021-03-01 |  | 2021-02-08 | 2021-02-15 | 2021-02-15 | -2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 6 | 1 | 12
| 31 | L2WL-54599 | 2021-02-01 | 2021-02-15 | 2021-03-01 | 2021-03-01 |  | 2021-02-09 | 2021-02-18 | 2021-02-18 | -1.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 97% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 8 | 1 | 12
| 32 | L2WL-54590 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-02-18 | 2021-02-18 | 2021-02-18 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 33 | L2WL-54589 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-02-15 | 2021-02-18 | 2021-02-18 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 94% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 1 | 7
| 34 | L2WL-54523 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 35 | L2WL-54522 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 36 | L2WL-54546 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 37 | L2WL-54547 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 38 | L2WL-54558 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 39 | L2WL-54544 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 40 | L2WL-54533 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-08 |  | 2021-02-11 | 2021-02-18 | 2021-02-18 | -2.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 6 | 1 | 12
| 41 | L2WL-54535 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-08 |  | 2021-02-11 | 2021-02-18 | 2021-02-18 | -2.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 6 | 1 | 12
| 42 | L2WL-54591 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-02-22 | 2021-02-25 | 2021-02-25 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 1 | 7
| 43 | L2WL-54596 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-02-22 | 2021-02-25 | 2021-02-25 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 97% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 1 | 7
| 44 | L2WL-54528 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-03-22 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 45 | L2WL-54537 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-03-22 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 46 | L2WL-54563 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-03-22 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 47 | L2WL-54564 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-03-22 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 48 | L2WL-54540 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-03-22 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 49 | L2WL-54541 | 2021-02-08 | 2021-02-22 | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-03-22 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 50 | L2WL-54505 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-03-15 |  | 2021-02-22 | 2021-02-24 | 2021-02-24 | -2.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 97% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 51 | L2WL-54598 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-03-15 |  | 2021-02-22 | 2021-02-24 | 2021-02-24 | -2.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 99% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 52 | L2WL-54592 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-02-25 | 2021-02-01 | 2021-02-01 | -5 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | -19 | 1 | 7
| 53 | L2WL-54593 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-03-01 | 2021-03-08 | 2021-03-08 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 6 | 1 | 5 | #N/A | #N/A | 6 | 1 | 7
| 54 | L2WL-54559 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-02-25 | 2021-03-01 | 2021-03-01 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 55 | L2WL-54515 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-03-02 | 2021-03-03 | 2021-03-03 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 56 | L2WL-54516 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-03-03 | 2021-03-04 | 2021-03-04 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 57 | L2WL-54517 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-03-04 | 2021-03-05 | 2021-03-05 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 58 | L2WL-54518 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-08 |  | 2021-03-04 | 2021-03-05 | 2021-03-05 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 59 | L2WL-54531 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-03-22 |  | 2021-02-23 | 2021-03-01 | 2021-03-01 | -3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 5 | 1 | 12
| 60 | L2WL-54534 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-03-22 |  | 2021-02-23 | 2021-03-02 | 2021-03-02 | -2.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 6 | 1 | 12
| 61 | L2WL-54594 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-02-22 | 2021-02-25 | 2021-02-25 | -2.6 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 1 | 7
| 62 | L2WL-54595 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-03-22 | 2021-03-23 | 2021-03-23 | 1.1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 63 | L2WL-54560 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-03-08 | 2021-03-09 | 2021-03-09 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 64 | L2WL-54570 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-03-09 | 2021-03-10 | 2021-03-10 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 65 | L2WL-54520 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-03-09 | 2021-03-10 | 2021-03-10 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 66 | L2WL-54554 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-03-10 | 2021-03-12 | 2021-03-12 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 67 | L2WL-54562 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-15 |  | 2021-03-10 | 2021-03-12 | 2021-03-12 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 68 | L2WL-54529 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-03-29 |  | 2021-02-25 | 2021-03-01 | 2021-03-01 | -4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 97% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 69 | L2WL-54506 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-03-29 |  | 2021-02-26 | 2021-03-02 | 2021-03-02 | -3.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 70 | L2WL-54588 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 0.1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 71 | L2WL-54582 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 0.1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 96% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 72 | L2WL-54539 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-02-25 | 2021-03-01 | 2021-03-01 | -3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 73 | L2WL-54538 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-02-25 | 2021-03-01 | 2021-03-01 | -3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 74 | L2WL-54524 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-12 | 2021-03-15 | 2021-03-15 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 75 | L2WL-54525 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-15 | 2021-03-16 | 2021-03-16 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 76 | L2WL-54584 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-03-22 |  | 2021-03-16 | 2021-03-18 | 2021-03-18 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 3 | 1 | 7
| 77 | L2WL-54536 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-05 |  | 2021-03-01 | 2021-03-04 | 2021-03-04 | -4.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 4 | 1 | 12
| 78 | L2WL-54503 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-05 |  | 2021-03-01 | 2021-03-03 | 2021-03-03 | -4.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 79 | L2WL-54597 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 80 | L2WL-54567 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-22 | 2021-03-23 | 2021-03-23 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 81 | L2WL-54549 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-23 | 2021-03-24 | 2021-03-24 | -0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 82 | L2WL-54521 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-24 | 2021-03-25 | 2021-03-25 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 83 | L2WL-54577 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-24 | 2021-03-25 | 2021-03-25 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 84 | L2WL-54600 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-25 | 2021-03-26 | 2021-03-26 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 85 | L2WL-54583 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-03-29 |  | 2021-03-25 | 2021-03-26 | 2021-03-26 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 86 | L2WL-54530 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-04-12 |  | 2021-03-03 | 2021-03-05 | 2021-03-05 | -5.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 87 | L2WL-54508 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-04-12 |  | 2021-03-05 | 2021-03-06 | 2021-03-06 | -5.3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 1 | 0 | 12
| 88 | L2WL-54568 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-26 | 2021-03-29 | 2021-03-29 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 89 | L2WL-54569 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-03-29 | 2021-03-30 | 2021-03-30 | -0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 90 | L2WL-54565 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-04-06 | 2021-04-07 | 2021-04-07 | 0.3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 91 | L2WL-54519 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-04-06 | 2021-04-07 | 2021-04-07 | 0.3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 92 | L2WL-54578 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-04-07 | 2021-04-08 | 2021-04-08 | 0.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 93 | L2WL-54585 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-05 |  | 2021-04-07 | 2021-04-08 | 2021-04-08 | 0.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 94 | L2WL-54504 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-04-19 |  | 2021-03-05 | 2021-03-08 | 2021-03-08 | -6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 2 | 1 | 12
| 95 | L2WL-54513 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-04-19 |  | 2021-03-08 | 2021-03-10 | 2021-03-10 | -5.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 3 | 1 | 12
| 96 | L2WL-54572 | 2021-03-22 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-04-08 | 2021-04-09 | 2021-04-09 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 97 | L2WL-54527 | 2021-03-22 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-04-09 | 2021-04-12 | 2021-04-12 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 2 | 1 | 7
| 98 | L2WL-54526 | 2021-03-22 | 2021-04-05 | 2021-04-12 | 2021-04-12 |  | 2021-04-12 | 2021-04-12 | 2021-04-12 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 99 | L2WL-54509 | 2021-03-29 | 2021-04-12 | 2021-04-26 | 2021-04-26 |  | 2021-03-09 | 2021-03-12 | 2021-03-12 | -6.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 4 | 1 | 12
| 100 | L2WL-54507 | 2021-03-29 | 2021-04-12 | 2021-04-26 | 2021-04-26 |  | 2021-03-10 | 2021-03-15 | 2021-03-15 | -6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 4 | 1 | 12
| 101 | L2WL-54512 | 2021-04-05 | 2021-04-19 | 2021-05-03 | 2021-05-03 |  | 2021-03-10 | 2021-03-16 | 2021-03-16 | -6.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 1 | 5 | #N/A | #N/A | 5 | 1 | 12
| 102 | L2WL-55253 | 2021-04-05 | 2021-04-19 | 2021-05-10 | 2021-05-10 |  | 2021-03-12 | 2021-03-26 | 2021-03-26 | -6.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 1 | 5 | #N/A | #N/A | 11 | 1 | 17
| 103 | L2WL-54574 | 2021-04-05 | 2021-04-19 | 2021-04-26 | 2021-04-26 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | -4.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 1 | R3DS-54315 | 2020-11-30 | 2020-12-14 | 2021-01-04 | 2021-01-11 |  | 2020-12-18 | 2021-01-14 | 2021-01-26 | 2.1 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 80% | 1 | 2 | 0 | 0 | 0 | 0 | 86% | 16 | 6 | 5 | #N/A | #N/A | 20 | 9 | 22
| 2 | R3DS-54310 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-04 | 2021-01-14 | 2021-01-26 | 0.1 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 82% | 0 | 4 | 0 | 0 | 0 | 0 | 82% | 11 | 6 | 5 | #N/A | #N/A | 9 | 9 | 17
| 3 | R3DS-54312 | 2020-12-14 | 2021-01-04 | 2021-01-18 | 2021-01-25 |  | 2021-01-04 | 2021-01-14 | 2021-01-29 | 0.6 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 80% | 0 | 2 | 0 | 0 | 0 | 0 | 97% | 11 | 6 | 5 | #N/A | #N/A | 9 | 12 | 17
| 4 | R3DS-54307 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-01-04 | 2021-01-14 | 2021-01-26 | -0.9 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 80% | 0 | 2 | 0 | 0 | 0 | 0 | 85% | 11 | 6 | 5 | #N/A | #N/A | 9 | 9 | 17
| 5 | R3DS-54311 | 2020-12-21 | 2021-01-11 | 2021-01-25 | 2021-02-01 |  | 2021-01-06 | 2021-01-18 | 2021-01-29 | -0.4 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 82% | 0 | 4 | 0 | 0 | 0 | 0 | 82% | 11 | 6 | 5 | #N/A | #N/A | 9 | 10 | 17
| 6 | R3DS-54313 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-01-14 | 2021-02-01 | 2021-02-04 | -0.6 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 80% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 11 | 6 | 5 | #N/A | #N/A | 13 | 4 | 17
| 7 | R3DS-54308 | 2020-12-28 | 2021-01-18 | 2021-02-01 | 2021-02-08 |  | 2021-01-25 | 2021-02-01 | 2021-02-04 | -0.6 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 80% | 0 | 2 | 0 | 0 | 0 | 0 | 85% | 11 | 6 | 5 | #N/A | #N/A | 6 | 4 | 17
| 8 | R3DS-54309 | 2021-01-04 | 2021-01-25 | 2021-02-08 | 2021-02-15 |  | 2021-01-28 | 2021-02-05 | 2021-02-10 | -0.7 | 1 | 0 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 1 | 60% | 0 | 4 | 0 | 0 | 0 | 0 | 82% | 11 | 6 | 5 | #N/A | #N/A | 7 | 4 | 17
| 9 | R3DS-54314 | 2021-01-04 | 2021-01-25 | 2021-02-08 | 2021-02-15 |  | 2021-02-08 | 2021-02-15 | 2021-02-18 | 0.4 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 80% | 0 | 2 | 0 | 0 | 0 | 0 | 86% | 11 | 6 | 5 | #N/A | #N/A | 6 | 4 | 17
| 10 | R3DS-54316 | 2021-01-04 | 2021-01-25 | 2021-02-08 | 2021-02-15 |  | 2021-02-25 | 2021-03-04 | 2021-03-05 | 2.6 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 80% | 3 | 2 | 0 | 0 | 0 | 0 | 73% | 11 | 6 | 5 | #N/A | #N/A | 6 | 2 | 17
| 1 | R3D2-54341 | 2020-11-23 | 2020-12-07 | 2021-01-04 | 2021-01-11 |  | 2020-12-03 | 2020-12-10 | 2020-12-14 | -4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 35% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 21 | 6 | 5 | #N/A | #N/A | 6 | 3 | 27
| 2 | R3DJ-91846 | 2020-12-07 | 2020-12-21 | 2021-01-18 | 2021-01-25 |  | 2020-12-15 | 2020-12-22 | 2021-01-28 | 0.4 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 85% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 21 | 6 | 5 | #N/A | #N/A | 6 | 28 | 27
| 3 | R3DJ-91848 | 2020-12-07 | 2020-12-21 | 2021-01-18 | 2021-01-25 |  | 2020-12-23 | 2021-01-28 | 2021-02-11 | 2.4 | 0 | 0 | 0 | 1 | 0 | 9 | 0 | 2 | 0 | 0 | 62% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 21 | 6 | 5 | #N/A | #N/A | 27 | 11 | 27
| 4 | R3DJ-91850 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-01 |  | 2021-01-04 | 2021-02-05 | 2021-02-11 | 1.4 | 0 | 0 | 1 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 81% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 25 | 5 | 22
| 5 | R3D2-54348 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-01 |  | 2021-01-04 | 2021-01-20 | 2021-01-28 | -0.6 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 81% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 13 | 7 | 22
| 6 | R3DJ-91852 | 2020-12-28 | 2021-01-11 | 2021-02-01 | 2021-02-08 |  | 2021-01-07 | 2021-01-20 | 2021-02-02 | -0.9 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 64% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 10 | 10 | 22
| 7 | R3DJ-91847 | 2020-12-28 | 2021-01-11 | 2021-02-01 | 2021-02-08 |  | 2021-01-15 | 2021-01-29 | 2021-02-02 | -0.9 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 92% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 11 | 3 | 22
| 8 | R3DP-64495 | 2020-12-28 | 2021-01-11 | 2021-02-01 | 2021-02-08 |  | 2021-01-15 | 2021-01-20 | 2021-01-27 | -1.7 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 92% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | 4 | 6 | 22
| 9 | R3DJ-91849 | 2021-01-04 | 2021-01-18 | 2021-02-08 | 2021-02-15 |  | 2021-01-22 | 2021-02-03 | 2021-02-05 | -1.4 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 0 | 4 | 0 | 0 | 0 | 0 | 90% | 16 | 6 | 5 | #N/A | #N/A | 9 | 3 | 22
| 10 | R3DJ-91851 | 2021-01-04 | 2021-01-18 | 2021-02-08 | 2021-02-15 |  | 2021-01-22 | 2021-02-22 | 2021-02-24 | 1.3 | 0 | 0 | 1 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 70% | 0 | 4 | 0 | 0 | 0 | 0 | 90% | 16 | 6 | 5 | #N/A | #N/A | 22 | 3 | 22
| 11 | R3DP-64497 | 2021-01-04 | 2021-01-18 | 2021-02-08 | 2021-02-15 |  | 2021-01-28 | 2021-02-10 | 2021-02-16 | 0.1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 62% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 10 | 5 | 22
| 12 | R3DJ-91853 | 2021-01-11 | 2021-01-25 | 2021-02-15 | 2021-02-22 |  | 2021-01-28 | 2021-02-12 | 2021-02-16 | -0.9 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 90% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 12 | 3 | 22
| 13 | R3DJ-91854 | 2021-01-11 | 2021-01-25 | 2021-02-15 | 2021-02-22 |  | 2021-01-29 | 2021-02-10 | 2021-02-11 | -1.6 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 81% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | 9 | 2 | 22
| 14 | R3DJ-91855 | 2021-01-11 | 2021-01-25 | 2021-02-15 | 2021-02-22 |  | 2021-01-29 | 2021-02-09 | 2021-02-11 | -1.6 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 81% | 0 | 4 | 0 | 0 | 0 | 0 | 90% | 16 | 6 | 5 | #N/A | #N/A | 8 | 3 | 22
| 15 | R3DJ-91856 | 2021-01-18 | 2021-02-01 | 2021-02-22 | 2021-03-01 |  | 2021-02-10 | 2021-02-17 | 2021-02-22 | -1 | 1 | 0 | 0 | 0 | 1 | 6 | 0 | 2 | 0 | 0 | 92% | 1 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 6 | 4 | 22
| 16 | R3DJ-91859 | 2021-01-18 | 2021-02-01 | 2021-02-22 | 2021-03-01 |  | 2021-02-12 | 2021-02-17 | 2021-02-22 | -1 | 1 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 90% | 0 | 1 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 4 | 4 | 22
| 17 | R3DF-56426 | 2021-01-18 | 2021-02-01 | 2021-02-22 | 2021-03-01 |  | 2021-02-12 | 2021-02-17 | 2021-02-26 | -0.4 | 1 | 0 | 0 | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 83% | 1 | 6 | 0 | 2 | 0 | 0 | 92% | 16 | 6 | 5 | #N/A | #N/A | 4 | 8 | 22
| 18 | R3DJ-91860 | 2021-01-25 | 2021-02-08 | 2021-03-01 | 2021-03-08 |  | 2021-02-12 | 2021-02-25 | 2021-03-11 | 0.4 | 0 | 1 | 0 | 0 | 1 | 6 | 0 | 1 | 0 | 0 | 90% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 16 | 6 | 5 | #N/A | #N/A | 10 | 11 | 22
| 19 | R3DJ-91861 | 2021-01-25 | 2021-02-08 | 2021-03-01 | 2021-03-08 |  | 2021-02-17 | 2021-02-19 | 2021-02-19 | -2.4 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 66% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 3 | 1 | 22
| 20 | R3D2-54349 | 2021-01-25 | 2021-02-08 | 2021-03-01 | 2021-03-08 |  | 2021-02-17 | 2021-02-19 | 2021-02-19 | -2.4 | 1 | 0 | 0 | 0 | 1 | 6 | 0 | 2 | 0 | 0 | 81% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 3 | 1 | 22
| 21 | R3D2-54342 | 2021-02-01 | 2021-02-15 | 2021-03-08 | 2021-03-15 |  | 2021-03-12 | 2021-04-01 | 2021-04-07 | 3.3 | 0 | 0 | 0 | 1 | 1 | 6 | 0 | 2 | 0 | 0 | 92% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 15 | 5 | 22
| 22 | R3D2-54343 | 2021-02-01 | 2021-02-15 | 2021-03-08 | 2021-03-15 |  | 2021-03-03 | 2021-03-23 | 2021-03-30 | 2.1 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 90% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 15 | 6 | 22
| 23 | R3D2-54344 | 2021-02-01 | 2021-02-15 | 2021-03-08 | 2021-03-15 |  | 2021-02-19 | 2021-02-25 | 2021-03-08 | -1 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 90% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 5 | 8 | 22
| 24 | R3DP-64496 | 2021-02-08 | 2021-02-22 | 2021-03-15 | 2021-03-22 |  | 2021-02-19 | 2021-02-23 | 2021-03-08 | -2 | 1 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 73% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 3 | 10 | 22
| 25 | R3D2-54345 | 2021-02-08 | 2021-02-22 | 2021-03-15 | 2021-03-22 |  | 2021-02-19 | 2021-03-15 | 2021-03-16 | -0.9 | 1 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 73% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 17 | 2 | 22
| 26 | R3D2-54346 | 2021-02-08 | 2021-02-22 | 2021-03-15 | 2021-03-22 |  | 2021-02-23 | 2021-02-25 | 2021-03-09 | -1.9 | 1 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 73% | 0 | 2 | 0 | 0 | 0 | 0 | 95% | 16 | 6 | 5 | #N/A | #N/A | 3 | 9 | 22
| 27 | R3D2-54347 | 2021-02-15 | 2021-03-01 | 2021-03-22 | 2021-03-29 |  | 2021-03-16 | 2021-03-26 | 2021-03-29 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 81% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 9 | 2 | 22
| 28 | R3DJ-91857 | 2021-02-15 | 2021-03-01 | 2021-03-22 | 2021-03-29 |  | 2021-02-24 | 2021-04-13 | 2021-04-15 | 2.4 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 81% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 35 | 3 | 22
| 29 | R3DD-54167 | 2021-02-15 | 2021-03-01 | 2021-03-22 | 2021-03-29 |  | 2021-02-23 | 2021-02-25 | 2021-03-11 | -2.6 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 81% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 3 | 11 | 22
| 30 | R3DP-64498 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-04-05 |  | 2021-03-04 | 2021-03-12 | 2021-03-17 | -2.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 7 | 4 | 22
| 31 | R3DJ-91858 | 2021-02-22 | 2021-03-08 | 2021-03-29 | 2021-04-05 |  | 2021-02-26 | 2021-03-10 | 2021-03-17 | -2.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 9 | 6 | 22
| 32 | R3DP-64499 | 2021-03-08 | 2021-03-22 | 2021-04-12 | 2021-04-19 |  | 2021-03-03 | 2021-03-12 | 2021-03-17 | -4.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 8 | 4 | 22
| 33 | R3DP-64500 | 2021-03-08 | 2021-03-22 | 2021-04-12 | 2021-04-19 |  | 2021-04-06 | 2021-04-12 | 2021-04-15 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | [7 empty] | 16 | 6 | 5 | #N/A | #N/A | 5 | 4 | 22
| 1 | 23JL-M2B01 | 2021-02-15 | 2021-03-01 | 2021-03-15 | 2021-03-22 |  | 2021-02-25 | 2021-03-08 | 2021-03-25 | 0.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 93% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 6 | 5 | #N/A | #N/A | 8 | 14 | 17
| 2 | 23JL-M2B02 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-03-29 |  | 2021-02-26 | 2021-03-08 | 2021-03-25 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 6 | 5 | #N/A | #N/A | 7 | 14 | 17
| 3 | 23JL-M2B03 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-03-29 |  | 2021-03-03 | 2021-03-12 | 2021-03-25 | -0.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 93% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 11 | 6 | 5 | #N/A | #N/A | 8 | 10 | 17
| 1 | R1WL-52116 | 2021-01-11 | 2021-01-25 | 2021-02-08 | 2021-02-22 |  | 2021-01-19 | 2021-02-08 | 2021-02-18 | -0.6 | 1 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 2 | 64% | 1 | 2 | 0 | 0 | 0 | 1 | 86% | 11 | 11 | 5 | #N/A | #N/A | 15 | 9 | 22
| 2 | R1WL-52108 | 2021-01-25 | 2021-02-08 | 2021-02-22 | 2021-03-08 |  | 2021-01-20 | 2021-02-09 | 2021-02-15 | -3 | 1 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 1 | 86% | 1 | 1 | 0 | 0 | 0 | 0 | 94% | 11 | 11 | 5 | #N/A | #N/A | 15 | 5 | 22
| 3 | R1WL-52120 | 2021-02-01 | 2021-02-15 | 2021-03-01 | 2021-03-15 |  | 2021-02-05 | 2021-02-19 | 2021-02-25 | -2.6 | 1 | 0 | 0 | 0 | 2 | 3 | 1 | 0 | 0 | 0 | 83% | 1 | 1 | 1 | 0 | 0 | 0 | 91% | 11 | 11 | 5 | #N/A | #N/A | 11 | 5 | 22
| 4 | R1WL-52119 | 2021-02-01 | 2021-02-15 | 2021-03-01 | 2021-03-15 |  | 2021-02-15 | 2021-03-04 | 2021-03-12 | -0.4 | 1 | 0 | 0 | 0 | 2 | 3 | 1 | 0 | 0 | 0 | 83% | 1 | 1 | 1 | 0 | 0 | 0 | 91% | 11 | 11 | 5 | #N/A | #N/A | 14 | 7 | 22
| 5 | R1WL-52115 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-22 |  | 2021-02-15 | 2021-02-25 | 2021-03-12 | -1.4 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 91% | 1 | 1 | 1 | 0 | 0 | 0 | 91% | 11 | 11 | 5 | #N/A | #N/A | 9 | 12 | 22
| 6 | R1WL-52114 | 2021-02-08 | 2021-02-22 | 2021-03-08 | 2021-03-22 |  | 2021-02-15 | 2021-02-05 | 2021-03-04 | -2.6 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 91% | 1 | 1 | 1 | 0 | 0 | 0 | 91% | 11 | 11 | 5 | #N/A | #N/A | -7 | 20 | 22
| 1 | L2WL-55139 | 2020-12-07 | 2021-01-04 | 2021-01-11 | 2021-01-11 |  | 2021-01-06 | 2021-01-11 | 2021-01-11 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 4 | 1 | 7
| 2 | L2WL-55133 | 2020-12-14 | 2021-01-11 | 2021-01-18 | 2021-01-18 |  | 2021-01-26 | 2021-02-17 | 2021-02-17 | 4.3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 44 | 29 | 0 | 71% | 0 | 1 | 0 | 6 | 5 | 0 | 94% | 6 | 1 | 5 | #N/A | #N/A | 17 | 1 | 7
| 3 | L2WL-55134 | 2020-12-14 | 2021-01-11 | 2021-01-18 | 2021-01-18 |  | 2021-02-09 | 2021-02-18 | 2021-02-18 | 4.4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 43 | 28 | 0 | 71% | 0 | 2 | 0 | 8 | 5 | 0 | 93% | 6 | 1 | 5 | #N/A | #N/A | 8 | 1 | 7
| 4 | L2WL-55143 | 2021-01-04 | 2021-01-18 | 2021-02-08 | 2021-02-08 |  | 2021-01-26 | 2021-02-26 | 2021-02-26 | 2.6 | 0 | 0 | 0 | 1 | 42 | 10 | 2 | 16 | 16 | 1 | 83% | 18 | 10 | 1 | 5 | 3 | 2 | 92% | 16 | 1 | 5 | #N/A | #N/A | 24 | 1 | 17
| 5 | L2WL-55144 | 2021-01-04 | 2021-01-18 | 2021-02-08 | 2021-02-08 |  | 2021-02-17 | 2021-03-05 | 2021-03-05 | 3.6 | 0 | 0 | 0 | 1 | 0 | 23 | 0 | 27 | 68 | 0 | 69% | 0 | 19 | 0 | 8 | 7 | 0 | 91% | 16 | 1 | 5 | #N/A | #N/A | 13 | 1 | 17
| 6 | L2WL-55136 | 2021-01-11 | 2021-01-25 | 2021-02-01 | 2021-02-01 |  | 2021-01-13 | 2021-02-05 | 2021-02-05 | 0.6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 18 | 1 | 7
| 7 | L2WL-55137 | 2021-01-11 | 2021-01-25 | 2021-02-01 | 2021-02-01 |  | 2021-01-13 | 2021-02-05 | 2021-02-05 | 0.6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 18 | 1 | 7
| 8 | L2WL-55138 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-01-20 | 2021-02-05 | 2021-02-05 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 13 | 1 | 7
| 9 | L2WL-55141 | 2021-01-18 | 2021-02-01 | 2021-02-08 | 2021-02-08 |  | 2021-01-20 | 2021-02-05 | 2021-02-05 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 95% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 13 | 1 | 7
| 10 | L2WL-55142 | 2021-01-25 | 2021-02-08 | 2021-02-22 | 2021-02-22 |  | 2021-02-10 | 2021-02-19 | 2021-02-19 | -0.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 97% | 0 | 0 | 0 | 1 | 0 | 0 | 99% | 11 | 1 | 5 | #N/A | #N/A | 8 | 1 | 12
| 11 | L2WL-55135 | 2021-01-25 | 2021-02-08 | 2021-02-15 | 2021-02-15 |  | 2021-03-11 | 2021-03-19 | 2021-03-19 | 4.6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 97% | 0 | 0 | 0 | 1 | 0 | 0 | 99% | 6 | 1 | 5 | #N/A | #N/A | 7 | 1 | 7
| 12 | L2WL-55140 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-02-22 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | -1.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 6 | 1 | 5 | #N/A | #N/A | 1 | 1 | 7
| 1 | K3WS-54783 | 2020-11-16 | 2020-11-30 | 2020-12-21 | 2021-01-25 |  | 2020-12-03 | 2021-01-25 | 2021-03-09 | 6.1 | 0 | 0 | 0 | 1 | 46 | 10 | 41 | 46 | 141 | 10 | 71% | 7 | 7 | 15 | 14 | 56 | 3 | 89% | 16 | 26 | 5 | #N/A | #N/A | 38 | 32 | 42
| 2 | K3WS-54791 | 2020-11-30 | 2020-12-14 | 2021-01-18 | 2021-02-08 |  | 2020-12-16 | 2021-01-27 | 2021-03-24 | 6.3 | 0 | 0 | 0 | 1 | 11 | 7 | 15 | 15 | 63 | 5 | 88% | 2 | 0 | 1 | 3 | 11 | 0 | 98% | 26 | 16 | 5 | #N/A | #N/A | 31 | 41 | 42
| 3 | K3WS-54784 | 2020-11-30 | 2020-12-14 | 2021-01-18 | 2021-02-08 |  | 2020-12-18 | 2021-01-28 | 2021-03-12 | 4.6 | 0 | 0 | 0 | 1 | 12 | 8 | 16 | 17 | 63 | 6 | 88% | 3 | 0 | 1 | 4 | 19 | 1 | 97% | 26 | 16 | 5 | #N/A | #N/A | 30 | 32 | 42
| 4 | K3WS-54792 | 2020-11-30 | 2020-12-14 | 2021-01-18 | 2021-02-08 |  | 2021-01-11 | 2021-02-01 | 2021-03-16 | 5.1 | 0 | 0 | 0 | 1 | 12 | 7 | 17 | 17 | 68 | 6 | 87% | 4 | 0 | 1 | 3 | 23 | 0 | 97% | 26 | 16 | 5 | #N/A | #N/A | 16 | 32 | 42
| 5 | K3WS-54790 | 2020-11-30 | 2020-12-14 | 2021-01-18 | 2021-02-08 |  | 2021-01-13 | 2021-02-04 | 2021-03-31 | 7.3 | 0 | 0 | 0 | 1 | 12 | 9 | 21 | 19 | 68 | 6 | 86% | 3 | 1 | 1 | 3 | 20 | 0 | 97% | 26 | 16 | 5 | #N/A | #N/A | 17 | 40 | 42
| 6 | K3WS-54788 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-15 |  | 2021-01-15 | 2021-02-05 | 2021-04-06 | 7.1 | 0 | 0 | 0 | 1 | 10 | 4 | 3 | 4 | 28 | 3 | 94% | 3 | 1 | 1 | 7 | 22 | 0 | 96% | 16 | 16 | 5 | #N/A | #N/A | 16 | 43 | 32
| 7 | K3WS-54789 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-15 |  | 2021-01-21 | 2021-02-09 | 2021-04-06 | 7.1 | 0 | 0 | 0 | 1 | 10 | 4 | 3 | 4 | 28 | 3 | 94% | 1 | 2 | 1 | 3 | 7 | 0 | 98% | 16 | 16 | 5 | #N/A | #N/A | 14 | 41 | 32
| 8 | K3WS-54793 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-15 |  | 2021-01-25 | 2021-02-09 | 2021-02-12 | -0.4 | 1 | 0 | 0 | 0 | 1 | 1 | - | 3 | 22 | - | 93% | 0 | 2 | 0 | 2 | 7 | - | 97% | 16 | 16 | 5 | #N/A | #N/A | 12 | 4 | 32
| 9 | K3WS-54787 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-15 |  | 2021-01-27 | 2021-02-10 | 2021-03-30 | 6.1 | 0 | 0 | 0 | 1 | 10 | 6 | 3 | 9 | 31 | 3 | 94% | 0 | 0 | 2 | 4 | 6 | 0 | 98% | 16 | 16 | 5 | #N/A | #N/A | 11 | 35 | 32
| 10 | K3WS-54786 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-15 |  | 2021-01-29 | 2021-02-11 | 2021-03-12 | 3.6 | 0 | 0 | 0 | 1 | 10 | 6 | 3 | 14 | 38 | 4 | 92% | 0 | 0 | 3 | 5 | 7 | 0 | 98% | 16 | 16 | 5 | #N/A | #N/A | 10 | 22 | 32
| 11 | K3WS-54785 | 2020-12-21 | 2021-01-04 | 2021-01-25 | 2021-02-15 |  | 2021-02-03 | 2021-02-19 | 2021-03-19 | 4.6 | 0 | 0 | 0 | 1 | 10 | 6 | 4 | 16 | 51 | 6 | 91% | 0 | 2 | 6 | 7 | 8 | 1 | 97% | 16 | 16 | 5 | #N/A | #N/A | 13 | 21 | 32

## Email Distribution
This distribution list will be added to all Announcement and Change emails. The emails will be saved to your draft folder. You can add additional (program specific) recipients and attachments to the email before pressing send. You can add to the bottom of this list.
Role | Email
PBE Manager | anthony.schoenherr@stellantis.com
Build Lead Manager | jim.sovis@stellantis.com
Body Supervisor | michael.moulton@stellantis.com
Int/Ext Supervisor | musharraf.nazir@stellantis.com
Chassis Supervisor | shafqat.bhatti@stellantis.com
Electrical Supervisor | juan.martinez9@stellantis.com
Engine Systems Supervisor | herb.white@stellantis.com
Powertrain Supervisor | david.ashley@stellantis.com
BOM Lead | shelly.frye@external.stellantis.com
Bridge Design Manager | steve.costello@stellantis.com
Mule/Proto ESG | jeffrey.lindgren@external.stellantis.com
Mule/Proto IPC | lakshminivasan.venkatesan@external.stellantis.com