## Summary
PPPM Program Managers | In-Process Events | [15 empty] | Completed Events
| Events | Total No. of Parts | % Reqs | % PO | % Rec'd | % RFQ Pending | # RFQ Sent | # REQ Submitted | # PO Issued | # Parts Received | Cost | % On Time | # Parts On Time | # Parts on Exception | # Parts Late | Timing Status Not Defined | Events | Total No. of Parts | % Reqs | % PO | % Rec'd | % RFQ Pending | # RFQ Sent | # REQ Submitted | # PO Issued | # Parts Received | Cost | % On Time | # Parts On Time | # Parts on Exception | # Parts Late | Timing Status Not Defined
Kelli Rodenbo
Mark Ballo
UNASSIGNED
Total
PPPM Engineers | In-Process Events | [15 empty] | Completed Events
| Events | Total No. of Parts | % Reqs | % PO | % Rec'd | % RFQ Pending | # RFQ Sent | # REQ Submitted | # PO Issued | # Parts Received | Cost | % On Time | # Parts On Time | # Parts on Exception | # Parts Late | Timing Status Not Defined | Events | Total No. of Parts | % Reqs | % PO | % Rec'd | % RFQ Pending | # RFQ Sent | # REQ Submitted | # PO Issued | # Parts Received | Cost | % On Time | # Parts On Time | # Parts on Exception | # Parts Late | Timing Status Not Defined
Brandi Wingate
Diana Stroebe
Eric Gierc
Jim Crile
Terry Costyk
Umair Tahir
Anurag Bansal
Ashritha Chandupatla
Rajatha Ramesh
UNASSIGNED
Total
Event Types | In-Process Events | [15 empty] | Completed Events
| Events | Total No. of Parts | % Reqs | % PO | % Rec'd | % RFQ Pending | # RFQ Sent | # REQ Submitted | # PO Issued | # Parts Received | Cost | % On Time | # Parts On Time | # Parts on Exception | # Parts Late | Timing Status Not Defined | Events | Total No. of Parts | % Reqs | % PO | % Rec'd | % RFQ Pending | # RFQ Sent | # REQ Submitted | # PO Issued | # Parts Received | Cost | % On Time | # Parts On Time | # Parts on Exception | # Parts Late | Timing Status Not Defined
PWB
QAF
DVPR
MEDIA
TTO
Safety
Dyno
Other
Total
Event Status | In-Process Events | [15 empty] | Completed Events
| Events | Total No. of Parts | % Reqs | % PO | % Rec'd | % RFQ Pending | # RFQ Sent | # REQ Submitted | # PO Issued | # Parts Received | Cost | % On Time | # Parts On Time | # Parts on Exception | # Parts Late | Timing Status Not Defined | Events | Total No. of Parts | % Reqs | % PO | % Rec'd | % RFQ Pending | # RFQ Sent | # REQ Submitted | # PO Issued | # Parts Received | Cost | % On Time | # Parts On Time | # Parts on Exception | # Parts Late | Timing Status Not Defined
In-Process
Complete
On Hold
Cancelled
Total

## Events
VF | MY | Event Name | Event Type | Event Title | Earliest MRD | Event Status | Program Manager | Requestor | WBS Code | Location of Event | Ship-to Code | Ship-to Address | Attention-to | Notes | Total # of Parts | % REQ | % PO | % Received | Cost | % Cancelled | # REQ Submitted | # PO Issued | # Parts Received | # Cancelled | # On Time | # Exception | # Late | # Not Defined | % On Time | % Exception | % Late | % Not Defined | #in RFQ Pending | #in REQ | #in PO | #in Rec'd | Date Added | Initial Part #s | Tracker URL
DT | 2022 | PWB | PWB | 2022 DT PWB | 2020-09-07 | In-Process | Kelli Rodenbo |  | VD00432_ELEC_ELPO | [5 empty] | 65 | 100% | 100% | 85% | 15106 | 0% | 65 | 65 | 55 | 0 | 0 | 0 | 0 | 65 | 0% | 0% | 0% | 100% | 0 | 0 | 10 | 55 | 2020-11-11 | 65 | https://docs.google.com/spreadsheets/d/1mJEmsecYF978TepwXuKD9_BtXBgc2iLyby0UZE946RE/
WS | 2022 | PS EXT | QAF | 2022 WS PS EXT QAF | 2021-01-29 | In-Process | Kelli Rodenbo | Joe Fazzari | VD00228_MGNM_VPVH | WTAP Metlab |  | 22318 Mound Rd) | Mike O'Neill |  | 89 | 100% | 1% | 0% | 0 | 0% | 89 | 1 | 0 | 0 | 0 | 0 | 0 | 89 | 0% | 0% | 0% | 100% | 0 | 88 | 1 | 0 | 2020-11-13 | 102 | https://docs.google.com/spreadsheets/d/1OaReSWtzHvppJ8KAgYXlh6aPBDPkpbqUMXen3g4Uiwg/
WS | 2022 | PS INT QAF | QAF | 2022 WS PS INT QAF | 2021-01-29 | In-Process | Kelli Rodenbo | Kathleen Todd | VD00228_MGNM_VPVH | WTAP Metlab |  | 22318 Mound Rd | Dan Campbell |  | 348 | 26% | 9% | 0% | 621 | 0% | 91 | 33 | 0 | 0 | 0 | 0 | 0 | 348 | 0% | 0% | 0% | 100% | 257 | 58 | 33 | 0 | 2020-11-13 | 357 | https://docs.google.com/spreadsheets/d/1eWTncCmisvzk1CD72R-2Hq5XH-UeCXQ20NmnkpbPCMc/
WD | 2021 | Pursuit PS QAF | QAF | 2021 WD Pursuit PS QAF | 2020-10-19 | Archived | Kelli Rodenbo | Elizabeth Amato |  | JNAP |  |  |  |  | 117 | 100% | 100% | 100% | 0 | 0% | 117 | 117 | 117 | 0 | 114 | 3 | 0 | 0 | 97.44% | 2.564% | 0% | 0% | 0 | 0 | 0 | 117 | 2020-10-09 07:50 |  | https://docs.google.com/spreadsheets/d/1dxDuCg0xuAoWITy76afUlnV1gz_Hfa0-mmCdX0TgysA/
WD | 2021 | Media Spare Parts | MEDIA | 2021 WD Media Spare Parts | 2020-10-26 | Archived | Kelli Rodenbo | Matt Ramey |  | FREC |  |  |  |  | 30 | 100% | 100% | 100% | 0 | 0% | 30 | 30 | 30 | 0 | 30 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 30 | 2020-10-09 09:08 | 35 | https://docs.google.com/spreadsheets/d/1XxeGfodHYGHNJ3-ndqtU-TDRvERjq1qPxhZ3xLIpCKE/
WL74 | 2022 | PHEV VPA QAF | QAF | 2022 WL74 PHEV VPA QAF | 2020-11-09 | Archived | Mark Ballo | John Mark Tarbunas, Nick Antovski, Chantal Saade | VD00194 | FCA Detroit Assy Complex MACK |  | 11570 E Warren Ave, Detroit, MI 48214 | John Mark Tarbunas |  | 5 | 100% | 100% | 100% | 1436.37 | 28.57% | 5 | 5 | 5 | 2 | 5 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 5 | 2020-09-22 | 6 | https://docs.google.com/spreadsheets/d/1iZEpr0VcUlI-mkTiFQznHK3zrWMj9dCiPruXDfL_sYM/
WL75 | 2021 | Sled Series | Safety | 2021 WL75 Sled Series | 2020-12-15 | In-Process | Mark Ballo | Sikyeon Kim | VD00192 | CPG | 1252 | 3700 SOUTH M 52, CHELSEA, MI 48118 | Sikyeon Kim | Migrated from SharePoint Series 6 and beyond | 191 | 100% | 100% | 26% | 54973 | 0% | 191 | 191 | 49 | 0 | 51 | 0 | 0 | 140 | 27% | 0% | 0% | 73% | 0 | 0 | 142 | 49 | 2020-11-24 | 94 | https://docs.google.com/spreadsheets/d/1IBcdi-kQUDixYTQOvk_VmZ1W6PyG-1S5DBOmYnhtSdU/
DT | 2024 | 5.7L DYNO | Dyno | 2024 DT 5.7L DYNO | 2021-01-11 | In-Process | Kelli Rodenbo | Troy Largo | VD00589 | CTC 1C Stockroom | 1250 |  | Jeff Forsman |  | 29 | 41% | 24% | 0% | 702 | 0% | 12 | 7 | 0 | 0 | 12 | 0 | 0 | 17 | 41% | 0% | 0% | 59% | 17 | 5 | 7 | 0 | 2020-11-24 |  | https://docs.google.com/spreadsheets/d/18-YOwjBTErTwPGF7Tyht_VqxQV9RWbs1-f7Nj7EO6-M/
DT | 2024 | 3.6L DYNO | Dyno | 2024 DT 3.6L DYNO | 2021-01-11 | In-Process | Kelli Rodenbo | Troy Largo | VD00586 | CTC 1C Stockroom | 1250 |  | Jeff Forsman |  | 60 | 0% | 0% | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0% | 0% | 0% | 100% | 60 | 0 | 0 | 0 | 2020-11-24 |  | https://docs.google.com/spreadsheets/d/1_aNs7BQzRQQPLYvdhcwQM7AWqiNG7tdA33P4c7UVZ78/
RU | 2022 | IP DV Test | DVPR | 2022 RU IP DV Test | 2021-01-15 | In-Process | Mark Ballo | Mangesh Atre John Jezuit | VD00483 | Dakkota Systems | 59967 | 490 Richard Rushton Dr., Tecumseh ONT N8N 0A9 | Vlada Jovanovic |  | 59 | 0% | 0% | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0% | 0% | 0% | 95% | 59 | 0 | 0 | 0 | 2020-12-03 | 59 | https://docs.google.com/spreadsheets/d/1LkO_bKKItbruJzXW3Evit61dtavxqnYRQgTaiXtjVe0/
XX | 2025 | Sample Event | TTO | 2025 XX Sample Event | 2025-04-15 | In-Process | Kelli Rodenbo | John Doe | VD00194 | CPG | 1250 | 12501 Chrysler Dr. | Jane Dao | Random Comments | 95 | 0% | 0% | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 55 | 23 | 17 | 0 | 58% | 24% | 18% | 0% | 95 | 0 | 0 | 0 | 2020-12-03 | 562 | https://docs.google.com/spreadsheets/d/14WIsmqz9cAjpAl_qlvghLPhHARFvJjtfF1JJIodAI7k/
DT | 2024 | GMET6 SO Beta DYNO | Dyno | 2024 DT GMET6 SO Beta DYNO | 2021-02-12 | In-Process | Kelli Rodenbo | Troy Largo | VD00589 | CTC 1C Stockroom | 1250 |  | Jeff Forsman |  | 0 | 0% | 0% | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 2020-12-09 | 75 | https://docs.google.com/spreadsheets/d/1-Qtl9RcTpJNKnYm0PAI8Pe7Ea8zEnQWLv2UOm9MpPXI/
DT | 2024 | GMET6 HO Beta DYNO | Dyno | 2024 DT GMET6 HO Beta DYNO | 2021-04-05 | In-Process | Kelli Rodenbo | Troy Largo | VD00589 | CTC 1C Stockroom | 1250 |  | Matt Sanborn |  | 0 | 0% | 0% | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 2020-12-09 | 94 | https://docs.google.com/spreadsheets/d/1OZCiuyxd6LJoEoLIQzKz2rgDY-DHbgAnjtIfNchzfO4/
XY | 2025 | Sample Event | PWB | 2025 XY Sample Event | 2021-04-15 | In-Process | Kelli Rodenbo | Mike Moulton | VD00194 | [5 empty] | 95 | 87% | 66% | 0% | 0 | 0% | 83 | 63 | 0 | 0 | 0 | 0 | 0 | 95 | 0% | 0% | 0% | 100% | 12 | 20 | 63 | 0 | 2020-12-09 |  | https://docs.google.com/spreadsheets/d/1LFuT3ZTXJ4zmFexLrE3DtarmPDNPSArGpkm-Mb_vsRs/

## Tracker Data
VF | Event Title | Tab | Event Title - Tab | Event Status | Program Manager | PPPM Engineer | MRD | Days until MRD | Total # of Parts | % REQ | % PO | % Received | Cost | % Cancelled | # REQ Submitted | # PO Issued | # Parts Received | # Cancelled | # On Time | # Exception | # Late | # Not Defined | % On Time | % Exception | % Late | % Not Defined | #in RFQ Pending | #in REQ | #in PO | #in Rec'd | Tracker URL
XY | 2025 XY Sample Event | Chassis | 2025 XY Sample Event - Chassis | Active | Kelli Rodenbo | Anurag Bansal | 2021-04-15 | 122 | 95 | 83.2% | 62.1% | 0% | 0 | 0% | 79 | 59 | 0 | 0 | 0 | 0 | 0 | 95 | 0% | 0% | 0% | 100% | 16 | 20 | 59 | 0 | https://docs.google.com/spreadsheets/d/1LFuT3ZTXJ4zmFexLrE3DtarmPDNPSArGpkm-Mb_vsRs/
XX | 2025 XX Sample Event | Sample Sheet | 2025 XX Sample Event - Sample Sheet | Active | Kelli Rodenbo | Anurag Bansal | 2021-01-21 | 38 | 95 | 0% | 0% | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 55 | 23 | 17 | 0 | 57.9% | 24.2% | 17.9% | 0% | 95 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/14WIsmqz9cAjpAl_qlvghLPhHARFvJjtfF1JJIodAI7k/
DT | 2024 DT GMET6 HO Beta DYNO | Beta TRACKER | 2024 DT GMET6 HO Beta DYNO - Beta TRACKER | Upcoming | Kelli Rodenbo | Ashritha Chandupatla | 2021-04-05 | 112 | 0 | 0% | 0% | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1OZCiuyxd6LJoEoLIQzKz2rgDY-DHbgAnjtIfNchzfO4/
DT | 2024 DT GMET6 SO Beta DYNO | Beta Tracker | 2024 DT GMET6 SO Beta DYNO - Beta Tracker | Upcoming | Kelli Rodenbo | Umair Tahir | 2021-02-12 | 60 | 0 | 0% | 0% | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1-Qtl9RcTpJNKnYm0PAI8Pe7Ea8zEnQWLv2UOm9MpPXI/
RU | 2022 RU IP DV Test | RU IP DV TEST PARTS | 2022 RU IP DV Test - RU IP DV TEST PARTS | Upcoming | Mark Ballo | <PPPM ENGINEER> | 2021-01-15 | 32 | 59 | 0% | 0% | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0% | 0% | 0% | 100% | 59 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1LkO_bKKItbruJzXW3Evit61dtavxqnYRQgTaiXtjVe0/
DT | 2024 DT 3.6L DYNO | PPPM Tracker | 2024 DT 3.6L DYNO - PPPM Tracker | Upcoming | Kelli Rodenbo | Terry Costyk | 2021-01-11 | 28 | 60 | 0% | 0% | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0% | 0% | 0% | 100% | 60 | 0 | 0 | 0 | https://docs.google.com/spreadsheets/d/1_aNs7BQzRQQPLYvdhcwQM7AWqiNG7tdA33P4c7UVZ78/
DT | 2024 DT 5.7L DYNO | PPPM Tracker | 2024 DT 5.7L DYNO - PPPM Tracker | Active | Kelli Rodenbo | Anurag Bansal | 2021-01-11 | 28 | 29 | 41.4% | 24.1% | 0% | 701.92 | 0% | 12 | 7 | 0 | 0 | 12 | 0 | 0 | 17 | 41.4% | 0% | 0% | 58.6% | 17 | 5 | 7 | 0 | https://docs.google.com/spreadsheets/d/18-YOwjBTErTwPGF7Tyht_VqxQV9RWbs1-f7Nj7EO6-M/
WL75 | 2021 WL75 Sled Series | Series 6 | 2021 WL75 Sled Series - Series 6 | Active | Mark Ballo | Anurag Bansal | 2020-12-15 | 1 | 66 | 100% | 100% | 36.4% | 48370.16 | 0% | 66 | 66 | 24 | 0 | 26 | 0 | 0 | 40 | 39.4% | 0% | 0% | 60.6% | 0 | 0 | 42 | 24 | https://docs.google.com/spreadsheets/d/1IBcdi-kQUDixYTQOvk_VmZ1W6PyG-1S5DBOmYnhtSdU/
WL75 | 2021 WL75 Sled Series | Series 7 | 2021 WL75 Sled Series - Series 7 | Upcoming | Mark Ballo | Anurag Bansal | 2021-01-15 | 32 | 63 | 100% | 100% | 20.6% | 5944.24 | 0% | 63 | 63 | 13 | 0 | 13 | 0 | 0 | 50 | 20.6% | 0% | 0% | 79.4% | 0 | 0 | 50 | 13 | https://docs.google.com/spreadsheets/d/1IBcdi-kQUDixYTQOvk_VmZ1W6PyG-1S5DBOmYnhtSdU/
WL75 | 2021 WL75 Sled Series | Series 8 | 2021 WL75 Sled Series - Series 8 | Upcoming | Mark Ballo | Anurag Bansal | 2021-02-15 | 63 | 62 | 100% | 100% | 19.4% | 658.8 | 0% | 62 | 62 | 12 | 0 | 12 | 0 | 0 | 50 | 19.4% | 0% | 0% | 80.6% | 0 | 0 | 50 | 12 | https://docs.google.com/spreadsheets/d/1IBcdi-kQUDixYTQOvk_VmZ1W6PyG-1S5DBOmYnhtSdU/
WL74 | 2022 WL74 PHEV VPA QAF | PPPM | 2022 WL74 PHEV VPA QAF - PPPM | Complete | Mark Ballo | Anurag Bansal | 2020-11-09 | -35 | 5 | 100% | 100% | 100% | 1436.37 | 28.6% | 5 | 5 | 5 | 2 | 5 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 5 | https://docs.google.com/spreadsheets/d/1iZEpr0VcUlI-mkTiFQznHK3zrWMj9dCiPruXDfL_sYM/
WD | 2021 WD Media Spare Parts | SpareParts | 2021 WD Media Spare Parts - SpareParts | Complete | Kelli Rodenbo | Jim Crile | 2020-10-26 | -49 | 30 | 100% | 100% | 100% | 0 | 0% | 30 | 30 | 30 | 0 | 30 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 30 | https://docs.google.com/spreadsheets/d/1XxeGfodHYGHNJ3-ndqtU-TDRvERjq1qPxhZ3xLIpCKE/
WD | 2021 WD Pursuit PS QAF | INTERIOR | 2021 WD Pursuit PS QAF - INTERIOR | Complete | Kelli Rodenbo | Umair Tahir | 2020-10-19 | -56 | 117 | 100% | 100% | 100% | 0 | 0% | 117 | 117 | 117 | 0 | 114 | 3 | 0 | 0 | 97.4% | 2.6% | 0% | 0% | 0 | 0 | 0 | 117 | https://docs.google.com/spreadsheets/d/1dxDuCg0xuAoWITy76afUlnV1gz_Hfa0-mmCdX0TgysA/
WS | 2022 WS PS INT QAF | IP/ Hard Trim | 2022 WS PS INT QAF - IP/ Hard Trim | Active | Kelli Rodenbo | Diana Stroebe | 2021-01-29 | 46 | 104 | 32.7% | 31.7% | 0% | 0 | 0% | 34 | 33 | 0 | 0 | 0 | 0 | 0 | 104 | 0% | 0% | 0% | 100% | 70 | 1 | 33 | 0 | https://docs.google.com/spreadsheets/d/1eWTncCmisvzk1CD72R-2Hq5XH-UeCXQ20NmnkpbPCMc/
WS | 2022 WS PS INT QAF | Console/ Door Mods & Trim/ Wiring | 2022 WS PS INT QAF - Console/ Door Mods & Trim/ Wiring | Active | Kelli Rodenbo | Eric Gierc | 2021-01-29 | 46 | 112 | 46.4% | 0% | 0% | 620.8 | 0% | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 0% | 0% | 0% | 100% | 60 | 52 | 0 | 0 | https://docs.google.com/spreadsheets/d/1eWTncCmisvzk1CD72R-2Hq5XH-UeCXQ20NmnkpbPCMc/
WS | 2022 WS PS INT QAF | Seats/ Headliner/ Misc | 2022 WS PS INT QAF - Seats/ Headliner/ Misc | Active | Kelli Rodenbo | Rajatha Ramesh | 2021-01-29 | 46 | 132 | 3.8% | 0% | 0% | 0 | 0% | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 0% | 0% | 0% | 100% | 127 | 5 | 0 | 0 | https://docs.google.com/spreadsheets/d/1eWTncCmisvzk1CD72R-2Hq5XH-UeCXQ20NmnkpbPCMc/
WS | 2022 WS PS EXT QAF | Tracker | 2022 WS PS EXT QAF - Tracker | Active | Kelli Rodenbo | Terry Costyk | 2021-01-29 | 46 | 89 | 100% | 1.1% | 0% | 0 | 0% | 89 | 1 | 0 | 0 | 0 | 0 | 0 | 89 | 0% | 0% | 0% | 100% | 0 | 88 | 1 | 0 | https://docs.google.com/spreadsheets/d/1OaReSWtzHvppJ8KAgYXlh6aPBDPkpbqUMXen3g4Uiwg/
DT | 2022 DT PWB | ELECTRICAL | 2022 DT PWB - ELECTRICAL | Active | Kelli Rodenbo | Eric Gierc | 2020-09-07 | -98 | 65 | 100% | 100% | 84.6% | 15105.97 | 0% | 65 | 65 | 55 | 0 | 0 | 0 | 0 | 65 | 0% | 0% | 0% | 100% | 0 | 0 | 10 | 55 | https://docs.google.com/spreadsheets/d/1mJEmsecYF978TepwXuKD9_BtXBgc2iLyby0UZE946RE/